## west circle
BESCOM Project-construction of Overhead Distribution Lines
LC Schedule from 11.02.13 to 16.02.13
SL.NO | DATE | DAY | CIRCLE NAME | SUB-DIVISION | MUSS | FEEDER # | ACTIVITY | UOM | QUANTITY | LC DURATION | Areas Affected
1 | 11.02.13 | MONDAY | WEST | N2 | CHANDRA LAYOUT | F2 | ABC | MTM | 350 | 11 am-5 pm | Kalyana nagara, BDA L/o, Chandra Layout, Bapuji layout, Vyalikaval Layout, Rajeevgandhi Layout, GKW Layout, PF Layout, Marenahalli part, Shivananda Nagar, Anubhava Nagar,
|  |  |  | K1 | BM | F10 | ABC CHARGING | MTM | 1000 | 11 am-5 pm | Komaghatta,Sulikere & Surrounding Villages
|  |  |  | K1 | KG | F4 | ABC | MTM | 500 | 11 am-5 pm | Ramohalli,Vinayakanagara,Marigundanahalli,Gulaganchanahalli,Krishnasagara
2 | 12.02.13 | TUESDAY | WEST | N2 | CHANDRA LAYOUT | F8 | ABC | MTM | 350 | 11 am-5 pm | Chandra Layout part, SBI Bank surrounding area, Jyothinagar, Maruthinagar, Vidyagirilayout, Income Tax L/O part, Binnylayout part, Siddaganga school surrounding area.
|  |  |  | K1 | BM | F11 | ABC CHARGING | MTM | 1000 | 11 am-5 pm | Kengerei upanagara,Vinayakaqnagar 8th mian,Gandhinagara & Surrounding
|  |  |  | K1 | BM | F3/F1 | CUT POINT | NO'S | 2 | 11 am-5 pm | KHB LAYOUT(CENTRAL BLOACK) & KHB LAYOUT (NORTH BLOCK)
3 | 13.02.13 | WEDNESDAY | WEST | N2 | NRS | F18 | ABC | MTM | 325 | 11 am-5 pm | Amarajyothi nagar, Sraswathi nagara, Marenahalli, Secretariate layout, MC layout, Byanna Indl.estate, Telephone exchange, Central excise layout, Vinayaka layout
|  |  |  | K1 | SRV | F4 | ABC CHARGING | MTM | 1000 | 11 am-5 pm | Sir M V Layout & nSurrounding areas
4 | 14.02.13 | THURSDAY | WEST | N2 | VIJAYA NAGAR | F8 | ABC | MTM | 325 | 11 am-5 pm | Thimmenahalli, Govindaraj nagarl part, KHB Colony, Prashanthnagar, Ranganathapura, Kamakshipalya part. HVR Layout, Syndicate Bank Colony and surrounding areas
|  |  |  | W7 | RRN | F14 | ABC CHARGING | MTM | 500 | 11 am-5 pm | Ideal Homes,Haridasa nagara,part of gattigere,Part of H V Halli,Part of kenchanahalli
|  |  |  | K1 | RRN | F9 | ABC CHARGING | MTM | 400 | 11 am-5 pm | BGS Hospitals,Bailsandra
5 | 15.02.13 | FRIDAY | WEST | N2 | NRS | F18 | ABC | MTM | 300 | 11 am-5 pm | Amarajyothi nagar, Sraswathi nagara, Marenahalli, Secretariate layout, MC layout, Byanna Indl.estate, Telephone exchange, Central excise layout, Vinayaka layout
|  |  |  | K1 | BM | F10 | ABC CHARGING | MTM | 1000 | 11 am-5 pm | Komaghatta,Sulikere & Surrounding Villages
6 | 16.02.13 | SATURDAY | WEST | N2 | CHANDRA LAYOUT | F1 | ABC | MTM | 300 | 11 am-5 pm | Widia layout, Marenahalli, IT layout, BHEL township, RPC layout, Attiguppe, Subbanna garden, Basaveshwara layout
|  |  |  | K1 | BM | F10 | ABC CHARGING | MTM | 1000 | 11 am-5 pm | Komaghatta,Sulikere & Surrounding Villages
|  |  |  | W6 | Vrishbhavathi | F4 | RMU CHARGING | NO'S | 1 | 11 am-5 pm | Jnanabharathi Campus

## South Circle
BESCOM Project-construction of Overhead Distribution Lines
LC Schedule from 11.02.13 to 16.02.13
SL.NO | DATE | DAY | CIRCLE NAME | SUB-DIVISION | MUSS | FEEDER # | ACTIVITY | UOM | QUANTITY | LC DURATION | Areas Affected
1 | 11.02.13 | MONDAY | SOUTH | S6 | SARAKKI | F21 | ABC LAYING | MTR. | 400 | 10am - 4pm | IG circle, Ayodhya nagar, 5th phase JP nagar
|  |  |  | S6 | SARAKKI | F21 | POLE ERECTION | NOS | 6 | 10am - 4pm
|  |  |  | S6 | SARAKKI | F21 | COYOTE | MTR. | 500 | 10am - 4pm
2 | 12.02.13 | TUESDAY | SOUTH | S11 | RMZ | F6 | ABC LAYING | MTR. | 575 | 10am - 4pm | Kaikondanahalli, Kasavanahalli, Bhovi Colony, Amurtha College, KPC Layout, SJR & Symphonia Apartment, Kristal Zaspero Layout, Lakeshore Home Layout
|  |  |  | S4 | ADUGODI | F27 | ABC CHARGING | MTR. | 500 | 10am - 4pm | Maruthinagar Main Rd, SJMC Qtrs, Jogi Colony, SPAR Hyper Market.
|  |  |  | S11 | RMZ | F6 | POLE ERECTION | NOS | 10 | 10am - 4pm | Kaikondanahalli, Kasavanahalli, Bhovi Colony, Amurtha College, KPC Layout, SJR & Symphonia Apartment, Kristal Zaspero Layout, Lakeshore Home Layout
3 | 13.02.13 | WEDNESDAY | SOUTH | S7 |  | KBH F5 K&C VALLEY | CUT POINT | NOS | 3 | 10am - 2pm | Panathur, Bhoganahalli, Kadubisanahalli, Panathur A.K.Colony, Kaverappa L/o, Munireddy L/o, Vikas telecom, Newhorizon college &
|  |  |  | S10 | BTM | F12 | ABC LAYING | MTR. | 500 | 10am - 4pm | Vijaya Bank Colony & Layout, IIMB, Telephone Exchange
|  |  |  | S10 | BTM | F12 | ABC CHARGING | MTR | 500 | 10am - 4pm
|  |  |  | S10 | BTM | F12 | POLE ERECTION | MTR. | 20 | 10am - 4pm
4 | 14.02.13 | THURSDAY | SOUTH | S3 | K&C VALLEY | F2&F3 | CUT POINT | NOS | 3 | 10am - 2pm | Innner Ring Road Area Srinivagilu Full, Ashwini layout & Amarjyothi L/O
|  |  |  | S6 | KHODAYS | F14 | AB CABLE LAYING | MTR. | 300 | 10am - 4pm | BDA Layout
|  |  |  | S6 | KHODAYS | F14 | AB CABLE CHARGING | MTR. | 300 | 10am - 4pm
|  |  |  | S6 | KHODAYS | F14 | POLE ERECTION | NOS | 6 | 10am - 4pm
5 | 15.02.13 | FRIDAY | SOUTH | S11 | SHOBHA | F7 | ABC | MTR | 400 | 10am - 4pm | Green land layout
|  |  |  | S11 | SHOBHA | F7 | PSC/RCC | NOS | 10 | 10am - 4pm
|  |  |  | S12 | RBI | F8 | ABC CHARGING | MTR | 400 | 10am - 4pm | Arekere-Mico L/O
6 | 16.02.13 | SATURDAY | SOUTH | S10 | BTM | F12 | ABC LAYING | MTRS | 500 | 10am - 4pm | Vijaya Bank Colony & Layout, IIMB, Telephone Exchange
|  |  |  | S10 | BTM | F12 | ABC CHARGING | MTR | 400 | 10am - 4pm
|  |  |  | S10 | BTM | F12 | POLE ERECTION | Nos | 5 | 10am - 4pm

## North Circle
BESCOM Project-construction of Overhead Distribution Lines
LC Schedule from 11.02.13 to 16.02.13
SL.NO | DATE | DAY | CIRCLE NAME | SUB-DIVISION | MUSS | FEEDER # | ACTIVITY | UOM | QUANTITY | LC DURATION | Areas Affected
1 | 11.02.13 | MONDAY | Hebbal | C7 | KHB | F4 | AB CABLE LAYING | MTRS | 200 | 10am - 4pm | Kenchenahally, Gatignahally, harohally, Suradenapura, Sadnahally, ISRO layout, Akashninar
|  |  |  | C7 | KHB | F4 | AB CABLE LAYING | MTRS | 200 | 10am - 4pm
|  |  |  | C7 | KHB | F4 | CHARGING OF ABC | MTRS | 200 | 10am - 4pm
|  |  | Hebbal | C4 | HEBBAL | F10& F8 | CUT POINT | NOS | 3 | 10am - 4pm | Shivashankarappa block, Guddadahally, Cholanayakanagally, Kupparaju Park, , Anandanagar 1st block, Dodamma layout, HEBBAL & Anandanagar, AGS layout, SBM colony, Baptist Hospital, Sumangali Ashrama, Parts of Guddahally etc.
|  |  | Peenya | N4 | BRI | F1 | RMU CHARGING | NO'S | 1 | 10am - 4pm | Peenya 3rd Stage,Peenya 4th Phase,
2 | 12.02.13 | TUESDAY |  | C7 | YELAHANKA | F4 | AB CABLE LAYING | MTRS | 200 | 10am - 4pm | YNK New town 208, 407, 'B' Sector, OB Sandra, Allalasandra, Saradhanagar, Janapriya, Anriya,
|  |  |  | C7 | YELAHANKA | F4 | AB CABLE LAYING | MTRS | 200 | 10am - 4pm
|  |  |  | C7 | YELAHANKA | F4 | CHARGING OF ABC | MTRS | 200 | 10am - 4pm
|  |  |  | C4 | HEBBAL | F7& F8 | CUT POINT | NOS | 3 | 10am - 4pm | CBI Mn Road, Parts of HMT layout, KHM block, Parts of MLA Layout, Shanthisagar Mn Road RT Nagar, Venugopala layout, Judges Colony, 80' Road, Vishveshwara Block, etc. & Shivashankarappa block, Guddadahally, Cholanayakanagally, Kupparaju Park, , Anandanagar 1st block, Dodamma layout, HEBBAL etc.
|  |  |  | N4 | BRI | F2 | RMU CHARGING | NO'S | 1 | 10am - 4pm | ABB, 7th main, Agro chem, GCL, Parl road,
3 | 13.02.13 | WEDNESDAY |  | C7 | KHB | F12 | AB CABLE LAYING | MTRS | 200 | 10am - 4pm | NAGARJUNA APT, MIG BLOCK, 5TH PHASE YNK NEW TOWN
|  |  |  | C7 | KHB | F12 | AB CABLE LAYING | MTRS | 200 | 10am - 4pm
|  |  |  | C7 | KHB | F12 | CHARGING OF ABC | MTRS | 200 | 10am - 4pm
|  |  |  | N4 | BRI | F9 | RMU CHARGING | NO'S | 1 | 10am - 4pm | SLV indl. Area, 2nd stage peenya
4 | 14.02.13 | THURSDAY |  | C7 | KHB | F4 | AB CABLE LAYING | MTRS | 200 | 10am - 4pm | Kenchenahally, Gatignahally, harohally, Suradenapura, Sadnahally, ISRO layout, Akashninar
|  |  |  | C7 | KHB | F4 | AB CABLE LAYING | MTRS | 200 | 10am - 4pm
|  |  |  | C7 | KHB | F4 | CHARGING OF ABC | MTRS | 200 | 10am - 4pm
|  |  |  | N4 | BRI | F7 | RMU CHARGING | NO'S | 1 | 10am - 4pm | GKW Layout, I.P. Nagar, Shambavinagar
5 | 15.02.13 | FRIDAY |  | C7 | YELAHANKA | F4 | AB CABLE LAYING | MTRS | 200 | 10am - 4pm | YNK New town 208, 407, 'B' Sector, OB Sandra, Allalasandra, Saradhanagar, Janapriya, Anriya,
|  |  |  | C7 | YELAHANKA | F4 | AB CABLE LAYING | MTRS | 200 | 10am - 4pm
|  |  |  | C7 | YELAHANKA | F4 | CHARGING OF ABC | MTRS | 200 | 10am - 4pm
|  |  |  | N4 | BRI | F1 | RMU CHARGING | NO'S | 1 | 10am - 4pm | Peenya 3rd Stage,Peenya 4th Phase,
6 | 16.02.13 | SATURDAY |  | C7 | KHB | F12 | AB CABLE LAYING | MTRS | 200 | 10am - 4pm | NAGARJUNA APT, MIG BLOCK, 5TH PHASE YNK NEW TOWN
|  |  |  | C7 | KHB | F12 | AB CABLE LAYING | MTRS | 200 | 10am - 4pm
|  |  |  | N4 | SRS | F21 | ABC | MTM | 300 | 10am - 4pm | 3rd phase, Kaveri nagar, Vidanasoudha layout, laxmi nagar.
|  |  |  | C7 | KHB | F12 | CHARGING OF ABC | MTRS | 200 | 10am - 4pm | NAGARJUNA APT, MIG BLOCK, 5TH PHASE YNK NEW TOWN

## East Circle
BESCOM Project-construction of Overhead Distribution Lines
LC Schedule from 11.02.13 to 16.02.13
SL.NO | DATE | DAY | CIRCLE NAME | SUB-DIVISION | MUSS | FEEDER # | ACTIVITY | UOM | QUANTITY | LC DURATION | Areas Affected
1 | 11.02.13 | MONDAY | EAST | E6 | LEELA PALACE | F10 | GOS | Nos | 2 | 10am - 2pm | NAL Compound, Kodihalli, 13th, 14th 'A' 16th 'C'main, Baba saheb colony, Puttappa layout, HAL 3rd stage, J.B.Nagar, LIC Qtrs.
|  |  |  | E5 | POTTERY ROAD | F1 | AB CABLE LAYING | MTRS | 200 | 10am - 4pm | M.S.Nagar, Jai Bharath Nagar, Nagayana Palya, Sathya Nagar, Ambedkar Nagar, Old Byappanahalli
2 | 12.02.13 | TUESDAY | EAST | E6 | LEELA PALACE | F12 | GOS | Nos | 2 | 10am - 2pm | Kodihalli Village, 17th, 18th 19th main, 100 feet road, Service road.
|  |  |  | E5 | POTTERY ROAD | F13 | AB CABLE LAYING | MTRS | 200 | 10am - 4pm | Jeevana Halli, MSO Colony, Raghavappa Garden, Muddappa Garden, ITC Colony, AK Colony, Slum area
3 | 13.02.13 | WEDNESDAY | EAST | E6 | LEELA PALACE | F14 | GOS | Nos | 3 | 10am - 4pm | INDRANAGAR 1 & 2ND STAGE,HAL 2ND STAGE,DOMLUR & SURROUNDING AREAS
|  |  |  | E5 | HBR | F4 | AB CABLE LAYING | MTRS | 200 | 10am - 4pm | Mayor Shankar Road,Kacharkana Halli, Jala Vayu Vihar, HRBR L/O, 2nd Block, 3rd Block, Behind BTS Depot, Ramaiah L/O, Harmony Apartment, Naga Devi Industries
4 | 14.02.13 | THURSDAY | EAST | E7 | ITI | F7 | GOS | Nos | 4 | 10am - 4pm | VB L/O, TC Palya, RMS Colony, Parvathi nagar
|  |  |  | E5 | POTTERY ROAD | F1 | AB CABLE LAYING | MTRS | 200 | 10am - 4pm | M.S.Nagar, Jai Bharath Nagar, Nagayana Palya, Sathya Nagar, Ambedkar Nagar, Old Byappanahalli
|  |  |  | E4 | ITI, Hoody | ITI F9,HOODY F10 | CUT POINT | NOS | 3 | 10am - 4pm | B.N.Pura, M.D.Pura, Ring Road, Ferns City, RR Layout, Kamadhenu Lyt, Munireddy Lyt, Chinnappa Lyt & G.C.Palya, R.H.B.Colony, Lakshmisagara, Saraswathinagar, Mahaeswarinagara, M.D.Pura Bande
|  |  |  | E5 | POTTERY ROAD | F13 | AB CABLE LAYING | MTRS | 200 | 10am - 4pm | Jeevana Halli, MSO Colony, Raghavappa Garden, Muddappa Garden, ITC Colony, AK Colony, Slum area
6 | 16.02.13 | SATURDAY | EAST | E7 | ITI | F7 | GOS | Nos | 2 | 10am - 2pm | VB L/O, TC Palya, RMS Colony, Parvathi nagar
|  |  |  | E4 | ITI, Hoody | ITI F9,HOODY F10 | CUT POINT | NOS | 3 | 10am - 4pm | B.N.Pura, M.D.Pura, Ring Road, Ferns City, RR Layout, Kamadhenu Lyt, Munireddy Lyt, Chinnappa Lyt & G.C.Palya, R.H.B.Colony, Lakshmisagara, Saraswathinagar, Mahaeswarinagara, M.D.Pura Bande
|  |  |  | E5 | HBR | F4 | AB CABLE LAYING | MTRS | 200 | 10am - 4pm | Mayor Shankar Road,Kacharkana Halli, Jala Vayu Vihar, HRBR L/O, 2nd Block, 3rd Block, Behind BTS Depot, Ramaiah L/O, Harmony Apartment, Naga Devi Industries