|  |  |  |
| --- | --- | --- |
| **Pkg No.** | **Contract Package – All turnkey basis** | **Physical progress as on Aug-2019** |
| **I** | **DAS System, Communication System & Control Center Facilities** | * DAS Master Station established and is in commercial operation. * Communication system established and is in commercial operation. * Network Operation Model (NOM) for nine division created. * Integration testing is in progress. * DAS acquiring data from 2551No’s sites (sites in Production system) and further 579No’s of sites (sites in testing system) are in configuration and development system. * Communication system training completed. * 11kV distribution network Operations for nine (HSR, Vidhanasoudha, Rajarajeshwarinagar, Malleshwaram, Indiranagar, Rajajinagar Shivajinagar, Peenya & Hebbal division) out of 12 Divisions is being carried out from control centre on 24X7 mode. * Revalidation of HSR division is completed. Jayanagara & Koramangala Division is in Progress. |
| **I** | Civil Infrastructure ( IA & IB ) | * The construction of DAS Control Center BICC1 at HSR Layout and BCC2 at Rajajinagar completed |
| **II** | Remote Terminal Units for RMUs ( IIA, IIB & IIC) | Delivered : 1590 No’s  Installed : 1590 No’s |
| **III** | Sectionalizers & Reclosers  (IIIA & IIIB) | Delivered: 795 LRCs & 745 LBS  Installed : 795 LRC & 745 LBS  Charged: 795 LRC & 745 LBS |
| **IV** | New Ring Main Units  (IVA, IVB & IVC) | Ordered Quantity:790No’s  Delivered: 790 No’s  Installed: 790 No’s  Commissioned: 790 No’s |
| **V** | New Ring Main Units in place of retrofitting  (VA & VB) | Ordered Quantity:800 No’s  Delivered: 800 No’s  Installed: 800 No’s  Commissioned:800 No’s |
| **VI** | Constn. Of Overhead Distribution Lines | Stringing of 698.6 KM coyote conductor, and 254.6 KM AB cable completed. |
| **VII** | Constn. Of Underground Distribution Lines | 228 KM of UG cable laid and commissioned |