DAS weekly Progress achieved upto 02.07.2016

| Sl No. | Particular | Package Description | Status |
| --- | --- | --- | --- |
| 1 | Package-I | DAS System Design | DAS system design and customization is completed. DAS Factory Acceptance Test (FAT) commenced. Communication system FAT completed. Configuration and Development System setup in BICC-1, HSR Layout, DAS & SG BESCOM office for training of BESCOM personnel. Substation model building of GIS data is completed. The details required for the integration of CCCS with DAS has been provided by DAS section to GM (CR) section. |
| 2 |  | Control Centers | Control Centre-1: All civil engineering works have been completed, except the following works which are in progress; Fire dampers Gas suppression system to server room, CH room and VPS enclosure. Control Centre-2: Building construction work is in progress. |
| 3 |  | Frequency Allocation | UHF: DL (Decision to grant license) for UHF frequency is issued by WPC (Wireless Planning & Coordination wing). WPC has issued Import License to import MARS Equipment of Communication system. Microwave: WPC has issued DL (Decision to grant license) for microwave frequency vide letter dated 28.07.2014. |
| 4 |  | Communication Towers | Tower Construction Status: 9 communication towers construction completed out of 11 towers. Radio modem and Antenna installation is in progress. Point to point testing of field equipments from C&DS(Configuration and Development System) server in control center has commenced |
| Sl No. | Package | Package Description | Name of the Contractor | Ordered Quantity | Allotted RMUs | RTUs Installed as on 02.07.2016 | RTUs Field Performance Test(FPT) as on 02.07.2016 |
| 1. | Package-II(A) | Remote Terminal Units for Existing and New Ring Main Units | M/s ABB | 700 | 699 | 687 | 660 |
| 2. | Package-II(B) |  | M/s CGL | 495 | 490 | 486 | 473 |
| 3. | Package-II(C) |  | M/s Efacec | 395 | 388 | 372 | 338 |
| Sl No. | Package Number | Package Description | Name of the Contractor | Ordered Quantity | Supplied upto 02.07.2016 | Erected as on 02.07.2016 | Site Acceptance Test (SAT) as on 02.07.2016 | Charged as on 02.07.2016 |
| 1. | Package-III(A) | Line Reclosers (LRC) | M/s P&C Co. | 500 | Completed | Completed | 495 | 104 |
|  |  | Load Break Switches (LBS) |  | 450 | Completed | Completed | 447 | 138 |
| 2. | Package-III(B) | Line Reclosers (LRC) | M/s Entec | 295 | Completed | Completed | 287 | 108 |
|  |  | Load Break Switches (LBS) |  | 295 | Completed | Completed | 291 | 94 |
| Sl No. | Package Number | Package Description | Name of the Contractor | Ordered Quantity | Supplied as on 02.07.2016 | Erected as as on 02.07.2016 | Commissioned as on 02.07.2016 |
| 3. | Package-IV(A) | New Ring Main Units(3 WAY) | M/s Schneider Electricals | 345 | Completed | Completed | Completed |
| 4. | Package-IV(B) | New Ring Main Units(5 WAY) | M/s CGL | 250 | Completed | Completed | Completed |
| 5. | Package-IV(C) | New Ring Main Units(5 WAY) | M/s Siemens | 195 | Completed | Completed | Completed |
| 6. | Package-V(A) | Replacement of existing RMU with DAS compatible RMU | M/s Eshwari Electricals | 200 | Completed | Completed | Completed |
| 7. | Package-V(B) | Replacement of existing RMU with DAS compatible RMU | M/s Schnieder Electricals | 600 | Completed | 590 | 590 |
| 8. | ** Package-VI | Construction of Overhead Lines(Coyote) | M/s L&T Limited | 700 Kms | Completed | 698.6 Km | 698.6 Km |
|  |  | Construction of Overhead Lines(ABC) |  | 500 Kms | 255 Kms | 254.6 Kms | 249 Kms |
|  |  | DP |  | 270 | Completed | Completed | Completed |
|  |  | Spun Pole |  | 1125 | Completed | Completed | Completed |
| 9. | Package-VII | Construction of Underground Cables | M/s L&T Limited | 230.5 Kms | Completed | 228 Kms | 228 Kms |

** M/s L&T Limited has supplied only 255Kms out of 500Kms AB Cable.