DAS weekly Progress achieved upto 28.09.2016

| Sl No. | Particular | Package Description | Status |
| --- | --- | --- | --- |
| 1 | Package-I | DAS System Design | DAS system design and customization is completed. DAS Factory Acceptance Test (FAT) completed. Communication system FAT completed. Configuration and Development System setup in BICC-1, HSR Layout, DAS & SG BESCOM office for training of BESCOM personnel. Substation model building of GIS data is completed. M/s Runtime Error Solutions Pvt Ltd., is awarded with work of Integration of DAS OMS with PGRS application. |
| 2 |  | Control Centers | Control Centre-1: All civil engineering works have been completed, except the following works which are in progress; Fire dampers Gas suppression system to server room, CH room and VPS enclosure. Control Centre-2: Building construction work is in progress. |
| 3 |  | Frequency Allocation | UHF: DL (Decision to grant license) for UHF frequency is issued by WPC (Wireless Planning & Coordination wing). WPC has issued Import License to import MARS Equipment of Communication system. Microwave: WPC has issued DL (Decision to grant license) for microwave frequency vide letter dated 28.07.2014. |
| 4 |  | Communication Towers | Tower Construction Status: 9 communication towers construction completed out of 11 towers. Radio modem and Antenna installation is in progress. Point to point testing of field equipments from C&DS(Configuration and Development System) server in control center has commenced |
| Sl No. | Package | Package Description | Name of the Contractor | Ordered Quantity | Allotted RMUs | RTUs Installed as on 28.09.2016 | RTUs Field Performance Test(FPT) as on 28.09.2016 |
| 1. | Package-II(A) | Remote Terminal Units for Existing and New Ring Main Units | M/s ABB | 700 | 695 | 687 | 660 |
| 2. | Package-II(B) |  | M/s CGL | 495 | 495 | 484 | 476 |
| 3. | Package-II(C) |  | M/s Efacec | 395 | 395 | 395 | 338 |
| Sl No. | Package Number | Package Description | Name of the Contractor | Ordered Quantity | Supplied upto 28.09.2016 | Erected as on 28.09.2016 | Site Acceptance Test (SAT) as on 28.09.2016 | Charged as on 28.09.2016 |
| 1. | Package-III(A) | Line Reclosers (LRC) | M/s P&C Co. | 500 | Completed | Completed | 495 | 131 |
|  |  | Load Break Switches (LBS) |  | 450 | Completed | Completed | 447 | 173 |
| 2. | Package-III(B) | Line Reclosers (LRC) | M/s Entec | 295 | Completed | Completed | 290 | 174 |
|  |  | Load Break Switches (LBS) |  | 295 | Completed | Completed | 290 | 182 |
| Sl No. | Package Number | Package Description | Name of the Contractor | Ordered Quantity | Supplied as on 28.09.2016 | Erected as as on 28.09.2016 | Commissioned as on 28.09.2016 |
| 3. | Package-IV(A) | New Ring Main Units(3 WAY) | M/s Schneider Electricals | 345 | Completed | Completed | Completed |
| 4. | Package-IV(B) | New Ring Main Units(5 WAY) | M/s CGL | 250 | Completed | Completed | Completed |
| 5. | Package-IV(C) | New Ring Main Units(5 WAY) | M/s Siemens | 195 | Completed | Completed | Completed |
| 6. | Package-V(A) | Replacement of existing RMU with DAS compatible RMU | M/s Eshwari Electricals | 200 | Completed | Completed | Completed |
| 7. | Package-V(B) | Replacement of existing RMU with DAS compatible RMU | M/s Schnieder Electricals | 600 | Completed | 593 | 593 |
| 8. | ** Package -VI | Construction of Overhead Lines(Coyote) | M/s L&T Limited | 700 Kms | Completed | 698.6 Km | 698.6 Km |
|  |  | Construction of Overhead Lines(ABC) |  | 500 Kms | 255 Kms | 254.6 Kms | 249 Kms |
|  |  | DP |  | 270 | Completed | Completed | Completed |
|  |  | Spun Pole |  | 1125 | Completed | Completed | Completed |
| 9. | Package-VII | Construction of Underground Cables | M/s L&T Limited | 230.5 Kms | Completed | 228 Kms | 228 Kms |

** M/s L&T Limited has supplied only 255Kms out of 500Kms AB Cable.