## english
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Progress of energisation of Drinking Water Supply for the month of April-2020
ABSTRACT
| Sl No | Zone/Circle | Division | No. of Applications pending as at the end of previous month | No. of Applications registered April-2020 | Total Applications | No. of Applications lapsed April-2020 | No. of Applications serviced April-2020 | No. of Applications pending as at the end April-2020 | Applications pending with Local Bodies |  |  | Applications pending with BESCOM end |  |  |  |  | Total applications serviced during 20-21
PÀæ. .¸ÀA | [9 empty] | Works completed from BESCOM end, but sevice not avalied | Formalilities not observed | Total applications pending from local bodies | Work Order issued | Work Under progress | Work to be taken up | Work order to be issued | Total applications pending from BESCOM end
|  |  |  | 1 | 2 | 3=1+2 | 4 | 5 | 6=3-(4+5) | 7 | 8 | 9=7+8 | 10 | 11 | 12 | 13 | 14=10+11+12+13 | 15
| 1 | South | Jayanagar | 11 | 0 | 11 | 0 | 0 | 11 | 11 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0
| 2 |  | Koramangala | 8 | 0 | 8 | 0 | 0 | 8 | 7 | 1 | 8 | 0 | 0 | 0 | 0 | 0 | 0
3 | 3 |  | HSR | 8 | 0 | 8 | 0 | 7 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7
4 | Total |  |  | 27 | 0 | 27 | 0 | 7 | 20 | 19 | 1 | 20 | 0 | 0 | 0 | 0 | 0 | 7
8 | 4 | West | Rajajinagar | 28 | 0 | 28 | 0 | 0 | 28 | 28 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0
9 | 5 |  | Kengeri | 28 | 0 | 28 | 0 | 0 | 28 | 0 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0
10 | 6 |  | RR Nagar | 21 | 2 | 23 | 9 | 0 | 14 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0
11 | Total |  |  | 77 | 2 | 79 | 9 | 0 | 70 | 42 | 28 | 70 | 0 | 0 | 0 | 0 | 0 | 0
| BMASZ |  |  | 104 | 2 | 106 | 9 | 7 | 90 | 61 | 29 | 90 | 0 | 0 | 0 | 0 | 0 | 7
1 | 1 | North | Malleswaram | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 2 |  | Hebbal | 12 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
| 3 |  | Peenya | 5 | 0 | 5 | 0 | 0 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0
| 4 |  | Jalahalli | 10 | 1 | 11 | 0 | 3 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 3
| Total |  |  | 27 | 1 | 28 | 0 | 15 | 13 | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 15
5 | 8 | East | Indiranagar | 8 | 0 | 8 | 5 | 2 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2
| 9 |  | Whitefield | 9 | 0 | 9 | 0 | 0 | 9 | 7 | 2 | 9 | 0 | 0 | 0 | 0 | 0 | 0
| 10 |  | Shivajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 11 |  | Vidhanasuoudha | 6 | 0 | 6 | 0 | 1 | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1
7 | Total |  |  | 23 | 0 | 23 | 5 | 3 | 15 | 13 | 2 | 15 | 0 | 0 | 0 | 0 | 0 | 3
| BMANZ |  |  | 50 | 1 | 51 | 5 | 18 | 28 | 13 | 15 | 28 | 0 | 0 | 0 | 0 | 0 | 18
| BMASZ & BMANZ |  |  | 154 | 3 | 157 | 14 | 25 | 118 | 74 | 44 | 118 | 0 | 0 | 0 | 0 | 0 | 25
13 | 15 | BRC | Nelamangala | 6 | 4 | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 2 | 8 | 0 | 10 | 0
14 | 16 |  | Hosakote | 19 | 0 | 19 | 0 | 2 | 17 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 17 | 2
|  | Total |  | 25 | 4 | 29 | 0 | 2 | 27 | 0 | 0 | 0 | 0 | 19 | 8 | 0 | 27 | 2
15 | 17 | Ramanagara | Ramanagara | 14 | 14 | 28 | 0 | 6 | 22 | 0 | 5 | 5 | 0 | 17 | 0 | 0 | 17 | 6
| 18 |  | Magadi | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0
| 19 |  | Kanakapura | 31 | 1 | 32 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 32 | 0
| 20 |  | Chandapura | 37 | 4 | 41 | 0 | 0 | 41 | 0 | 29 | 29 | 0 | 12 | 0 | 0 | 12 | 0
| Total |  |  | 83 | 19 | 102 | 0 | 6 | 96 | 0 | 34 | 34 | 0 | 62 | 0 | 0 | 62 | 6
16 | 21 | Kolar | Kolar | 1 | 5 | 6 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
17 | 22 |  | KGF | 13 | 42 | 55 | 0 | 12 | 43 | 0 | 0 | 0 | 0 | 27 | 0 | 16 | 43 | 12
18 | 23 |  | Chikkaballapur | 5 | 5 | 10 | 0 | 8 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 8
19 | 24 |  | Chintamani | 3 | 6 | 9 | 0 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 7
| Total |  |  | 22 | 58 | 80 | 1 | 32 | 47 | 0 | 0 | 0 | 0 | 29 | 0 | 18 | 47 | 32
| BRAZ |  |  | 130 | 81 | 211 | 1 | 40 | 170 | 0 | 34 | 34 | 0 | 110 | 8 | 18 | 136 | 40
20 | 25 | Davangere | Davangere | 34 | 3 | 37 | 0 | 5 | 32 | 0 | 2 | 2 | 0 | 3 | 17 | 10 | 30 | 5
21 | 26 |  | Harihara | 10 | 0 | 10 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 5
22 | 27 |  | Chitradurga | 18 | 1 | 19 | 0 | 3 | 16 | 0 | 0 | 0 | 0 | 7 | 6 | 3 | 16 | 3
23 | 28 |  | Hiriyuru | 10 | 5 | 15 | 0 | 3 | 12 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 12 | 3
| Total |  |  | 72 | 9 | 81 | 0 | 16 | 65 | 0 | 2 | 2 | 0 | 16 | 34 | 13 | 63 | 16
24 | 29 | Tumkur | Tumkur | 7 | 0 | 7 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 4
| 30 |  | Kunigal | 10 | 0 | 10 | 0 | 1 | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9 | 1
25 | 31 |  | Tipur | 6 | 18 | 24 | 1 | 1 | 22 | 0 | 0 | 0 | 0 | 16 | 3 | 3 | 22 | 1
26 | 32 |  | Madhugiri | 4 | 17 | 21 | 0 | 3 | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 18 | 3
| Total |  |  | 27 | 35 | 62 | 1 | 9 | 52 | 0 | 0 | 0 | 0 | 46 | 3 | 3 | 52 | 9
| CTAZ |  |  | 99 | 44 | 143 | 1 | 25 | 117 | 0 | 2 | 2 | 0 | 62 | 37 | 16 | 115 | 25
| BESCOM |  |  | 383 | 128 | 511 | 16 | 90 | 405 | 74 | 80 | 154 | 0 | 172 | 45 | 34 | 251 | 90