## english
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Progress of energisation of Drinking Water Supply for the month of May-2020
ABSTRACT
| Sl No | Zone/Circle | Division | No. of Applications pending as at the end of previous month | No. of Applications registered during the Present month | Total Applications | No. of Applications during the Present month | No. of Applications serviced during the Present month | No. of Applications pending during the Present month | Applications pending with Local Bodies |  |  | Applications pending with BESCOM end |  |  |  |  | Total applications serviced during 20-21
PÀæ. .¸ÀA | [9 empty] | Works completed from BESCOM end, but sevice not avalied | Formalilities not observed | Total applications pending from local bodies | Work Order issued | Work Under progress | Work to be taken up | Work order to be issued | Total applications pending from BESCOM end
|  |  |  | 1 | 2 | 3=1+2 | 4 | 5 | 6=3-(4+5) | 7 | 8 | 9=7+8 | 10 | 11 | 12 | 13 | 14=10+11+12+13 | 15
| 1 | South | Jayanagar | 11 | 0 | 11 | 0 | 0 | 11 | 11 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0
| 2 |  | Koramangala | 8 | 0 | 8 | 0 | 2 | 6 | 5 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 2
3 | 3 |  | HSR | 1 | 7 | 8 | 0 | 7 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14
4 | Total |  |  | 20 | 7 | 27 | 0 | 9 | 18 | 17 | 1 | 18 | 0 | 0 | 0 | 0 | 0 | 16
8 | 4 | West | Rajajinagar | 28 | 7 | 35 | 0 | 30 | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 30
9 | 5 |  | Kengeri | 28 | 5 | 33 | 0 | 17 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 17
10 | 6 |  | RR Nagar | 14 | 0 | 14 | 0 | 5 | 9 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 5
11 | Total |  |  | 70 | 12 | 82 | 0 | 52 | 30 | 14 | 16 | 30 | 0 | 0 | 0 | 0 | 0 | 52
| BMASZ |  |  | 90 | 19 | 109 | 0 | 61 | 48 | 31 | 17 | 48 | 0 | 0 | 0 | 0 | 0 | 68
1 | 1 | North | Malleswaram | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 2 |  | Hebbal | 0 | 10 | 10 | 0 | 6 | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 18
| 3 |  | Peenya | 5 | 14 | 19 | 0 | 5 | 14 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 5
| 4 |  | Jalahalli | 8 | 1 | 9 | 0 | 2 | 7 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 5
| Total |  |  | 13 | 25 | 38 | 0 | 13 | 25 | 0 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 28
5 | 8 | East | Indiranagar | 1 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
| 9 |  | Whitefield | 9 | 1 | 10 | 0 | 2 | 8 | 5 | 3 | 8 | 0 | 0 | 0 | 0 | 0 | 2
| 10 |  | Shivajinagar | 0 | 15 | 15 | 0 | 6 | 9 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 6
6 | 11 |  | Vidhanasuoudha | 5 | 0 | 5 | 0 | 0 | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1
7 | Total |  |  | 15 | 17 | 32 | 0 | 10 | 22 | 10 | 12 | 22 | 0 | 0 | 0 | 0 | 0 | 13
| BMANZ |  |  | 28 | 42 | 70 | 0 | 23 | 47 | 10 | 37 | 47 | 0 | 0 | 0 | 0 | 0 | 41
| BMASZ & BMANZ |  |  | 118 | 61 | 179 | 0 | 84 | 95 | 41 | 54 | 95 | 0 | 0 | 0 | 0 | 0 | 109
13 | 15 | BRC | Nelamangala | 10 | 1 | 11 | 0 | 6 | 5 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 5 | 6
14 | 16 |  | Hosakote | 17 | 0 | 17 | 0 | 2 | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 15 | 4
|  | Total |  | 27 | 1 | 28 | 0 | 8 | 20 | 0 | 0 | 0 | 0 | 16 | 4 | 0 | 20 | 10
15 | 17 | Ramanagara | Ramanagara | 22 | 8 | 30 | 0 | 16 | 14 | 0 | 5 | 5 | 0 | 9 | 0 | 0 | 9 | 22
| 18 |  | Magadi | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 19 |  | Kanakapura | 32 | 7 | 39 | 0 | 20 | 19 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 19 | 20
| 20 |  | Chandapura | 41 | 1 | 42 | 23 | 6 | 13 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 13 | 6
| Total |  |  | 96 | 16 | 112 | 23 | 43 | 46 | 0 | 5 | 5 | 0 | 41 | 0 | 0 | 41 | 49
16 | 21 | Kolar | Kolar | 0 | 15 | 15 | 0 | 12 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 17
17 | 22 |  | KGF | 43 | 65 | 108 | 20 | 31 | 57 | 0 | 0 | 0 | 16 | 41 | 0 | 0 | 57 | 43
18 | 23 |  | Chikkaballapur | 2 | 6 | 8 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 12
19 | 24 |  | Chintamani | 2 | 4 | 6 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 12
| Total |  |  | 47 | 90 | 137 | 20 | 52 | 65 | 0 | 0 | 0 | 16 | 49 | 0 | 0 | 65 | 84
| BRAZ |  |  | 170 | 107 | 277 | 43 | 103 | 131 | 0 | 5 | 5 | 16 | 106 | 4 | 0 | 126 | 143
20 | 25 | Davangere | Davangere | 32 | 24 | 56 | 0 | 46 | 10 | 0 | 2 | 2 | 0 | 6 | 0 | 2 | 8 | 51
21 | 26 |  | Harihara | 5 | 4 | 9 | 0 | 3 | 6 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 6 | 8
22 | 27 |  | Chitradurga | 16 | 8 | 24 | 0 | 8 | 16 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 16 | 11
23 | 28 |  | Hiriyuru | 12 | 7 | 19 | 0 | 14 | 5 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 5 | 17
| Total |  |  | 65 | 43 | 108 | 0 | 71 | 37 | 0 | 2 | 2 | 0 | 19 | 6 | 10 | 35 | 87
24 | 29 | Tumkur | Tumkur | 3 | 3 | 6 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 9
| 30 |  | Kunigal | 9 | 0 | 9 | 0 | 7 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 8
25 | 31 |  | Tipur | 22 | 8 | 30 | 0 | 18 | 12 | 0 | 0 | 0 | 0 | 8 | 1 | 3 | 12 | 19
26 | 32 |  | Madhugiri | 18 | 9 | 27 | 0 | 17 | 10 | 0 | 0 | 0 | 0 | 7 | 1 | 2 | 10 | 20
| Total |  |  | 52 | 20 | 72 | 0 | 47 | 25 | 0 | 0 | 0 | 0 | 18 | 2 | 5 | 25 | 56
| CTAZ |  |  | 117 | 63 | 180 | 0 | 118 | 62 | 0 | 2 | 2 | 0 | 37 | 8 | 15 | 60 | 143
| BESCOM |  |  | 405 | 231 | 636 | 43 | 305 | 288 | 41 | 61 | 102 | 16 | 143 | 12 | 15 | 186 | 395