## Website Dec-20
Bangalore Electricity Supply Company Limited
Progress & pending Application details of Gangakalyana upto Dec-20
All Corporations | [12 empty] | Annexure-1
Sl No | Circle | Division | Opening balance of applications as on 1-4-2020 | Total applications received during the year 2020-21 (up to Dec-20) | Total applications lapsed during the year 2020-21 (up to Dec-20) | Total applications added during the year 2020-21 (up to Dec-20) | Total Valid Applications | Total borewells energised during the year 2020-21 (up to Dec-20) | Applications pending as at the end of the year 2020-21 (up to Dec-20) | Work Completed Service Not availed | Formalities Not observed | Applications pending at Corporation End | Work Under Progress | Work to be taken Up | Work order to be issued | Estimate to be prepared | Applications pending at BESCOM End
|  |  | 1 | 2 | 3 | 4=2-3 | 5=1+4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | North | Malleshwaram | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | Hebbala | 25 | 3 | 2 | 1 | 26 | 23 | 3 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 3
3 |  | Peenya | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | Jalahalli | 18 | 12 | 0 | 12 | 30 | 16 | 14 | 0 | 1 | 1 | 7 | 0 | 0 | 6 | 13
| Total |  | 43 | 15 | 2 | 13 | 56 | 39 | 17 | 0 | 1 | 1 | 9 | 1 | 0 | 6 | 16
5 | East | Indiranagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Shivajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | Vidhanasoudha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Whitefield | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BMANZ |  |  | 43 | 15 | 2 | 13 | 56 | 39 | 17 | 0 | 1 | 1 | 9 | 1 | 0 | 6 | 16
9 | South | Jaynagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Kormangala | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  | H S R | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | West | Rajajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
13 |  | Rajarajeshwari nagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | Kengeri | 13 | 0 | 0 | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 13 | 0 | 0 | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BMASZ |  | 13 | 0 | 0 | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Blore Rural | Nelmangala | 15 | 88 | 0 | 88 | 103 | 83 | 20 | 0 | 1 | 1 | 17 | 2 | 0 | 0 | 19
16 |  | Yelhanka | 11 | 46 | 0 | 46 | 57 | 25 | 32 | 0 | 5 | 5 | 27 | 0 | 0 | 0 | 27
| Total |  | 26 | 134 | 0 | 134 | 160 | 108 | 52 | 0 | 6 | 6 | 44 | 2 | 0 | 0 | 46
17 | Ramnagara | Ramnagara | 0 | 40 | 0 | 40 | 40 | 17 | 23 | 0 | 20 | 20 | 3 | 0 | 0 | 0 | 3
18 |  | Magadi | 5 | 12 | 0 | 12 | 17 | 14 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3
19 |  | Chandapura | 16 | 29 | 3 | 26 | 42 | 31 | 11 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 11
20 |  | Kanakpura | 0 | 35 | 0 | 35 | 35 | 33 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
| Total |  | 21 | 116 | 3 | 113 | 134 | 95 | 39 | 0 | 20 | 20 | 19 | 0 | 0 | 0 | 19
21 | Kolar | Kolar | 17 | 39 | 0 | 39 | 56 | 37 | 19 | 0 | 0 | 0 | 0 | 1 | 18 | 0 | 19
22 |  | K G F | 23 | 174 | 0 | 174 | 197 | 163 | 34 | 0 | 1 | 1 | 17 | 0 | 16 | 0 | 33
23 |  | C B Pura | 2 | 13 | 0 | 13 | 15 | 14 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
24 |  | Chintamani | 2 | 50 | 0 | 50 | 52 | 18 | 34 | 0 | 0 | 0 | 1 | 0 | 33 | 0 | 34
| Total |  | 44 | 276 | 0 | 276 | 320 | 232 | 88 | 0 | 1 | 1 | 19 | 1 | 67 | 0 | 87
25 | Davangere | Davangere | 49 | 324 | 4 | 320 | 369 | 279 | 90 | 0 | 0 | 0 | 4 | 72 | 0 | 15 | 91
26 |  | Harihara | 9 | 140 | 2 | 138 | 147 | 87 | 60 | 0 | 0 | 0 | 16 | 43 | 0 | 0 | 59
27 |  | Chitradurga | 794 | 347 | 19 | 328 | 1122 | 871 | 251 | 0 | 2 | 2 | 55 | 76 | 0 | 118 | 249
28 |  | Hiriyur | 75 | 309 | 0 | 309 | 384 | 295 | 89 | 0 | 0 | 0 | 20 | 68 | 0 | 1 | 89
| Total |  | 927 | 1120 | 25 | 1095 | 2022 | 1532 | 490 | 0 | 2 | 2 | 95 | 259 | 0 | 134 | 488
29 | Tumkur | Tumkur | 13 | 79 | 3 | 76 | 89 | 73 | 16 | 0 | 1 | 1 | 15 | 0 | 0 | 0 | 15
30 |  | Kunigal | 12 | 13 | 0 | 13 | 25 | 24 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
31 |  | Tiptur | 21 | 96 | 2 | 94 | 115 | 86 | 29 | 0 | 8 | 8 | 8 | 0 | 0 | 13 | 21
32 |  | Madhugiri | 9 | 220 | 0 | 220 | 229 | 209 | 20 | 0 | 0 | 0 | 15 | 5 | 0 | 0 | 20
| Total |  | 55 | 408 | 5 | 403 | 458 | 392 | 66 | 0 | 9 | 9 | 39 | 5 | 0 | 13 | 57
| BESCOM Total |  | 1129 | 2069 | 35 | 2034 | 3163 | 2411 | 752 | 0 | 39 | 39 | 225 | 268 | 67 | 153 | 713
|  | Assistant General Manager(Op-3) | [5 empty] | 11: Deputy General Manager(Op-1)
|  | BESCOM | [5 empty] | 11: BESCOM
Chief General Manager(Op)
BESCOM