## Abstract_Comm_Indi (cumulative) (hidden)
Bangalore Electricity Supply Company Limited
Progress & pending Application details of Gangakalyana upto Feb-24
All Corporations | [12 empty] | Annexure-1
Sl No | Circle | Division | Opening balance of applications as on 1-4-2023 | Total applications received during the year 2023-24 (up to Feb-24) | Total applications lapsed during the year 2023-24 (up to Feb-24) | Total applications added during the year 2023-24 (up to Feb-24) | Total Valid Applications | Total borewells energised during the year 2023-24 (up to Feb-24) | Applications pending as at the end of the year 2023-24 (up to Feb-24) | Work Completed Service Not availed | Formalities Not observed | Applications pending at Corporation End | Work Under Progress | Work to be taken Up | Work order to be issued | Estimate to be prepared | Applications pending at BESCOM End
|  |  | 1 | 2 | 3 | 4=2-3 | 5=1+4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | North | Malleshwaram | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | Hebbala | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 |  | Peenya | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | Jalahalli | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | East | Indiranagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Shivajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | Vidhanasoudha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Whitefield | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BMANZ |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | South | Jaynagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Kormangala | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  | H S R | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | West | Rajajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
13 |  | Rajarajeshwari nagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | Kengeri | 0 | 5 | 0 | 5 | 5 | 2 | 3 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 2 | 0
| Total |  | 0 | 5 | 0 | 5 | 5 | 2 | 3 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 2 | 0
| BMASZ |  | 0 | 5 | 0 | 5 | 5 | 2 | 3 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 2 | 0
15 | Blore Rural | Nelmangala | 6 | 72 | 0 | 72 | 78 | 26 | 52 | 0 | 32 | 32 | 14 | 6 | 0 | 0 | 20 | 0
16 |  | Yelhanka | 0 | 61 | 2 | 59 | 59 | 22 | 37 | 0 | 0 | 0 | 26 | 0 | 0 | 11 | 37 | 0
| Total |  | 6 | 133 | 2 | 131 | 137 | 48 | 89 | 0 | 32 | 32 | 40 | 6 | 0 | 11 | 57 | 0
17 | Ramnagara | Ramnagara | 0 | 9 | 1 | 8 | 8 | 3 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0
18 |  | Magadi | 0 | 24 | 0 | 24 | 24 | 14 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 10 | 0
19 |  | Chandapura | 1 | 23 | 0 | 23 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 |  | Kanakpura | 0 | 22 | 3 | 19 | 19 | 7 | 12 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12 | 0 | 28
| Total |  | 1 | 78 | 4 | 74 | 75 | 48 | 27 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 27 | 0
21 | Kolar | Kolar | 0 | 47 | 0 | 47 | 47 | 35 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 10 | 0
22 |  | K G F | 7 | 118 | 4 | 114 | 121 | 84 | 39 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 39 | 0
23 |  | C B Pura | 6 | 175 | 1 | 174 | 180 | 147 | 33 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 33 | 0
24 |  | Chintamani | 1 | 30 | 0 | 30 | 31 | 28 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0
| Total |  | 14 | 370 | 5 | 365 | 379 | 294 | 85 | 0 | 0 | 0 | 85 | 0 | 0 | 0 | 85 | 0
25 | Davangere | Davangere | 2 | 184 | 3 | 181 | 183 | 119 | 64 | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 64 | 0
26 |  | Harihara | 9 | 133 | 5 | 128 | 137 | 115 | 22 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 22 | 0
27 |  | Chitradurga | 10 | 374 | 0 | 374 | 384 | 345 | 39 | 0 | 0 | 0 | 21 | 18 | 0 | 0 | 39 | 0
28 |  | Hiriyur | 30 | 122 | 0 | 122 | 152 | 117 | 35 | 0 | 0 | 0 | 11 | 24 | 0 | 0 | 35 | 0
| Total |  | 51 | 813 | 8 | 805 | 856 | 696 | 160 | 0 | 0 | 0 | 118 | 42 | 0 | 0 | 160 | 0
29 | Tumkur | Tumkur | 0 | 183 | 1 | 182 | 182 | 132 | 50 | 0 | 23 | 23 | 5 | 19 | 0 | 3 | 27 | 0
30 |  | Kunigal | 0 | 26 | 0 | 26 | 26 | 17 | 9 | 0 | 2 | 2 | 5 | 2 | 0 | 0 | 7 | 0
31 |  | Tiptur | 1 | 130 | 0 | 130 | 131 | 57 | 74 | 0 | 23 | 23 | 41 | 0 | 0 | 10 | 51 | 0
32 |  | Madhugiri | 1 | 108 | 0 | 108 | 109 | 59 | 50 | 0 | 3 | 3 | 45 | 0 | 0 | 2 | 47 | 0
| Total |  | 2 | 447 | 1 | 446 | 448 | 265 | 183 | 0 | 51 | 51 | 96 | 21 | 0 | 15 | 132 | 0
| BESCOM Total |  | 74 | 1846 | 20 | 1826 | 1900 | 1353 | 547 | 0 | 84 | 84 | 368 | 69 | 0 | 26 | 463 | 0
[5 empty] | 1826 |  | 172.7273
|  | Assistant General Manager-3 | [5 empty] | 6: 73; 11: Deputy General Manager(Ele)
|  | Operation-1, BESCOM | [5 empty] | 8: 179; 11: Operation-1, BESCOM
Chief General Manager(Ele)
Operation, BESCOM
1900
[5 empty] | 547 | 78 | 39 | bar: 10
[6 empty] | 502 |  | 7: 59.3653
1434

## Website kannada
¨ÉAUÀ¼ÀÆgÀÄ «zÀÄåvï ¸ÀgÀ§gÁdÄ PÀA¥À¤ ¤AiÀÄ«ÄvÀ
2023-24 £ÉÃ ¸Á°£À ¥sÉ§æªÀj-24 gÀ CAvÀåPÉÌ UÀAUÁPÀ¯Áåt AiÉÆÃd£ÀAiÀÄr «zÀÄåvï ¸ÀA¥ÀPÀð PÀ°à¹zÀ ºÁUÀÆ ¨ÁQ EgÀÄªÀ CfðUÀ¼À «ªÀgÀUÀ¼ÀÄ
J¯Áè C©üªÀÈ¢Þ ¤UÀªÀÄUÀ¼ÀÄ ¸ÉÃj
PÀæªÀÄ ¸ÀASÉå | ªÀÈvÀÛ | «¨sÁUÀ | 31.03.2023 gÀ CAvÀåPÉÌ ¨ÁQ EgÀÄªÀ CfðUÀ¼À ¸ÀASÉå | 2023-24 £ÉÃ ¸Á°£À (¥sÉ§æªÀj-24gÀ CAvÀåPÉÌ) £ÉÆÃAzÀtÂUÉÆAqÀ CfðUÀ¼À ¸ÀASÉå | 2023-24 £ÉÃ ¸Á°£À (¥sÉ§æªÀj-24 gÀ CAvÀåPÉÌ) gÀzÁÝzÀ CfðUÀ¼À ¸ÀASÉå | 2023-24 £ÉÃ ¸Á°£À (¥sÉ§æªÀj-24gÀ CAvÀåPÉÌ) £ÉÆÃAzÀtÂUÉÆAqÀ MlÄÖ CfðUÀ¼À ¸ÀASÉå | MlÄÖ CfðUÀ¼À ¸ÀASÉå | 2023-24 £ÉÃ ¸Á°£À (¥sÉ§æªÀj-24 gÀ CAvÀåPÉÌ) «zÀÄåvï ¸ÀA¥ÀPÀð ¥ÀqÉzÀ MlÄÖ CfðUÀ¼À ¸ÀASÉå | 2023-24 £ÉÃ ¸Á°£À (¥sÉ§æªÀj-24 gÀ CAvÀåPÉÌ) ¨ÁQ EgÀÄªÀ MlÄÖ CfðUÀ¼À ¸ÀASÉå | ¨É«PÀA ªÀw¬ÄAzÀ PÉ®¸À ªÀÄÄV¢zÀÄÝ DzÀgÉ C©üªÀÈ¢Þ ¤UÀªÀÄzÀªÀgÀÄ «zÀÄåvï ¸ÀA¥ÀPÀð vÉUÉzÀÄPÉÆ¼Àî¢gÀÄªÀ CfðUÀ¼À ¸ÀASÉå | C©üªÀÈ¢Þ ¤UÀªÀÄzÀªÀgÀÄ ¨É«PÀA£À ¤AiÀÄªÀÄUÀ¼À£ÀÄß ¥Á°¸À¢gÀÄªÀ CfðUÀ¼À ¸ÀASÉå | wAUÀ¼À CAvÀåPÉÌ C©üªÀÈ¢Þ ¤UÀªÀÄzÀªÀgÀªÀw¬ÄAzÀ ¨ÁQ EgÀÄªÀ MlÄÖ CfðUÀ¼À ¸ÀASÉå | PÁAiÀÄð ¥ÀæUÀwAiÀÄ°ègÀÄªÀ CfðUÀ¼À ¸ÀASÉå | PÁAiÀÄð PÉÊUÉwÛ PÉÆ¼Àî¨ÉÃPÁVgÀÄªÀ CfðUÀ¼À ¸ÀASÉå | PÁAiÀiÁðzÉÃ±À ¤ÃqÀ ¨ÉÃPÁVgÀÄªÀ CfðUÀ¼À ¸ÀASÉå | CAzÁdÄ ¥ÀnÖ vÀ0iÀiÁj ºÀAvÀzÀ°ègÀÄªÀ ¸ÀASÉå | wAUÀ¼À CAvÀåPÉÌ ¨É«PÀA ªÀw¬ÄAzÀ ¨ÁQ EgÀÄªÀ MlÄÖ CfðUÀ¼À ¸ÀASÉå
|  |  | 1 | 2 | 3 | 4=2-3 | 5=1+4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | GvÀÛgÀ | ªÀÄ¯ÉèÃ±ÀégÀA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | ºÉ¨Áâ¼À | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 |  | ¦Ãtå | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | eÁ®ºÀ°î | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MlÄÖ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ¥ÀÆªÀð | EA¢gÁ£ÀUÀgÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | ²ªÁf£ÀUÀgÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | «zsÁ£À¸ËzsÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | ªÉÊmï¦üÃ¯ïØ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MlÄÖ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ¨ÉAUÀ¼ÀÆgÀÄ ªÀÄºÁ£ÀUÀgÀ GvÀÛgÀ PÉëÃvÀæ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | zÀQët | dAiÀÄ£ÀUÀgÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | PÉÆÃgÀªÀÄAUÀ® | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  | ºÉZï.J¸ï.Dgï | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MlÄÖ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | ¥À²ÑªÀÄ | gÁeÁf£ÀUÀgÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  | gÁdgÁeÉÃ±Àéj £ÀUÀgÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | PÉAUÉÃj | 0 | 5 | 0 | 5 | 5 | 2 | 3 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 2
| MlÄÖ |  | 0 | 5 | 0 | 5 | 5 | 2 | 3 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 2
| ¨ÉAUÀ¼ÀÆgÀÄ ªÀÄºÁ£ÀUÀgÀ zÀQët PÉëÃvÀæ |  | 0 | 5 | 0 | 5 | 5 | 2 | 3 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 2
15 | ¨ÉAUÀ¼ÀÆgÀÄ UÁæ«ÄÃt | £É®ªÀÄAUÀ® | 6 | 72 | 0 | 72 | 78 | 26 | 52 | 0 | 32 | 32 | 14 | 6 | 0 | 0 | 20
16 |  | AiÀÄ®ºÀAPÀ | 0 | 61 | 2 | 59 | 59 | 22 | 37 | 0 | 0 | 0 | 26 | 0 | 0 | 11 | 37
| MlÄÖ |  | 6 | 133 | 2 | 131 | 137 | 48 | 89 | 0 | 32 | 32 | 40 | 6 | 0 | 11 | 57
17 | gÁªÀÄ£ÀUÀgÀ | gÁªÀÄ£ÀUÀgÀ | 0 | 9 | 1 | 8 | 8 | 3 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5
18 |  | ªÀiÁUÀr | 0 | 24 | 0 | 24 | 24 | 14 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 10
19 |  | ZÀAzÁ¥ÀÄgÀ | 1 | 23 | 0 | 23 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 |  | PÀ£ÀPÀ¥ÀÄgÀ | 0 | 22 | 3 | 19 | 19 | 7 | 12 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12
| MlÄÖ |  | 1 | 78 | 4 | 74 | 75 | 48 | 27 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 27
21 | PÉÆÃ¯ÁgÀ | PÀÉÆÃ¯ÁgÀ | 0 | 47 | 0 | 47 | 47 | 35 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 10
22 |  | PÉ.f.J¥sï | 7 | 118 | 4 | 114 | 121 | 84 | 39 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 39
23 |  | aPÀÌ§¼Áî¥ÀÄgÀ | 6 | 175 | 1 | 174 | 180 | 147 | 33 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 33
24 |  | aAvÁªÀÄtÂ | 1 | 30 | 0 | 30 | 31 | 28 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3
| MlÄÖ |  | 14 | 370 | 5 | 365 | 379 | 294 | 85 | 0 | 0 | 0 | 85 | 0 | 0 | 0 | 85
25 | zÀÁªÀtUÉgÉ | zÀÁªÀtUÉgÉ | 2 | 184 | 3 | 181 | 183 | 119 | 64 | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 64
26 |  | ºÀjºÀgÀ | 9 | 133 | 5 | 128 | 137 | 115 | 22 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 22
27 |  | avÀæzÀÄUÀð | 10 | 374 | 0 | 374 | 384 | 345 | 39 | 0 | 0 | 0 | 21 | 18 | 0 | 0 | 39
28 |  | »jAiÀÄÆgÀÄ | 30 | 122 | 0 | 122 | 152 | 117 | 35 | 0 | 0 | 0 | 11 | 24 | 0 | 0 | 35
| MlÄÖ |  | 51 | 813 | 8 | 805 | 856 | 696 | 160 | 0 | 0 | 0 | 118 | 42 | 0 | 0 | 160
29 | vÀÄªÀÄPÀÆgÀÄ | vÀÄªÀÄPÀÆgÀÄ | 0 | 183 | 1 | 182 | 182 | 132 | 50 | 0 | 23 | 23 | 5 | 19 | 0 | 3 | 27
30 |  | PÀÄtÂUÀ¯ï | 0 | 26 | 0 | 26 | 26 | 17 | 9 | 0 | 2 | 2 | 5 | 2 | 0 | 0 | 7
31 |  | w¥ÀlÆgÀÄ | 1 | 130 | 0 | 130 | 131 | 57 | 74 | 0 | 23 | 23 | 41 | 0 | 0 | 10 | 51
32 |  | ªÀÄzsÀÄVj | 1 | 108 | 0 | 108 | 109 | 59 | 50 | 0 | 3 | 3 | 45 | 0 | 0 | 2 | 47
| MlÄÖ |  | 2 | 447 | 1 | 446 | 448 | 265 | 183 | 0 | 51 | 51 | 96 | 21 | 0 | 15 | 132
| ¨É«PÀA MlÄÖ |  | 74 | 1846 | 20 | 1826 | 1900 | 1353 | 547 | 0 | 84 | 84 | 368 | 69 | 0 | 26 | 463