## Website English
Bangalore Electricity Supply Company Limited
Progress & pending Application details of Gangakalyana upto Feb-21
All Corporations | [12 empty] | Annexure-1
Sl No | Circle | Division | Opening balance of applications as on 1-4-2020 | Total applications received during the year 2020-21 (up to Feb-21) | Total applications lapsed during the year 2020-21 (up to Feb-21) | Total applications added during the year 2020-21 (up to Feb-21) | Total Valid Applications | Total borewells energised during the year 2020-21 (up to Feb-21) | Applications pending as at the end of the year 2020-21 (up to Feb-21) | Work Completed Service Not availed | Formalities Not observed | Applications pending at Corporation End | Work Under Progress | Work to be taken Up | Work order to be issued | Estimate to be prepared | Applications pending at BESCOM End
|  |  | 1 | 2 | 3 | 4=2-3 | 5=1+4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | North | Malleshwaram | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | Hebbala | 25 | 3 | 2 | 1 | 26 | 24 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
3 |  | Peenya | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | Jalahalli | 18 | 13 | 1 | 12 | 30 | 20 | 10 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 5
| Total |  | 43 | 16 | 3 | 13 | 56 | 44 | 12 | 0 | 5 | 5 | 7 | 0 | 0 | 0 | 7
5 | East | Indiranagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Shivajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | Vidhanasoudha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Whitefield | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BMANZ |  |  | 43 | 16 | 3 | 13 | 56 | 44 | 12 | 0 | 5 | 5 | 7 | 0 | 0 | 0 | 7
9 | South | Jaynagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Kormangala | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  | H S R | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | West | Rajajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  | Rajarajeshwari nagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | Kengeri | 13 | 5 | 0 | 5 | 18 | 13 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0
| Total |  | 13 | 5 | 0 | 5 | 18 | 13 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0
| BMASZ |  | 13 | 5 | 0 | 5 | 18 | 13 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0
15 | Blore Rural | Nelmangala | 15 | 104 | 0 | 104 | 119 | 102 | 17 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 17
16 |  | Yelhanka | 11 | 78 | 0 | 78 | 89 | 61 | 28 | 0 | 4 | 4 | 23 | 1 | 0 | 0 | 24
| Total |  | 26 | 182 | 0 | 182 | 208 | 163 | 45 | 0 | 4 | 4 | 23 | 18 | 0 | 0 | 41
17 | Ramnagara | Ramnagara | 0 | 57 | 0 | 57 | 57 | 23 | 34 | 0 | 12 | 12 | 22 | 0 | 0 | 0 | 22
18 |  | Magadi | 5 | 24 | 0 | 24 | 29 | 16 | 13 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 13
19 |  | Chandapura | 16 | 35 | 3 | 32 | 48 | 40 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8
20 |  | Kanakpura | 0 | 52 | 0 | 52 | 52 | 35 | 17 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 17
| Total |  | 21 | 168 | 3 | 165 | 186 | 114 | 72 | 0 | 12 | 12 | 60 | 0 | 0 | 0 | 60
21 | Kolar | Kolar | 17 | 111 | 3 | 108 | 125 | 40 | 85 | 0 | 0 | 0 | 85 | 0 | 0 | 0 | 85
22 |  | K G F | 23 | 250 | 0 | 250 | 273 | 172 | 101 | 0 | 16 | 16 | 24 | 61 | 0 | 0 | 85
23 |  | C B Pura | 2 | 69 | 0 | 69 | 71 | 15 | 56 | 0 | 0 | 0 | 2 | 54 | 0 | 0 | 56
24 |  | Chintamani | 2 | 118 | 0 | 118 | 120 | 20 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 100
| Total |  | 44 | 548 | 3 | 545 | 589 | 247 | 342 | 0 | 16 | 16 | 111 | 215 | 0 | 0 | 326
25 | Davangere | Davangere | 49 | 404 | 4 | 400 | 449 | 351 | 98 | 0 | 4 | 4 | 5 | 89 | 0 | 0 | 94
26 |  | Harihara | 9 | 177 | 3 | 174 | 183 | 147 | 36 | 0 | 0 | 0 | 13 | 23 | 0 | 0 | 36
27 |  | Chitradurga | 794 | 460 | 24 | 436 | 1230 | 1039 | 191 | 0 | 6 | 6 | 72 | 45 | 0 | 68 | 185
28 |  | Hiriyur | 75 | 381 | 0 | 381 | 456 | 377 | 79 | 0 | 0 | 0 | 40 | 39 | 0 | 0 | 79
| Total |  | 927 | 1422 | 31 | 1391 | 2318 | 1914 | 404 | 0 | 10 | 10 | 130 | 196 | 0 | 68 | 394
29 | Tumkur | Tumkur | 13 | 104 | 3 | 101 | 114 | 102 | 12 | 0 | 0 | 0 | 7 | 5 | 0 | 0 | 12
30 |  | Kunigal | 12 | 25 | 0 | 25 | 37 | 27 | 10 | 0 | 0 | 0 | 3 | 5 | 0 | 2 | 10
31 |  | Tiptur | 21 | 102 | 2 | 100 | 121 | 107 | 14 | 0 | 1 | 1 | 11 | 2 | 0 | 0 | 13
32 |  | Madhugiri | 9 | 294 | 0 | 294 | 303 | 246 | 57 | 0 | 4 | 4 | 42 | 11 | 0 | 0 | 53
| Total |  | 55 | 525 | 5 | 520 | 575 | 482 | 93 | 0 | 5 | 5 | 63 | 23 | 0 | 2 | 88
| BESCOM Total |  | 1129 | 2866 | 45 | 2821 | 3950 | 2977 | 973 | 0 | 57 | 57 | 394 | 452 | 0 | 70 | 916