## Abstract_Comm_Indi (cumulative)
Bangalore Electricity Supply Company Limited
Progress & pending Application details of Gangakalyana upto Feb-20
All Schemes
Sl No | Circle | Division | Opening balance of applications as on 1-4-2019 | Total applications received during the year 2019-20 (up to Feb-20) | Total applications lapsed during the year 2019-20 (up to Feb-20) | Total applications added during the year 2019-20 (up to Feb-20) | Total Valid Applications | Total borewells energised during the year 2019-20 (up toFeb-20) | Applications pending as at the end of the year 2019-20 (up to Feb-20) | Work Completed Service Not availed | Formalities Not observed | Applications pending at Corporation End | Work Under Progress | Work to be taken Up | Work order to be issued | Estimate to be prepared | Applications pending at BESCOM End
|  |  | 1 | 2 | 3 | 4=2-3 | 5=1+4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | North | Malleshwaram | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | Hebbala | 20 | 23 | 17 | 6 | 26 | 1 | 25 | 0 | 7 | 7 | 8 | 10 | 0 | 0 | 18
3 |  | Peenya | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | Jalahalli | 17 | 17 | 0 | 17 | 34 | 6 | 28 | 0 | 5 | 5 | 23 | 0 | 0 | 0 | 23
| Total |  | 37 | 40 | 17 | 23 | 60 | 7 | 53 | 0 | 12 | 12 | 31 | 10 | 0 | 0 | 41
5 | East | Indiranagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Shivajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | Vidhanasoudha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Whitefield | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BMANZ |  |  | 37 | 40 | 17 | 23 | 60 | 7 | 53 | 0 | 12 | 12 | 31 | 10 | 0 | 0 | 41
9 | South | Jaynagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Kormangala | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  | H S R | 1 | 0 | 1 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 1 | 0 | 1 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | West | Rajajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  | Rajarajeshwari nagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | Kengeri | 0 | 15 | 0 | 15 | 15 | 2 | 13 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 13
| Total |  | 0 | 15 | 0 | 15 | 15 | 2 | 13 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 13
| BMASZ |  | 1 | 15 | 1 | 14 | 15 | 2 | 13 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 13
15 | Blore Rural | Nelmangala | 24 | 96 | 3 | 93 | 117 | 101 | 16 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 16
16 |  | Yelhanka | 16 | 51 | 4 | 47 | 63 | 43 | 20 | 0 | 6 | 6 | 14 | 0 | 0 | 0 | 14
| Total |  | 40 | 147 | 7 | 140 | 180 | 144 | 36 | 0 | 6 | 6 | 14 | 16 | 0 | 0 | 30
17 | Ramnagara | Ramnagara | 1 | 13 | 0 | 13 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 |  | Magadi | 0 | 26 | 0 | 26 | 26 | 25 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
19 |  | Chandapura | 31 | 73 | 5 | 68 | 99 | 73 | 26 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 26
20 |  | Kanakpura | 2 | 26 | 2 | 24 | 26 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 34 | 138 | 7 | 131 | 165 | 138 | 27 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 27
21 | Kolar | Kolar | 23 | 112 | 13 | 99 | 122 | 114 | 8 | 0 | 0 | 0 | 3 | 2 | 3 | 0 | 8
22 |  | K G F | 32 | 175 | 2 | 173 | 205 | 173 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 32
23 |  | C B Pura | 16 | 42 | 7 | 35 | 51 | 49 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 2
24 |  | Chintamani | 7 | 61 | 6 | 55 | 62 | 60 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
| Total |  | 78 | 390 | 28 | 362 | 440 | 396 | 44 | 0 | 0 | 0 | 38 | 2 | 3 | 1 | 44
25 | Davangere | Davangere | 224 | 172 | 17 | 155 | 379 | 346 | 33 | 0 | 1 | 1 | 0 | 25 | 0 | 7 | 32
26 |  | Harihara | 142 | 117 | 1 | 116 | 258 | 248 | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 10
27 |  | Chitradurga | 536 | 1054 | 5 | 1049 | 1585 | 810 | 775 | 0 | 3 | 3 | 156 | 480 | 0 | 136 | 772
28 |  | Hiriyur | 104 | 454 | 0 | 454 | 558 | 475 | 83 | 0 | 0 | 0 | 48 | 27 | 1 | 7 | 83
| Total |  | 1006 | 1797 | 23 | 1774 | 2780 | 1879 | 901 | 0 | 4 | 4 | 204 | 542 | 1 | 150 | 897
29 | Tumkur | Tumkur | 111 | 126 | 40 | 86 | 197 | 187 | 10 | 0 | 7 | 7 | 3 | 0 | 0 | 0 | 3
30 |  | Kunigal | 4 | 31 | 5 | 26 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 |  | Tiptur | 47 | 71 | 9 | 62 | 109 | 84 | 25 | 0 | 7 | 7 | 1 | 0 | 17 | 0 | 18
32 |  | Madhugiri | 140 | 226 | 4 | 222 | 362 | 358 | 4 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 2
| Total |  | 302 | 454 | 58 | 396 | 698 | 659 | 39 | 0 | 16 | 16 | 6 | 0 | 17 | 0 | 23
| BESCOM Total |  | 1498 | 2981 | 141 | 2840 | 4338 | 3225 | 1113 | 0 | 38 | 38 | 333 | 570 | 21 | 151 | 1075