## Abstract_Comm_Indi (cumulative)
Bangalore Electricity Supply Company Limited
Progress & pending Application details of Gangakalyana upto Aug-19
All Schemes
Sl No | Circle | Division | Opening balance of applications as on 1-4-2019 | Total applications received during the year 2019-20 (up to Aug-19) | Total applications lapsed during the year 2019-20 (up to Aug-19) | Total applications added during the year 2019-20 (up to Aug-19) | Total Valid Applications | Total borewells energised during the year 2019-20 (up to Aug-19) | Applications pending as at the end of the year 2019-20 (up to Aug-19) | Work Completed Service Not availed | Formalities Not observed | Applications pending at Corporation End | Work Under Progress | Work to be taken Up | Work order to be issued | Estimate to be prepared | Applications pending at BESCOM End
|  |  | 1 | 2 | 3 | 4=2-3 | 5=1+3 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | North | Malleshwaram | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | Hebbala | 20 | 0 | 14 | -14 | 6 | 0 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
3 |  | Peenya | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | Jalahalli | 17 | 11 | 0 | 11 | 28 | 0 | 28 | 0 | 5 | 5 | 7 | 9 | 0 | 7 | 23
| Total |  | 37 | 11 | 14 | -3 | 34 | 0 | 34 | 0 | 11 | 11 | 7 | 9 | 0 | 7 | 23
5 | East | Indiranagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Shivajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | Vidhanasoudha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Whitefield | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BMANZ |  |  | 37 | 11 | 14 | -3 | 34 | 0 | 34 | 0 | 11 | 11 | 7 | 9 | 0 | 7 | 23
9 | South | Jaynagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Kormangala | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  | H S R | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Total |  | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
12 | West | Rajajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
13 |  | Rajarajeshwari nagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | Kengeri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BMASZ |  | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
15 | Blore Rural | Nelmangala | 24 | 26 | 3 | 23 | 47 | 33 | 14 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 14
16 |  | Yelhanka | 16 | 14 | 1 | 13 | 29 | 13 | 16 | 0 | 10 | 10 | 2 | 2 | 0 | 2 | 6
| Total |  | 40 | 40 | 4 | 36 | 76 | 46 | 30 | 0 | 10 | 10 | 2 | 16 | 0 | 2 | 20
17 | Ramnagara | Ramnagara | 1 | 11 | 0 | 11 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 |  | Magadi | 0 | 6 | 0 | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
19 |  | Chandapura | 31 | 33 | 2 | 31 | 62 | 53 | 9 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 9
20 |  | Kanakpura | 2 | 19 | 0 | 19 | 21 | 18 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3
| Total |  | 34 | 69 | 2 | 67 | 101 | 87 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 14
21 | Kolar | Kolar | 23 | 45 | 13 | 32 | 55 | 33 | 22 | 0 | 0 | 0 | 6 | 0 | 0 | 16 | 22
22 |  | K G F | 32 | 50 | 0 | 50 | 82 | 69 | 13 | 0 | 0 | 0 | 7 | 6 | 0 | 0 | 13
23 |  | C B Pura | 16 | 35 | 3 | 32 | 48 | 39 | 9 | 0 | 3 | 3 | 3 | 0 | 0 | 3 | 6
24 |  | Chintamani | 7 | 50 | 4 | 46 | 53 | 47 | 6 | 1 | 0 | 1 | 1 | 4 | 0 | 0 | 5
| Total |  | 78 | 180 | 20 | 160 | 238 | 188 | 50 | 1 | 3 | 4 | 17 | 10 | 0 | 19 | 46
25 | Davangere | Davangere | 224 | 108 | 9 | 99 | 323 | 267 | 56 | 0 | 0 | 0 | 8 | 40 | 0 | 8 | 56
26 |  | Harihara | 142 | 83 | 1 | 82 | 224 | 199 | 25 | 0 | 0 | 0 | 6 | 19 | 0 | 0 | 25
27 |  | Chitradurga | 536 | 320 | 3 | 317 | 853 | 248 | 605 | 0 | 12 | 12 | 7 | 483 | 6 | 97 | 593
28 |  | Hiriyur | 104 | 169 | 0 | 169 | 273 | 181 | 92 | 0 | 7 | 7 | 35 | 50 | 0 | 0 | 85
| Total |  | 1006 | 680 | 13 | 667 | 1673 | 895 | 778 | 0 | 19 | 19 | 56 | 592 | 6 | 105 | 759
29 | Tumkur | Tumkur | 111 | 91 | 19 | 72 | 183 | 141 | 42 | 0 | 14 | 14 | 20 | 6 | 0 | 2 | 28
30 |  | Kunigal | 4 | 28 | 5 | 23 | 27 | 25 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 2
31 |  | Tiptur | 47 | 41 | 8 | 33 | 80 | 60 | 20 | 0 | 3 | 3 | 13 | 3 | 0 | 1 | 17
32 |  | Madhugiri | 140 | 163 | 0 | 163 | 303 | 263 | 40 | 0 | 2 | 2 | 31 | 6 | 1 | 0 | 38
| Total |  | 302 | 323 | 32 | 291 | 593 | 489 | 104 | 0 | 19 | 19 | 65 | 15 | 1 | 4 | 85
| BESCOM Total |  | 1498 | 1303 | 85 | 1218 | 2716 | 1705 | 1011 | 1 | 63 | 64 | 161 | 642 | 7 | 137 | 947
|  | Assistant General Manager(Op-3) | [5 empty] | 11: Deputy General Manager(Op-1)
|  | BESCOM | [5 empty] | 11: BESCOM
Chief General Manager(Op)
BESCOM
Dec
Aug