## Abstract_Comm_Indi (cumulative)
Bangalore Electricity Supply Company Limited
Progress & pending Application details of Gangakalyana upto Jan-23
All Corporations | [12 empty] | Annexure-1
Sl No | Circle | Division | Opening balance of applications as on 1-4-2022 | Total applications received during the year 2022-23 (up to Jan-23) | Total applications lapsed during the year 2022-23 (up to Jan-23) | Total applications added during the year 2022-23 (up to Jan-23) | Total Valid Applications | Total borewells energised during the year 2022-23 (up to Jan-23) | Applications pending as at the end of the year 2022-23 (up to Jan-23) | Work Completed Service Not availed | Formalities Not observed | Applications pending at Corporation End | Work Under Progress | Work to be taken Up | Work order to be issued | Estimate to be prepared | Applications pending at BESCOM End
|  |  | 1 | 2 | 3 | 4=2-3 | 5=1+4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | North | Malleshwaram | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | Hebbala | 4 | 3 | 0 | 3 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 |  | Peenya | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | Jalahalli | 1 | 2 | 0 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 5 | 5 | 0 | 5 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | East | Indiranagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Shivajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | Vidhanasoudha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Whitefield | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BMANZ |  |  | 5 | 5 | 0 | 5 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | South | Jaynagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Kormangala | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  | H S R | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | West | Rajajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
13 |  | Rajarajeshwari nagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | Kengeri | 2 | 3 | 1 | 2 | 4 | 2 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0
| Total |  | 2 | 3 | 1 | 2 | 4 | 2 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0
| BMASZ |  | 2 | 3 | 1 | 2 | 4 | 2 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0
15 | Blore Rural | Nelmangala | 2 | 45 | 0 | 45 | 47 | 46 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0
16 |  | Yelhanka | 1 | 16 | 1 | 15 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 3 | 61 | 1 | 60 | 63 | 62 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0
17 | Ramnagara | Ramnagara | 3 | 19 | 2 | 17 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 |  | Magadi | 2 | 25 | 2 | 23 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 |  | Chandapura | 0 | 12 | 0 | 12 | 12 | 8 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0
20 |  | Kanakpura | 0 | 21 | 0 | 21 | 21 | 20 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 28
| Total |  | 5 | 77 | 4 | 73 | 78 | 73 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0
21 | Kolar | Kolar | 6 | 64 | 0 | 64 | 70 | 67 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0
22 |  | K G F | 24 | 161 | 0 | 161 | 185 | 174 | 11 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 11 | 0
23 |  | C B Pura | 14 | 257 | 0 | 257 | 271 | 257 | 14 | 0 | 0 | 0 | 9 | 5 | 0 | 0 | 14 | 0
24 |  | Chintamani | 19 | 151 | 1 | 150 | 169 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 63 | 633 | 1 | 632 | 695 | 667 | 28 | 0 | 0 | 0 | 23 | 5 | 0 | 0 | 28 | 0
25 | Davangere | Davangere | 49 | 351 | 4 | 347 | 396 | 351 | 45 | 0 | 0 | 0 | 43 | 2 | 0 | 0 | 45 | 0
26 |  | Harihara | 0 | 145 | 0 | 145 | 145 | 117 | 28 | 0 | 0 | 0 | 20 | 8 | 0 | 0 | 28 | 0
27 |  | Chitradurga | 57 | 433 | 15 | 418 | 475 | 470 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0
28 |  | Hiriyur | 0 | 113 | 0 | 113 | 113 | 112 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0
| Total |  | 106 | 1042 | 19 | 1023 | 1129 | 1050 | 79 | 0 | 0 | 0 | 68 | 11 | 0 | 0 | 79 | 0
29 | Tumkur | Tumkur | 17 | 76 | 1 | 75 | 92 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 |  | Kunigal | 1 | 10 | 0 | 10 | 11 | 10 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0
31 |  | Tiptur | 22 | 36 | 2 | 34 | 56 | 51 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0
32 |  | Madhugiri | 0 | 39 | 0 | 39 | 39 | 29 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 10 | 0
| Total |  | 40 | 161 | 3 | 158 | 198 | 182 | 16 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 0
| BESCOM Total |  | 224 | 1982 | 29 | 1953 | 2177 | 2046 | 131 | 0 | 0 | 0 | 115 | 16 | 0 | 0 | 131 | 0