## Abstract_Comm_Indi (cumulative) (hidden)
Bangalore Electricity Supply Company Limited
Progress & pending Application details of Gangakalyana upto Jan-24
All Corporations | [12 empty] | Annexure-1
Sl No | Circle | Division | Opening balance of applications as on 1-4-2023 | Total applications received during the year 2023-24 (up to Jan-24) | Total applications lapsed during the year 2023-24 (up to Jan-24) | Total applications added during the year 2023-24 (up to Jan-24) | Total Valid Applications | Total borewells energised during the year 2023-24 (up to Jan-24) | Applications pending as at the end of the year 2023-24 (up to Jan-24) | Work Completed Service Not availed | Formalities Not observed | Applications pending at Corporation End | Work Under Progress | Work to be taken Up | Work order to be issued | Estimate to be prepared | Applications pending at BESCOM End
|  |  | 1 | 2 | 3 | 4=2-3 | 5=1+4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | North | Malleshwaram | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | Hebbala | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 |  | Peenya | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | Jalahalli | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | East | Indiranagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Shivajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | Vidhanasoudha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Whitefield | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BMANZ |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | South | Jaynagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Kormangala | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  | H S R | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | West | Rajajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  | Rajarajeshwari nagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | Kengeri | 0 | 3 | 0 | 3 | 3 | 2 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 3 | 0 | 3 | 3 | 2 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| BMASZ |  | 0 | 3 | 0 | 3 | 3 | 2 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
15 | Blore Rural | Nelmangala | 6 | 51 | 0 | 51 | 57 | 19 | 38 | 0 | 17 | 17 | 8 | 12 | 0 | 1 | 21
16 |  | Yelhanka | 0 | 42 | 1 | 41 | 41 | 18 | 23 | 0 | 0 | 0 | 7 | 16 | 0 | 0 | 23
| Total |  | 6 | 93 | 1 | 92 | 98 | 37 | 61 | 0 | 17 | 17 | 15 | 28 | 0 | 1 | 44
17 | Ramnagara | Ramnagara | 0 | 3 | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
18 |  | Magadi | 0 | 11 | 0 | 11 | 11 | 1 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 10
19 |  | Chandapura | 1 | 23 | 0 | 23 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 |  | Kanakpura | 0 | 6 | 0 | 6 | 6 | 3 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
| Total |  | 1 | 43 | 1 | 42 | 43 | 29 | 14 | 0 | 3 | 3 | 11 | 0 | 0 | 0 | 11
21 | Kolar | Kolar | 0 | 36 | 0 | 36 | 36 | 22 | 12 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12
22 |  | K G F | 7 | 88 | 4 | 84 | 91 | 56 | 37 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 37
23 |  | C B Pura | 6 | 156 | 1 | 155 | 161 | 138 | 23 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 23
24 |  | Chintamani | 1 | 27 | 0 | 27 | 28 | 23 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5
| Total |  | 14 | 307 | 5 | 302 | 316 | 239 | 77 | 0 | 0 | 0 | 77 | 0 | 0 | 0 | 77
25 | Davangere | Davangere | 2 | 171 | 3 | 168 | 170 | 111 | 59 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 59
26 |  | Harihara | 9 | 124 | 5 | 119 | 128 | 106 | 22 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 22
27 |  | Chitradurga | 10 | 348 | 0 | 348 | 358 | 310 | 48 | 0 | 0 | 0 | 35 | 13 | 0 | 0 | 48
28 |  | Hiriyur | 30 | 100 | 0 | 100 | 130 | 94 | 36 | 0 | 0 | 0 | 14 | 22 | 0 | 0 | 36
| Total |  | 51 | 743 | 8 | 735 | 786 | 621 | 165 | 0 | 0 | 0 | 130 | 35 | 0 | 0 | 165
29 | Tumkur | Tumkur | 0 | 147 | 1 | 146 | 146 | 78 | 68 | 0 | 19 | 19 | 42 | 7 | 0 | 0 | 49
30 |  | Kunigal | 0 | 21 | 0 | 21 | 21 | 7 | 14 | 0 | 3 | 3 | 11 | 0 | 0 | 0 | 11
31 |  | Tiptur | 1 | 73 | 0 | 73 | 74 | 32 | 42 | 0 | 13 | 13 | 22 | 1 | 0 | 6 | 29
32 |  | Madhugiri | 1 | 78 | 0 | 78 | 79 | 38 | 41 | 0 | 0 | 0 | 36 | 3 | 0 | 2 | 41
| Total |  | 2 | 319 | 1 | 318 | 320 | 155 | 165 | 0 | 35 | 35 | 111 | 11 | 0 | 8 | 130
| BESCOM Total |  | 74 | 1508 | 16 | 1492 | 1566 | 1083 | 483 | 0 | 56 | 56 | 344 | 74 | 0 | 9 | 427

## Website kannada
¨ÉAUÀ¼ÀÆgÀÄ «zÀÄåvï ¸ÀgÀ§gÁdÄ PÀA¥À¤ ¤AiÀÄ«ÄvÀ
2023-24 £ÉÃ ¸Á°£À d£ÀªÀj-24 gÀ CAvÀåPÉÌ UÀAUÁPÀ¯Áåt AiÉÆÃd£ÀAiÀÄr «zÀÄåvï ¸ÀA¥ÀPÀð PÀ°à¹zÀ ºÁUÀÆ ¨ÁQ EgÀÄªÀ CfðUÀ¼À «ªÀgÀUÀ¼ÀÄ
J¯Áè C©üªÀÈ¢Þ ¤UÀªÀÄUÀ¼ÀÄ ¸ÉÃj
PÀæªÀÄ ¸ÀASÉå | ªÀÈvÀÛ | «¨sÁUÀ | 31.03.2023 gÀ CAvÀåPÉÌ ¨ÁQ EgÀÄªÀ CfðUÀ¼À ¸ÀASÉå | 2023-24 £ÉÃ ¸Á°£À (d£ÀªÀj-24gÀ CAvÀåPÉÌ) £ÉÆÃAzÀtÂUÉÆAqÀ CfðUÀ¼À ¸ÀASÉå | 2023-24 £ÉÃ ¸Á°£À (d£ÀªÀj-24 gÀ CAvÀåPÉÌ) gÀzÁÝzÀ CfðUÀ¼À ¸ÀASÉå | 2023-24 £ÉÃ ¸Á°£À (d£ÀªÀj-24gÀ CAvÀåPÉÌ) £ÉÆÃAzÀtÂUÉÆAqÀ MlÄÖ CfðUÀ¼À ¸ÀASÉå | MlÄÖ CfðUÀ¼À ¸ÀASÉå | 2023-24 £ÉÃ ¸Á°£À (d£ÀªÀj-24 gÀ CAvÀåPÉÌ) «zÀÄåvï ¸ÀA¥ÀPÀð ¥ÀqÉzÀ MlÄÖ CfðUÀ¼À ¸ÀASÉå | 2023-24 £ÉÃ ¸Á°£À (d£ÀªÀj-24 gÀ CAvÀåPÉÌ) ¨ÁQ EgÀÄªÀ MlÄÖ CfðUÀ¼À ¸ÀASÉå | ¨É«PÀA ªÀw¬ÄAzÀ PÉ®¸À ªÀÄÄV¢zÀÄÝ DzÀgÉ C©üªÀÈ¢Þ ¤UÀªÀÄzÀªÀgÀÄ «zÀÄåvï ¸ÀA¥ÀPÀð vÉUÉzÀÄPÉÆ¼Àî¢gÀÄªÀ CfðUÀ¼À ¸ÀASÉå | C©üªÀÈ¢Þ ¤UÀªÀÄzÀªÀgÀÄ ¨É«PÀA£À ¤AiÀÄªÀÄUÀ¼À£ÀÄß ¥Á°¸À¢gÀÄªÀ CfðUÀ¼À ¸ÀASÉå | wAUÀ¼À CAvÀåPÉÌ C©üªÀÈ¢Þ ¤UÀªÀÄzÀªÀgÀªÀw¬ÄAzÀ ¨ÁQ EgÀÄªÀ MlÄÖ CfðUÀ¼À ¸ÀASÉå | PÁAiÀÄð ¥ÀæUÀwAiÀÄ°ègÀÄªÀ CfðUÀ¼À ¸ÀASÉå | PÁAiÀÄð PÉÊUÉwÛ PÉÆ¼Àî¨ÉÃPÁVgÀÄªÀ CfðUÀ¼À ¸ÀASÉå | PÁAiÀiÁðzÉÃ±À ¤ÃqÀ ¨ÉÃPÁVgÀÄªÀ CfðUÀ¼À ¸ÀASÉå | CAzÁdÄ ¥ÀnÖ vÀ0iÀiÁj ºÀAvÀzÀ°ègÀÄªÀ ¸ÀASÉå | wAUÀ¼À CAvÀåPÉÌ ¨É«PÀA ªÀw¬ÄAzÀ ¨ÁQ EgÀÄªÀ MlÄÖ CfðUÀ¼À ¸ÀASÉå
|  |  | 1 | 2 | 3 | 4=2-3 | 5=1+4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | GvÀÛgÀ | ªÀÄ¯ÉèÃ±ÀégÀA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | ºÉ¨Áâ¼À | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 |  | ¦Ãtå | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | eÁ®ºÀ°î | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MlÄÖ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ¥ÀÆªÀð | EA¢gÁ£ÀUÀgÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | ²ªÁf£ÀUÀgÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | «zsÁ£À¸ËzsÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | ªÉÊmï¦üÃ¯ïØ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MlÄÖ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ¨ÉAUÀ¼ÀÆgÀÄ ªÀÄºÁ£ÀUÀgÀ GvÀÛgÀ PÉëÃvÀæ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | zÀQët | dAiÀÄ£ÀUÀgÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | PÉÆÃgÀªÀÄAUÀ® | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  | ºÉZï.J¸ï.Dgï | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MlÄÖ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | ¥À²ÑªÀÄ | gÁeÁf£ÀUÀgÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  | gÁdgÁeÉÃ±Àéj £ÀUÀgÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | PÉAUÉÃj | 0 | 3 | 0 | 3 | 3 | 2 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| MlÄÖ |  | 0 | 3 | 0 | 3 | 3 | 2 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| ¨ÉAUÀ¼ÀÆgÀÄ ªÀÄºÁ£ÀUÀgÀ zÀQët PÉëÃvÀæ |  | 0 | 3 | 0 | 3 | 3 | 2 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
15 | ¨ÉAUÀ¼ÀÆgÀÄ UÁæ«ÄÃt | £É®ªÀÄAUÀ® | 6 | 51 | 0 | 51 | 57 | 19 | 38 | 0 | 17 | 17 | 8 | 12 | 0 | 1 | 21
16 |  | AiÀÄ®ºÀAPÀ | 0 | 42 | 1 | 41 | 41 | 18 | 23 | 0 | 0 | 0 | 7 | 16 | 0 | 0 | 23
| MlÄÖ |  | 6 | 93 | 1 | 92 | 98 | 37 | 61 | 0 | 17 | 17 | 15 | 28 | 0 | 1 | 44
17 | gÁªÀÄ£ÀUÀgÀ | gÁªÀÄ£ÀUÀgÀ | 0 | 3 | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
18 |  | ªÀiÁUÀr | 0 | 11 | 0 | 11 | 11 | 1 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 10
19 |  | ZÀAzÁ¥ÀÄgÀ | 1 | 23 | 0 | 23 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 |  | PÀ£ÀPÀ¥ÀÄgÀ | 0 | 6 | 0 | 6 | 6 | 3 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
| MlÄÖ |  | 1 | 43 | 1 | 42 | 43 | 29 | 14 | 0 | 3 | 3 | 11 | 0 | 0 | 0 | 11
21 | PÉÆÃ¯ÁgÀ | PÀÉÆÃ¯ÁgÀ | 0 | 36 | 0 | 36 | 36 | 22 | 12 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12
22 |  | PÉ.f.J¥sï | 7 | 88 | 4 | 84 | 91 | 56 | 37 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 37
23 |  | aPÀÌ§¼Áî¥ÀÄgÀ | 6 | 156 | 1 | 155 | 161 | 138 | 23 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 23
24 |  | aAvÁªÀÄtÂ | 1 | 27 | 0 | 27 | 28 | 23 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5
| MlÄÖ |  | 14 | 307 | 5 | 302 | 316 | 239 | 77 | 0 | 0 | 0 | 77 | 0 | 0 | 0 | 77
25 | zÀÁªÀtUÉgÉ | zÀÁªÀtUÉgÉ | 2 | 171 | 3 | 168 | 170 | 111 | 59 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 59
26 |  | ºÀjºÀgÀ | 9 | 124 | 5 | 119 | 128 | 106 | 22 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 22
27 |  | avÀæzÀÄUÀð | 10 | 348 | 0 | 348 | 358 | 310 | 48 | 0 | 0 | 0 | 35 | 13 | 0 | 0 | 48
28 |  | »jAiÀÄÆgÀÄ | 30 | 100 | 0 | 100 | 130 | 94 | 36 | 0 | 0 | 0 | 14 | 22 | 0 | 0 | 36
| MlÄÖ |  | 51 | 743 | 8 | 735 | 786 | 621 | 165 | 0 | 0 | 0 | 130 | 35 | 0 | 0 | 165
29 | vÀÄªÀÄPÀÆgÀÄ | vÀÄªÀÄPÀÆgÀÄ | 0 | 147 | 1 | 146 | 146 | 78 | 68 | 0 | 19 | 19 | 42 | 7 | 0 | 0 | 49
30 |  | PÀÄtÂUÀ¯ï | 0 | 21 | 0 | 21 | 21 | 7 | 14 | 0 | 3 | 3 | 11 | 0 | 0 | 0 | 11
31 |  | w¥ÀlÆgÀÄ | 1 | 73 | 0 | 73 | 74 | 32 | 42 | 0 | 13 | 13 | 22 | 1 | 0 | 6 | 29
32 |  | ªÀÄzsÀÄVj | 1 | 78 | 0 | 78 | 79 | 38 | 41 | 0 | 0 | 0 | 36 | 3 | 0 | 2 | 41
| MlÄÖ |  | 2 | 319 | 1 | 318 | 320 | 155 | 165 | 0 | 35 | 35 | 111 | 11 | 0 | 8 | 130
| ¨É«PÀA MlÄÖ |  | 74 | 1508 | 16 | 1492 | 1566 | 1083 | 483 | 0 | 56 | 56 | 344 | 74 | 0 | 9 | 427