## Abstract_Comm_Indi (cumulative)
Bangalore Electricity Supply Company Limited
Progress & pending Application details of Gangakalyana upto July-22
All Corporations | [12 empty] | Annexure-1
Sl No | Circle | Division | Opening balance of applications as on 1-4-2022 | Total applications received during the year 2021-22 (up to July-22) | Total applications lapsed during the year 2021-22 (up to July-22) | Total applications added during the year 2021-22 (up to July-22) | Total Valid Applications | Total borewells energised during the year 2021-22 (up to July-22) | Applications pending as at the end of the year 2021-22 (up to July-22) | Work Completed Service Not availed | Formalities Not observed | Applications pending at Corporation End | Work Under Progress | Work to be taken Up | Work order to be issued | Estimate to be prepared | Applications pending at BESCOM End
|  |  | 1 | 2 | 3 | 4=2-3 | 5=1+4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | North | Malleshwaram | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | Hebbala | 4 | 3 | 0 | 3 | 7 | 6 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
3 |  | Peenya | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | Jalahalli | 1 | 2 | 0 | 2 | 3 | 0 | 3 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 2
| Total |  | 5 | 5 | 0 | 5 | 10 | 6 | 4 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2
5 | East | Indiranagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Shivajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | Vidhanasoudha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Whitefield | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BMANZ |  |  | 5 | 5 | 0 | 5 | 10 | 6 | 4 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2
9 | South | Jaynagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Kormangala | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  | H S R | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | West | Rajajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  | Rajarajeshwari nagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | Kengeri | 2 | 1 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
| Total |  | 2 | 1 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
| BMASZ |  | 2 | 1 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
15 | Blore Rural | Nelmangala | 2 | 14 | 0 | 14 | 16 | 12 | 4 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 4
16 |  | Yelhanka | 1 | 9 | 1 | 8 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 3 | 23 | 1 | 22 | 25 | 21 | 4 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 4
17 | Ramnagara | Ramnagara | 3 | 10 | 1 | 9 | 12 | 0 | 12 | 0 | 10 | 10 | 2 | 0 | 0 | 0 | 2
18 |  | Magadi | 2 | 5 | 2 | 3 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 |  | Chandapura | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 |  | Kanakpura | 0 | 2 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 5 | 17 | 3 | 14 | 19 | 7 | 12 | 0 | 10 | 10 | 2 | 0 | 0 | 0 | 2
21 | Kolar | Kolar | 6 | 48 | 0 | 48 | 54 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 |  | K G F | 24 | 33 | 0 | 33 | 57 | 49 | 8 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 8
23 |  | C B Pura | 14 | 75 | 0 | 75 | 89 | 66 | 23 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 23
24 |  | Chintamani | 19 | 91 | 1 | 90 | 109 | 65 | 44 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 44
| Total |  | 63 | 247 | 1 | 246 | 309 | 234 | 75 | 0 | 0 | 0 | 71 | 4 | 0 | 0 | 75
25 | Davangere | Davangere | 49 | 136 | 4 | 132 | 181 | 131 | 50 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 50
26 |  | Harihara | 0 | 48 | 0 | 48 | 48 | 44 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4
27 |  | Chitradurga | 57 | 331 | 3 | 328 | 385 | 344 | 41 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 41
28 |  | Hiriyur | 0 | 89 | 0 | 89 | 89 | 87 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
| Total |  | 106 | 604 | 7 | 597 | 703 | 606 | 97 | 0 | 0 | 0 | 97 | 0 | 0 | 0 | 97
29 | Tumkur | Tumkur | 17 | 69 | 1 | 68 | 85 | 74 | 11 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 11
30 |  | Kunigal | 1 | 8 | 0 | 8 | 9 | 6 | 3 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 2
31 |  | Tiptur | 22 | 30 | 2 | 28 | 50 | 40 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 10
32 |  | Madhugiri | 0 | 29 | 0 | 29 | 29 | 27 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
| Total |  | 40 | 136 | 3 | 133 | 173 | 147 | 26 | 0 | 1 | 1 | 25 | 0 | 0 | 0 | 25
| BESCOM Total |  | 224 | 1033 | 16 | 1017 | 1241 | 1021 | 220 | 1 | 12 | 13 | 201 | 6 | 0 | 0 | 207