## June-20
Bangalore Electricity Supply Company Limited
Progress & pending Application details of Gangakalyana upto June-20
All Schemes
Sl No | Circle | Division | Opening balance of applications as on 1-4-2020 | Total applications received during the year 2020-21 (up to June-20) | Total applications lapsed during the year 2020-21 (up to June-20) | Total applications added during the year 2020-21 (up to June-20) | Total Valid Applications | Total borewells energised during the year 2020-21 (up to June-20) | Applications pending as at the end of the year 2020-21 (up to June-20) | Work Completed Service Not availed | Formalities Not observed | Applications pending at Corporation End | Work Under Progress | Work to be taken Up | Work order to be issued | Estimate to be prepared | Applications pending at BESCOM End
|  |  | 1 | 2 | 3 | 4=2-3 | 5=1+4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | North | Malleshwaram | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | Hebbala | 25 | 1 | 1 | 0 | 25 | 22 | 3 | 0 | 2 | 2 | 0 | 1 | 0 | 0 | 1
3 |  | Peenya | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | Jalahalli | 18 | 2 | 0 | 2 | 20 | 7 | 13 | 0 | 1 | 1 | 10 | 0 | 2 | 0 | 12
| Total |  | 43 | 3 | 1 | 2 | 45 | 29 | 16 | 0 | 3 | 3 | 10 | 1 | 2 | 0 | 13
5 | East | Indiranagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Shivajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | Vidhanasoudha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Whitefield | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BMANZ |  |  | 43 | 3 | 1 | 2 | 45 | 29 | 16 | 0 | 3 | 3 | 10 | 1 | 2 | 0 | 13
9 | South | Jaynagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Kormangala | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  | H S R | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | West | Rajajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  | Rajarajeshwari nagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | Kengeri | 13 | 0 | 0 | 0 | 13 | 11 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
| Total |  | 13 | 0 | 0 | 0 | 13 | 11 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
| BMASZ |  | 13 | 0 | 0 | 0 | 13 | 11 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
15 | Blore Rural | Nelmangala | 15 | 34 | 0 | 34 | 49 | 13 | 36 | 0 | 0 | 0 | 10 | 26 | 0 | 0 | 36
16 |  | Yelhanka | 11 | 8 | 0 | 8 | 19 | 4 | 15 | 0 | 7 | 7 | 8 | 0 | 0 | 0 | 8
| Total |  | 26 | 42 | 0 | 42 | 68 | 17 | 51 | 0 | 7 | 7 | 18 | 26 | 0 | 0 | 44
17 | Ramnagara | Ramnagara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 |  | Magadi | 5 | 1 | 0 | 1 | 6 | 4 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
19 |  | Chandapura | 16 | 1 | 0 | 1 | 17 | 12 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5
20 |  | Kanakpura | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 21 | 2 | 0 | 2 | 23 | 16 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 7
21 | Kolar | Kolar | 17 | 11 | 0 | 11 | 28 | 25 | 3 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 3
22 |  | K G F | 23 | 53 | 0 | 53 | 76 | 40 | 36 | 0 | 0 | 0 | 32 | 0 | 1 | 3 | 36
23 |  | C B Pura | 2 | 11 | 0 | 11 | 13 | 3 | 10 | 0 | 0 | 0 | 9 | 1 | 0 | 0 | 10
24 |  | Chintamani | 2 | 7 | 0 | 7 | 9 | 1 | 8 | 0 | 0 | 0 | 1 | 0 | 3 | 4 | 8
| Total |  | 44 | 82 | 0 | 82 | 126 | 69 | 57 | 0 | 0 | 0 | 42 | 2 | 5 | 8 | 57
25 | Davangere | Davangere | 49 | 68 | 1 | 67 | 116 | 50 | 66 | 0 | 3 | 3 | 6 | 40 | 0 | 17 | 63
26 |  | Harihara | 9 | 6 | 0 | 6 | 15 | 9 | 6 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 6
27 |  | Chitradurga | 794 | 84 | 3 | 81 | 875 | 430 | 445 | 0 | 17 | 17 | 201 | 173 | 4 | 50 | 428
28 |  | Hiriyur | 75 | 74 | 0 | 74 | 149 | 107 | 42 | 0 | 0 | 0 | 6 | 28 | 0 | 8 | 42
| Total |  | 927 | 232 | 4 | 228 | 1155 | 596 | 559 | 0 | 20 | 20 | 215 | 245 | 4 | 75 | 539
29 | Tumkur | Tumkur | 13 | 10 | 1 | 9 | 22 | 15 | 7 | 0 | 2 | 2 | 3 | 2 | 0 | 0 | 5
30 |  | Kunigal | 12 | 4 | 0 | 4 | 16 | 13 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3
31 |  | Tiptur | 21 | 37 | 0 | 37 | 58 | 24 | 34 | 0 | 12 | 12 | 19 | 3 | 0 | 0 | 22
32 |  | Madhugiri | 9 | 75 | 0 | 75 | 84 | 16 | 68 | 0 | 3 | 3 | 2 | 62 | 0 | 1 | 65
| Total |  | 55 | 126 | 1 | 125 | 180 | 68 | 112 | 0 | 17 | 17 | 27 | 67 | 0 | 1 | 95
| BESCOM Total |  | 1129 | 487 | 6 | 481 | 1610 | 806 | 804 | 0 | 47 | 47 | 321 | 341 | 11 | 84 | 757