## Abstract_Comm_Indi (cumulative)
Bangalore Electricity Supply Company Limited
Progress & pending Application details of Gangakalyana upto May-21
All Corporations | [12 empty] | Annexure-1
Sl No | Circle | Division | Opening balance of applications as on 1-4-2021 | Total applications received during the year 2021-22 (up to May-21) | Total applications lapsed during the year 2021-22 (up to May-21) | Total applications added during the year 2021-22 (up to May-21) | Total Valid Applications | Total borewells energised during the year 2021-22 (up to May-21) | Applications pending as at the end of the year 2021-22 (up to May-21) | Work Completed Service Not availed | Formalities Not observed | Applications pending at Corporation End | Work Under Progress | Work to be taken Up | Work order to be issued | Estimate to be prepared | Applications pending at BESCOM End
|  |  | 1 | 2 | 3 | 4=2-3 | 5=1+4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | North | Malleshwaram | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | Hebbala | 4 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 1 | 1 | 0 | 3 | 0 | 0 | 3
3 |  | Peenya | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | Jalahalli | 9 | 0 | 0 | 0 | 9 | 3 | 6 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 3
| Total |  | 13 | 0 | 0 | 0 | 13 | 3 | 10 | 0 | 4 | 4 | 3 | 3 | 0 | 0 | 6
5 | East | Indiranagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Shivajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | Vidhanasoudha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Whitefield | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BMANZ |  |  | 13 | 0 | 0 | 0 | 13 | 3 | 10 | 0 | 4 | 4 | 3 | 3 | 0 | 0 | 6
9 | South | Jaynagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Kormangala | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  | H S R | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | West | Rajajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  | Rajarajeshwari nagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | Kengeri | 5 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5
| Total |  | 5 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5
| BMASZ |  | 5 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5
15 | Blore Rural | Nelmangala | 14 | 9 | 0 | 9 | 23 | 9 | 14 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 14
16 |  | Yelhanka | 17 | 6 | 1 | 5 | 22 | 2 | 20 | 0 | 5 | 5 | 7 | 8 | 0 | 0 | 15
| Total |  | 31 | 15 | 1 | 14 | 45 | 11 | 34 | 0 | 5 | 5 | 7 | 22 | 0 | 0 | 29
17 | Ramnagara | Ramnagara | 13 | 8 | 0 | 8 | 21 | 10 | 11 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0
18 |  | Magadi | 1 | 5 | 0 | 5 | 6 | 0 | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 6
19 |  | Chandapura | 27 | 6 | 0 | 6 | 33 | 0 | 33 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 33
20 |  | Kanakpura | 27 | 4 | 0 | 4 | 31 | 22 | 9 | 0 | 0 | 0 | 6 | 3 | 0 | 0 | 9
| Total |  | 68 | 23 | 0 | 23 | 91 | 32 | 59 | 0 | 11 | 11 | 45 | 3 | 0 | 0 | 48
21 | Kolar | Kolar | 49 | 15 | 0 | 15 | 64 | 45 | 19 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 19
22 |  | K G F | 121 | 66 | 0 | 66 | 187 | 43 | 144 | 0 | 11 | 11 | 71 | 25 | 26 | 11 | 133
23 |  | C B Pura | 88 | 52 | 1 | 51 | 139 | 30 | 109 | 0 | 0 | 0 | 46 | 0 | 67 | 4 | 117
24 |  | Chintamani | 84 | 77 | 0 | 77 | 161 | 65 | 96 | 0 | 0 | 0 | 40 | 0 | 48 | 0 | 88
| Total |  | 342 | 210 | 1 | 209 | 551 | 183 | 368 | 0 | 11 | 11 | 176 | 25 | 141 | 15 | 357
25 | Davangere | Davangere | 129 | 74 | 1 | 73 | 202 | 39 | 163 | 0 | 2 | 2 | 9 | 124 | 0 | 28 | 161
26 |  | Harihara | 15 | 80 | 0 | 80 | 95 | 24 | 71 | 0 | 0 | 0 | 56 | 15 | 0 | 0 | 71
27 |  | Chitradurga | 184 | 76 | 1 | 75 | 259 | 50 | 209 | 0 | 9 | 9 | 67 | 67 | 66 | 0 | 200
28 |  | Hiriyur | 11 | 72 | 0 | 72 | 83 | 1 | 82 | 0 | 0 | 0 | 9 | 73 | 0 | 0 | 82
| Total |  | 339 | 302 | 2 | 300 | 639 | 114 | 525 | 0 | 11 | 11 | 141 | 279 | 66 | 28 | 514
29 | Tumkur | Tumkur | 5 | 78 | 0 | 78 | 83 | 2 | 81 | 0 | 7 | 7 | 74 | 0 | 0 | 0 | 74
30 |  | Kunigal | 5 | 8 | 0 | 8 | 13 | 5 | 8 | 0 | 0 | 0 | 7 | 1 | 0 | 0 | 8
31 |  | Tiptur | 6 | 32 | 0 | 32 | 38 | 14 | 24 | 0 | 3 | 3 | 13 | 1 | 7 | 0 | 21
32 |  | Madhugiri | 43 | 50 | 0 | 50 | 93 | 30 | 63 | 0 | 4 | 4 | 58 | 0 | 0 | 1 | 59
| Total |  | 59 | 168 | 0 | 168 | 227 | 51 | 176 | 0 | 14 | 14 | 152 | 2 | 7 | 1 | 162
| BESCOM Total |  | 857 | 718 | 4 | 714 | 1571 | 394 | 1177 | 0 | 56 | 56 | 529 | 334 | 214 | 44 | 1121