## Website English
Bangalore Electricity Supply Company Limited
Progress & pending Application details of Gangakalyana upto Nov-22
All Corporations | [12 empty] | Annexure-1
Sl No | Circle | Division | Opening balance of applications as on 1-4-2022 | Total applications received during the year 2022-23 (up to Nov-22) | Total applications lapsed during the year 2022-23 (up to Nov-22) | Total applications added during the year 2022-23 (up to Nov-22) | Total Valid Applications | Total borewells energised during the year 2022-23 (up to Nov-22) | Applications pending as at the end of the year 2022-23 (up to Nov-22) | Work Completed Service Not availed | Formalities Not observed | Applications pending at Corporation End | Work Under Progress | Work to be taken Up | Work order to be issued | Estimate to be prepared | Applications pending at BESCOM End
|  |  | 1 | 2 | 3 | 4=2-3 | 5=1+4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | North | Malleshwaram | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | Hebbala | 4 | 3 | 0 | 3 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 |  | Peenya | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | Jalahalli | 1 | 2 | 0 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 5 | 5 | 0 | 5 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | East | Indiranagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Shivajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | Vidhanasoudha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Whitefield | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BMANZ |  |  | 5 | 5 | 0 | 5 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | South | Jaynagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Kormangala | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  | H S R | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | West | Rajajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  | Rajarajeshwari nagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | Kengeri | 2 | 3 | 1 | 2 | 4 | 2 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
| Total |  | 2 | 3 | 1 | 2 | 4 | 2 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
| BMASZ |  | 2 | 3 | 1 | 2 | 4 | 2 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
15 | Blore Rural | Nelmangala | 2 | 39 | 0 | 39 | 41 | 37 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4
16 |  | Yelhanka | 1 | 14 | 1 | 13 | 14 | 12 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
| Total |  | 3 | 53 | 1 | 52 | 55 | 49 | 6 | 0 | 2 | 2 | 4 | 0 | 0 | 0 | 4
17 | Ramnagara | Ramnagara | 3 | 19 | 2 | 17 | 20 | 19 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
18 |  | Magadi | 2 | 23 | 2 | 21 | 23 | 11 | 12 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12
19 |  | Chandapura | 0 | 12 | 0 | 12 | 12 | 5 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 7
20 |  | Kanakpura | 0 | 18 | 0 | 18 | 18 | 16 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
| Total |  | 5 | 72 | 4 | 68 | 73 | 51 | 22 | 0 | 1 | 1 | 21 | 0 | 0 | 0 | 21
21 | Kolar | Kolar | 6 | 61 | 0 | 61 | 67 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 |  | K G F | 24 | 151 | 0 | 151 | 175 | 115 | 60 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 60
23 |  | C B Pura | 14 | 215 | 0 | 215 | 229 | 142 | 87 | 0 | 0 | 0 | 87 | 0 | 0 | 0 | 87
24 |  | Chintamani | 19 | 141 | 1 | 140 | 159 | 153 | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 6
| Total |  | 63 | 568 | 1 | 567 | 630 | 477 | 153 | 0 | 0 | 0 | 153 | 0 | 0 | 0 | 153
25 | Davangere | Davangere | 49 | 305 | 4 | 301 | 350 | 260 | 90 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 90
26 |  | Harihara | 0 | 68 | 0 | 68 | 68 | 61 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 7
27 |  | Chitradurga | 57 | 376 | 8 | 368 | 425 | 402 | 23 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 23
28 |  | Hiriyur | 0 | 107 | 0 | 107 | 107 | 106 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| Total |  | 106 | 856 | 12 | 844 | 950 | 829 | 121 | 0 | 0 | 0 | 121 | 0 | 0 | 0 | 121
29 | Tumkur | Tumkur | 17 | 72 | 1 | 71 | 88 | 87 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
30 |  | Kunigal | 1 | 10 | 0 | 10 | 11 | 9 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
31 |  | Tiptur | 22 | 31 | 2 | 29 | 51 | 50 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
32 |  | Madhugiri | 0 | 29 | 0 | 29 | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 40 | 142 | 3 | 139 | 179 | 175 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4
| BESCOM Total |  | 224 | 1699 | 22 | 1677 | 1901 | 1593 | 308 | 0 | 5 | 5 | 303 | 0 | 0 | 0 | 303