## Upto Sep-20
Bangalore Electricity Supply Company Limited
Progress & pending Application details of Gangakalyana upto Sep-20
All Schemes
Sl No | Circle | Division | Opening balance of applications as on 1-4-2020 | Total applications received during the year 2020-21 (up to Sep-20) | Total applications lapsed during the year 2020-21 (up to Sep-20) | Total applications added during the year 2020-21 (up to Sep-20) | Total Valid Applications | Total borewells energised during the year 2020-21 (up to Sep-20) | Applications pending as at the end of the year 2020-21 (up to Sep-20) | Work Completed Service Not availed | Formalities Not observed | Applications pending at Corporation End | Work Under Progress | Work to be taken Up | Work order to be issued | Estimate to be prepared | Applications pending at BESCOM End
|  |  | 1 | 2 | 3 | 4=2-3 | 5=1+4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | North | Malleshwaram | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | Hebbala | 25 | 3 | 2 | 1 | 26 | 22 | 4 | 0 | 1 | 1 | 2 | 1 | 0 | 0 | 3
3 |  | Peenya | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | Jalahalli | 18 | 4 | 0 | 4 | 22 | 10 | 12 | 0 | 1 | 1 | 11 | 0 | 0 | 0 | 11
| Total |  | 43 | 7 | 2 | 5 | 48 | 32 | 16 | 0 | 2 | 2 | 13 | 1 | 0 | 0 | 14
5 | East | Indiranagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Shivajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | Vidhanasoudha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Whitefield | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BMANZ |  |  | 43 | 7 | 2 | 5 | 48 | 32 | 16 | 0 | 2 | 2 | 13 | 1 | 0 | 0 | 14
9 | South | Jaynagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Kormangala | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  | H S R | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | West | Rajajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
13 |  | Rajarajeshwari nagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | Kengeri | 13 | 0 | 0 | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 13 | 0 | 0 | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BMASZ |  | 13 | 0 | 0 | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Blore Rural | Nelmangala | 15 | 65 | 0 | 65 | 80 | 54 | 26 | 0 | 11 | 11 | 0 | 15 | 0 | 0 | 15
16 |  | Yelhanka | 11 | 20 | 0 | 20 | 31 | 14 | 17 | 0 | 12 | 12 | 5 | 0 | 0 | 0 | 5
| Total |  | 26 | 85 | 0 | 85 | 111 | 68 | 43 | 0 | 23 | 23 | 5 | 15 | 0 | 0 | 20
17 | Ramnagara | Ramnagara | 0 | 17 | 0 | 17 | 17 | 14 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3
18 |  | Magadi | 5 | 11 | 0 | 11 | 16 | 6 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 10
19 |  | Chandapura | 16 | 22 | 1 | 21 | 37 | 22 | 15 | 0 | 4 | 4 | 10 | 0 | 1 | 0 | 11
20 |  | Kanakpura | 0 | 34 | 0 | 34 | 34 | 20 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 14
| Total |  | 21 | 84 | 1 | 83 | 104 | 62 | 42 | 0 | 4 | 4 | 37 | 0 | 1 | 0 | 38
21 | Kolar | Kolar | 17 | 39 | 0 | 39 | 56 | 37 | 19 | 0 | 0 | 0 | 0 | 0 | 11 | 8 | 19
22 |  | K G F | 23 | 149 | 0 | 149 | 172 | 146 | 26 | 0 | 3 | 3 | 23 | 0 | 0 | 0 | 23
23 |  | C B Pura | 2 | 11 | 0 | 11 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 |  | Chintamani | 2 | 18 | 0 | 18 | 20 | 18 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2
| Total |  | 44 | 217 | 0 | 217 | 261 | 214 | 47 | 0 | 3 | 3 | 23 | 1 | 11 | 9 | 44
25 | Davangere | Davangere | 49 | 180 | 1 | 179 | 228 | 94 | 134 | 0 | 1 | 1 | 5 | 90 | 0 | 38 | 133
26 |  | Harihara | 9 | 44 | 2 | 42 | 51 | 21 | 30 | 0 | 0 | 0 | 11 | 19 | 0 | 0 | 30
27 |  | Chitradurga | 794 | 247 | 9 | 238 | 1032 | 737 | 295 | 0 | 4 | 4 | 176 | 26 | 0 | 89 | 291
28 |  | Hiriyur | 75 | 209 | 0 | 209 | 284 | 197 | 87 | 0 | 0 | 0 | 12 | 63 | 0 | 12 | 87
| Total |  | 927 | 680 | 12 | 668 | 1595 | 1049 | 546 | 0 | 5 | 5 | 204 | 198 | 0 | 139 | 541
29 | Tumkur | Tumkur | 13 | 57 | 1 | 56 | 69 | 39 | 30 | 0 | 4 | 4 | 26 | 0 | 0 | 0 | 26
30 |  | Kunigal | 12 | 13 | 0 | 13 | 25 | 22 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3
31 |  | Tiptur | 21 | 61 | 0 | 61 | 82 | 66 | 16 | 0 | 11 | 11 | 5 | 0 | 0 | 0 | 5
32 |  | Madhugiri | 9 | 177 | 0 | 177 | 186 | 109 | 77 | 0 | 0 | 0 | 72 | 2 | 0 | 3 | 77
| Total |  | 55 | 308 | 1 | 307 | 362 | 236 | 126 | 0 | 15 | 15 | 106 | 2 | 0 | 3 | 111
| BESCOM Total |  | 1129 | 1381 | 16 | 1365 | 2494 | 1674 | 820 | 0 | 52 | 52 | 388 | 217 | 12 | 151 | 768