## Abstract_Comm_Indi (cumulative)
Bangalore Electricity Supply Company Limited
Progress & pending Application details of Gangakalyana upto Sep-22
All Corporations | [12 empty] | Annexure-1
Sl No | Circle | Division | Opening balance of applications as on 1-4-2022 | Total applications received during the year 2022-23 (up to Sep-22) | Total applications lapsed during the year 2022-23 (up to Sep-22) | Total applications added during the year 2022-23 (up to Sep-22) | Total Valid Applications | Total borewells energised during the year 2022-23 (up to Sep-22) | Applications pending as at the end of the year 2022-23 (up to Sep-22) | Work Completed Service Not availed | Formalities Not observed | Applications pending at Corporation End | Work Under Progress | Work to be taken Up | Work order to be issued | Estimate to be prepared | Applications pending at BESCOM End
|  |  | 1 | 2 | 3 | 4=2-3 | 5=1+4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | North | Malleshwaram | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | Hebbala | 4 | 3 | 0 | 3 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 |  | Peenya | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | Jalahalli | 1 | 2 | 0 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 5 | 5 | 0 | 5 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | East | Indiranagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Shivajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | Vidhanasoudha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Whitefield | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BMANZ |  |  | 5 | 5 | 0 | 5 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | South | Jaynagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Kormangala | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  | H S R | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | West | Rajajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  | Rajarajeshwari nagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | Kengeri | 2 | 1 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 2 | 1 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BMASZ |  | 2 | 1 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Blore Rural | Nelmangala | 2 | 35 | 0 | 35 | 37 | 17 | 20 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 20
16 |  | Yelhanka | 1 | 10 | 1 | 9 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 3 | 45 | 1 | 44 | 47 | 27 | 20 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 20
17 | Ramnagara | Ramnagara | 3 | 11 | 2 | 9 | 12 | 2 | 10 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0
18 |  | Magadi | 2 | 7 | 2 | 5 | 7 | 6 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
19 |  | Chandapura | 0 | 10 | 0 | 10 | 10 | 0 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 10
20 |  | Kanakpura | 0 | 18 | 0 | 18 | 18 | 2 | 16 | 0 | 0 | 0 | 9 | 7 | 0 | 0 | 16
| Total |  | 5 | 46 | 4 | 42 | 47 | 10 | 37 | 0 | 10 | 10 | 20 | 7 | 0 | 0 | 27
21 | Kolar | Kolar | 6 | 59 | 0 | 59 | 65 | 64 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
22 |  | K G F | 24 | 85 | 0 | 85 | 109 | 80 | 29 | 0 | 0 | 0 | 25 | 4 | 0 | 0 | 29
23 |  | C B Pura | 14 | 141 | 0 | 141 | 155 | 95 | 60 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 60
24 |  | Chintamani | 19 | 132 | 1 | 131 | 150 | 131 | 19 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 19
| Total |  | 63 | 417 | 1 | 416 | 479 | 370 | 109 | 0 | 0 | 0 | 105 | 4 | 0 | 0 | 109
25 | Davangere | Davangere | 49 | 253 | 4 | 249 | 298 | 150 | 148 | 0 | 0 | 0 | 148 | 0 | 0 | 0 | 148
26 |  | Harihara | 0 | 56 | 0 | 56 | 56 | 51 | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 5
27 |  | Chitradurga | 57 | 368 | 8 | 360 | 417 | 378 | 39 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 39
28 |  | Hiriyur | 0 | 105 | 0 | 105 | 105 | 97 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8
| Total |  | 106 | 782 | 12 | 770 | 876 | 676 | 200 | 0 | 0 | 0 | 195 | 5 | 0 | 0 | 200
29 | Tumkur | Tumkur | 17 | 71 | 1 | 70 | 87 | 81 | 6 | 0 | 1 | 1 | 5 | 0 | 0 | 0 | 5
30 |  | Kunigal | 1 | 10 | 0 | 10 | 11 | 8 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3
31 |  | Tiptur | 22 | 30 | 2 | 28 | 50 | 49 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
32 |  | Madhugiri | 0 | 29 | 0 | 29 | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 40 | 140 | 3 | 137 | 177 | 167 | 10 | 0 | 1 | 1 | 9 | 0 | 0 | 0 | 9
| BESCOM Total |  | 224 | 1436 | 22 | 1414 | 1638 | 1262 | 376 | 0 | 11 | 11 | 349 | 16 | 0 | 0 | 365
|  | Assistant General Manager(Op-3) | [5 empty] | 11: Deputy General Manager(Op-1)
|  | BESCOM | [5 empty] | 11: BESCOM
Chief General Manager(Op)
BESCOM