## Website English
Bangalore Electricity Supply Company Limited
Progress & pending Application details of Gangakalyana upto Jan-22
Annexure-1
Sl No | Circle | Division | Opening balance of applications as on 1-4-2021 | Total applications received during the year 2021-22 (up to Jan-22) | Total applications lapsed during the year 2021-22 (up to Jan-22) | Total applications added during the year 2021-22 (up to Jan-22) | Total Valid Applications | Total borewells energised during the year 2021-22 (up to Jan-22) | Applications pending as at the end of the year 2021-22 (up to Jan-22) | Work Completed Service Not availed | Formalities Not observed | Applications pending at Corporation End | Work Under Progress | Work to be taken Up | Work order to be issued | Estimate to be prepared | Applications pending at BESCOM End
|  |  | 1 | 2 | 3 | 4=2-3 | 5=1+4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | North | Malleshwaram | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | Hebbala | 4 | 2 | 1 | 1 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
3 |  | Peenya | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | Jalahalli | 9 | 1 | 0 | 1 | 10 | 9 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| Total |  | 13 | 3 | 1 | 2 | 15 | 13 | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2
5 | East | Indiranagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Shivajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | Vidhanasoudha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Whitefield | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BMANZ |  |  | 13 | 3 | 1 | 2 | 15 | 13 | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2
9 | South | Jaynagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Kormangala | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  | H S R | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | West | Rajajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9
13 |  | Rajarajeshwari nagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | Kengeri | 5 | 17 | 1 | 16 | 21 | 20 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Total |  | 5 | 17 | 1 | 16 | 21 | 20 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| BMASZ |  | 5 | 17 | 1 | 16 | 21 | 20 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
15 | Blore Rural | Nelmangala | 14 | 54 | 11 | 43 | 57 | 54 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3
16 |  | Yelhanka | 17 | 48 | 2 | 46 | 63 | 60 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3
| Total |  | 31 | 102 | 13 | 89 | 120 | 114 | 6 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 6
17 | Ramnagara | Ramnagara | 13 | 26 | 0 | 26 | 39 | 37 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
18 |  | Magadi | 1 | 83 | 1 | 82 | 83 | 79 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4
19 |  | Chandapura | 27 | 52 | 0 | 52 | 79 | 71 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8
20 |  | Kanakpura | 27 | 29 | 2 | 27 | 54 | 53 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 28
| Total |  | 68 | 190 | 3 | 187 | 255 | 240 | 15 | 0 | 3 | 3 | 12 | 0 | 0 | 0 | 12
1 | Kolar | Kolar | 49 | 77 | 0 | 77 | 126 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | K G F | 121 | 245 | 0 | 245 | 366 | 354 | 12 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 12 | 366 | 12
3 |  | C B Pura | 88 | 234 | 3 | 231 | 319 | 282 | 37 | 0 | 0 | 0 | 39 | 5 | 0 | 0 | 44 | 319 | 37
4 |  | Chintamani | 84 | 244 | 3 | 241 | 325 | 301 | 24 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 17
| Total |  | 342 | 800 | 6 | 794 | 1136 | 1063 | 73 | 0 | 0 | 0 | 62 | 11 | 0 | 0 | 73
25 | Davangere | Davangere | 129 | 314 | 9 | 305 | 434 | 346 | 88 | 0 | 0 | 0 | 22 | 66 | 0 | 0 | 88
26 |  | Harihara | 15 | 306 | 0 | 306 | 321 | 314 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 7
27 |  | Chitradurga | 184 | 413 | 7 | 406 | 590 | 571 | 19 | 0 | 0 | 0 | 13 | 6 | 0 | 0 | 19
28 |  | Hiriyur | 11 | 302 | 1 | 301 | 312 | 292 | 20 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 20
| Total |  | 339 | 1335 | 17 | 1318 | 1657 | 1523 | 134 | 0 | 0 | 0 | 62 | 72 | 0 | 0 | 134
29 | Tumkur | Tumkur | 5 | 255 | 1 | 254 | 259 | 234 | 25 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 25
30 |  | Kunigal | 5 | 21 | 0 | 21 | 26 | 25 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
31 |  | Tiptur | 6 | 170 | 2 | 168 | 174 | 151 | 23 | 0 | 8 | 8 | 15 | 0 | 0 | 0 | 15
32 |  | Madhugiri | 43 | 208 | 0 | 208 | 251 | 241 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 10
| Total |  | 59 | 654 | 3 | 651 | 710 | 651 | 59 | 0 | 8 | 8 | 51 | 0 | 0 | 0 | 51
| BESCOM Total |  | 857 | 3101 | 44 | 3057 | 3914 | 3624 | 290 | 0 | 12 | 12 | 191 | 87 | 0 | 0 | 278

## Website kannada
¨ÉAUÀ¼ÀÆgÀÄ «zÀÄåvï ¸ÀgÀ§gÁdÄ PÀA¥À¤ ¤AiÀÄ«ÄvÀ
2021-22 £ÉÃ ¸Á°£À d£ÀªÀj-22 gÀ CAvÀåPÉÌ UÀAUÁPÀ¯Áåt AiÉÆÃd£ÀAiÀÄr «zÀÄåvï ¸ÀA¥ÀPÀð PÀ°à¹zÀ ºÁUÀÆ ¨ÁQ EgÀÄªÀ CfðUÀ¼À «ªÀgÀUÀ¼ÀÄ
J¯Áè C©üªÀÈ¢Þ ¤UÀªÀÄUÀ¼ÀÄ ¸ÉÃj
PÀæªÀÄ ¸ÀASÉå | ªÀÈvÀÛ | «¨sÁUÀ | 31.03.2021 gÀ CAvÀåPÉÌ ¨ÁQ EgÀÄªÀ CfðUÀ¼À ¸ÀASÉå | 2021-22 £ÉÃ ¸Á°£À (d£ÀªÀj-22 gÀ CAvÀåPÉÌ) £ÉÆÃAzÀtÂUÉÆAqÀ CfðUÀ¼À ¸ÀASÉå | 2021-22 £ÉÃ ¸Á°£À (d£ÀªÀj-22 gÀ CAvÀåPÉÌ) gÀzÁÝzÀ CfðUÀ¼À ¸ÀASÉå | 2021-22 £ÉÃ ¸Á°£À (d£ÀªÀj-22 gÀ CAvÀåPÉÌ) £ÉÆÃAzÀtÂUÉÆAqÀ MlÄÖ CfðUÀ¼À ¸ÀASÉå | MlÄÖ CfðUÀ¼À ¸ÀASÉå | 2021-22 £ÉÃ ¸Á°£À (d£ÀªÀj-22 gÀ CAvÀåPÉÌ) «zÀÄåvï ¸ÀA¥ÀPÀð ¥ÀqÉzÀ MlÄÖ CfðUÀ¼À ¸ÀASÉå | 2021-22 £ÉÃ ¸Á°£À (d£ÀªÀj-22 gÀ CAvÀåPÉÌ) ¨ÁQ EgÀÄªÀ MlÄÖ CfðUÀ¼À ¸ÀASÉå | ¨É«PÀA ªÀw¬ÄAzÀ PÉ®¸À ªÀÄÄV¢zÀÄÝ DzÀgÉ C©üªÀÈ¢Þ ¤UÀªÀÄzÀªÀgÀÄ «zÀÄåvï ¸ÀA¥ÀPÀð vÉUÉzÀÄPÉÆ¼Àî¢gÀÄªÀ CfðUÀ¼À ¸ÀASÉå | C©üªÀÈ¢Þ ¤UÀªÀÄzÀªÀgÀÄ ¨É«PÀA£À ¤AiÀÄªÀÄUÀ¼À£ÀÄß ¥Á°¸À¢gÀÄªÀ CfðUÀ¼À ¸ÀASÉå | wAUÀ¼À CAvÀåPÉÌ C©üªÀÈ¢Þ ¤UÀªÀÄzÀªÀgÀªÀw¬ÄAzÀ ¨ÁQ EgÀÄªÀ MlÄÖ CfðUÀ¼À ¸ÀASÉå | PÁAiÀÄð ¥ÀæUÀwAiÀÄ°ègÀÄªÀ CfðUÀ¼À ¸ÀASÉå | PÁAiÀÄð PÉÊUÉwÛ PÉÆ¼Àî¨ÉÃPÁVgÀÄªÀ CfðUÀ¼À ¸ÀASÉå | PÁAiÀiÁðzÉÃ±À ¤ÃqÀ ¨ÉÃPÁVgÀÄªÀ CfðUÀ¼À ¸ÀASÉå | CAzÁdÄ ¥ÀnÖ vÀ0iÀiÁj ºÀAvÀzÀ°ègÀÄªÀ ¸ÀASÉå | wAUÀ¼À CAvÀåPÉÌ ¨É«PÀA ªÀw¬ÄAzÀ ¨ÁQ EgÀÄªÀ MlÄÖ CfðUÀ¼À ¸ÀASÉå
|  |  | 1 | 2 | 3 | 4=2-3 | 5=1+4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | GvÀÛgÀ | ªÀÄ¯ÉèÃ±ÀégÀA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | ºÉ¨Áâ¼À | 4 | 2 | 1 | 1 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
3 |  | ¦Ãtå | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | eÁ®ºÀ°î | 9 | 1 | 0 | 1 | 10 | 9 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| MlÄÖ |  | 13 | 3 | 1 | 2 | 15 | 13 | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2
5 | ¥ÀÆªÀð | EA¢gÁ£ÀUÀgÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | ²ªÁf£ÀUÀgÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | «zsÁ£À¸ËzsÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | ªÉÊmï¦üÃ¯ïØ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MlÄÖ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ¨ÉAUÀ¼ÀÆgÀÄ ªÀÄºÁ£ÀUÀgÀ GvÀÛgÀ PÉëÃvÀæ |  | 13 | 3 | 1 | 2 | 15 | 13 | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2
9 | zÀQët | dAiÀÄ£ÀUÀgÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | PÉÆÃgÀªÀÄAUÀ® | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  | ºÉZï.J¸ï.Dgï | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MlÄÖ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | ¥À²ÑªÀÄ | gÁeÁf£ÀUÀgÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  | gÁdgÁeÉÃ±Àéj £ÀUÀgÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | PÉAUÉÃj | 5 | 17 | 1 | 16 | 21 | 20 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| MlÄÖ |  | 5 | 17 | 1 | 16 | 21 | 20 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| ¨ÉAUÀ¼ÀÆgÀÄ ªÀÄºÁ£ÀUÀgÀ zÀQët PÉëÃvÀæ |  | 5 | 17 | 1 | 16 | 21 | 20 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
15 | ¨ÉAUÀ¼ÀÆgÀÄ UÁæ«ÄÃt | £É®ªÀÄAUÀ® | 14 | 54 | 11 | 43 | 57 | 54 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3
16 |  | AiÀÄ®ºÀAPÀ | 17 | 48 | 2 | 46 | 63 | 60 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3
| MlÄÖ |  | 31 | 102 | 13 | 89 | 120 | 114 | 6 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 6
17 | gÁªÀÄ£ÀUÀgÀ | gÁªÀÄ£ÀUÀgÀ | 13 | 26 | 0 | 26 | 39 | 37 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
18 |  | ªÀiÁUÀr | 1 | 83 | 1 | 82 | 83 | 79 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4
19 |  | ZÀAzÁ¥ÀÄgÀ | 27 | 52 | 0 | 52 | 79 | 71 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8
20 |  | PÀ£ÀPÀ¥ÀÄgÀ | 27 | 29 | 2 | 27 | 54 | 53 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| MlÄÖ |  | 68 | 190 | 3 | 187 | 255 | 240 | 15 | 0 | 3 | 3 | 12 | 0 | 0 | 0 | 12
21 | PÉÆÃ¯ÁgÀ | PÀÉÆÃ¯ÁgÀ | 49 | 77 | 0 | 77 | 126 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 |  | PÉ.f.J¥sï | 121 | 245 | 0 | 245 | 366 | 354 | 12 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 12
23 |  | aPÀÌ§¼Áî¥ÀÄgÀ | 88 | 234 | 3 | 231 | 319 | 282 | 37 | 0 | 0 | 0 | 39 | 5 | 0 | 0 | 44
24 |  | aAvÁªÀÄtÂ | 84 | 244 | 3 | 241 | 325 | 301 | 24 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 17
| MlÄÖ |  | 342 | 800 | 6 | 794 | 1136 | 1063 | 73 | 0 | 0 | 0 | 62 | 11 | 0 | 0 | 73
25 | zÀÁªÀtUÉgÉ | zÀÁªÀtUÉgÉ | 129 | 314 | 9 | 305 | 434 | 346 | 88 | 0 | 0 | 0 | 22 | 66 | 0 | 0 | 88
26 |  | ºÀjºÀgÀ | 15 | 306 | 0 | 306 | 321 | 314 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 7
27 |  | avÀæzÀÄUÀð | 184 | 413 | 7 | 406 | 590 | 571 | 19 | 0 | 0 | 0 | 13 | 6 | 0 | 0 | 19
28 |  | »jAiÀÄÆgÀÄ | 11 | 302 | 1 | 301 | 312 | 292 | 20 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 20
| MlÄÖ |  | 339 | 1335 | 17 | 1318 | 1657 | 1523 | 134 | 0 | 0 | 0 | 62 | 72 | 0 | 0 | 134
29 | vÀÄªÀÄPÀÆgÀÄ | vÀÄªÀÄPÀÆgÀÄ | 5 | 255 | 1 | 254 | 259 | 234 | 25 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 25
30 |  | PÀÄtÂUÀ¯ï | 5 | 21 | 0 | 21 | 26 | 25 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
31 |  | w¥ÀlÆgÀÄ | 6 | 170 | 2 | 168 | 174 | 151 | 23 | 0 | 8 | 8 | 15 | 0 | 0 | 0 | 15
32 |  | ªÀÄzsÀÄVj | 43 | 208 | 0 | 208 | 251 | 241 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 10
| MlÄÖ |  | 59 | 654 | 3 | 651 | 710 | 651 | 59 | 0 | 8 | 8 | 51 | 0 | 0 | 0 | 51
| ¨É«PÀA MlÄÖ |  | 857 | 3101 | 44 | 3057 | 3914 | 3624 | 290 | 0 | 12 | 12 | 191 | 87 | 0 | 0 | 278