## Website English
Bangalore Electricity Supply Company Limited
Progress & pending Application details of Gangakalyana upto March-22
Annexure-1
Sl No | Circle | Division | Opening balance of applications as on 1-4-2021 | Total applications received during the year 2021-22 (up to March-22) | Total applications lapsed during the year 2021-22 (up to March-22) | Total applications added during the year 2021-22 (up to March-22) | Total Valid Applications | Total borewells energised during the year 2021-22 (up to March-22) | Applications pending as at the end of the year 2021-22 (up to March-22) | Work Completed Service Not availed | Formalities Not observed | Applications pending at Corporation End | Work Under Progress | Work to be taken Up | Work order to be issued | Estimate to be prepared | Applications pending at BESCOM End
|  |  | 1 | 2 | 3 | 4=2-3 | 5=1+4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | North | Malleshwaram | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | Hebbala | 4 | 6 | 1 | 5 | 9 | 5 | 4 | 0 | 1 | 1 | 3 | 0 | 0 | 0 | 3
3 |  | Peenya | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | Jalahalli | 9 | 4 | 0 | 4 | 13 | 12 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| Total |  | 13 | 10 | 1 | 9 | 22 | 17 | 5 | 0 | 1 | 1 | 4 | 0 | 0 | 0 | 4
5 | East | Indiranagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Shivajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | Vidhanasoudha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Whitefield | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BMANZ |  |  | 13 | 10 | 1 | 9 | 22 | 17 | 5 | 0 | 1 | 1 | 4 | 0 | 0 | 0 | 4
9 | South | Jaynagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Kormangala | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  | H S R | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | West | Rajajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  | Rajarajeshwari nagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | Kengeri | 5 | 18 | 1 | 17 | 22 | 20 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
| Total |  | 5 | 18 | 1 | 17 | 22 | 20 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
| BMASZ |  | 5 | 18 | 1 | 17 | 22 | 20 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
15 | Blore Rural | Nelmangala | 14 | 58 | 11 | 47 | 61 | 59 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
16 |  | Yelhanka | 17 | 57 | 2 | 55 | 72 | 71 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| Total |  | 31 | 115 | 13 | 102 | 133 | 130 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3
17 | Ramnagara | Ramnagara | 13 | 27 | 0 | 27 | 40 | 37 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
18 |  | Magadi | 1 | 88 | 1 | 87 | 88 | 86 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
19 |  | Chandapura | 27 | 53 | 0 | 53 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 |  | Kanakpura | 27 | 34 | 3 | 31 | 58 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 68 | 202 | 4 | 198 | 266 | 261 | 5 | 0 | 3 | 3 | 2 | 0 | 0 | 0 | 2
1 | Kolar | Kolar | 49 | 102 | 0 | 102 | 151 | 145 | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 6
2 |  | K G F | 121 | 292 | 1 | 291 | 412 | 388 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24
3 |  | C B Pura | 88 | 270 | 3 | 267 | 355 | 348 | 7 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 14
4 |  | Chintamani | 84 | 268 | 3 | 265 | 349 | 323 | 26 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 19
| Total |  | 342 | 932 | 7 | 925 | 1267 | 1204 | 63 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 63
25 | Davangere | Davangere | 129 | 346 | 9 | 337 | 466 | 417 | 49 | 0 | 0 | 0 | 44 | 5 | 0 | 0 | 49
26 |  | Harihara | 15 | 337 | 3 | 334 | 349 | 349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 |  | Chitradurga | 184 | 540 | 9 | 531 | 715 | 658 | 57 | 0 | 0 | 0 | 57 | 0 | 0 | 0 | 57
28 |  | Hiriyur | 11 | 333 | 1 | 332 | 343 | 343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 339 | 1556 | 22 | 1534 | 1873 | 1767 | 106 | 0 | 0 | 0 | 101 | 5 | 0 | 0 | 106
29 | Tumkur | Tumkur | 5 | 280 | 1 | 279 | 284 | 267 | 17 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 17
30 |  | Kunigal | 5 | 23 | 0 | 23 | 28 | 27 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
31 |  | Tiptur | 6 | 190 | 7 | 183 | 189 | 167 | 22 | 0 | 5 | 5 | 17 | 0 | 0 | 0 | 17
32 |  | Madhugiri | 43 | 221 | 1 | 220 | 263 | 263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 59 | 714 | 9 | 705 | 764 | 724 | 40 | 0 | 5 | 5 | 35 | 0 | 0 | 0 | 35
| BESCOM Total |  | 857 | 3547 | 57 | 3490 | 4347 | 4123 | 224 | 0 | 11 | 11 | 208 | 5 | 0 | 0 | 213

## Website kannada
¨ÉAUÀ¼ÀÆgÀÄ «zÀÄåvï ¸ÀgÀ§gÁdÄ PÀA¥À¤ ¤AiÀÄ«ÄvÀ
2021-22 £ÉÃ ¸Á°£À ¥sÉ§æªÀj-22 gÀ CAvÀåPÉÌ UÀAUÁPÀ¯Áåt AiÉÆÃd£ÀAiÀÄr «zÀÄåvï ¸ÀA¥ÀPÀð PÀ°à¹zÀ ºÁUÀÆ ¨ÁQ EgÀÄªÀ CfðUÀ¼À «ªÀgÀUÀ¼ÀÄ
J¯Áè C©üªÀÈ¢Þ ¤UÀªÀÄUÀ¼ÀÄ ¸ÉÃj
PÀæªÀÄ ¸ÀASÉå | ªÀÈvÀÛ | «¨sÁUÀ | 31.03.2021 gÀ CAvÀåPÉÌ ¨ÁQ EgÀÄªÀ CfðUÀ¼À ¸ÀASÉå | 2021-22 £ÉÃ ¸Á°£À (¥sÉ§æªÀj-22 gÀ CAvÀåPÉÌ) £ÉÆÃAzÀtÂUÉÆAqÀ CfðUÀ¼À ¸ÀASÉå | 2021-22 £ÉÃ ¸Á°£À (¥sÉ§æªÀj-22 gÀ CAvÀåPÉÌ) gÀzÁÝzÀ CfðUÀ¼À ¸ÀASÉå | 2021-22 £ÉÃ ¸Á°£À (¥sÉ§æªÀj-22 gÀ CAvÀåPÉÌ) £ÉÆÃAzÀtÂUÉÆAqÀ MlÄÖ CfðUÀ¼À ¸ÀASÉå | MlÄÖ CfðUÀ¼À ¸ÀASÉå | 2021-22 £ÉÃ ¸Á°£À (¥sÉ§æªÀj-22 gÀ CAvÀåPÉÌ) «zÀÄåvï ¸ÀA¥ÀPÀð ¥ÀqÉzÀ MlÄÖ CfðUÀ¼À ¸ÀASÉå | 2021-22 £ÉÃ ¸Á°£À (¥sÉ§æªÀj-22 gÀ CAvÀåPÉÌ) ¨ÁQ EgÀÄªÀ MlÄÖ CfðUÀ¼À ¸ÀASÉå | ¨É«PÀA ªÀw¬ÄAzÀ PÉ®¸À ªÀÄÄV¢zÀÄÝ DzÀgÉ C©üªÀÈ¢Þ ¤UÀªÀÄzÀªÀgÀÄ «zÀÄåvï ¸ÀA¥ÀPÀð vÉUÉzÀÄPÉÆ¼Àî¢gÀÄªÀ CfðUÀ¼À ¸ÀASÉå | C©üªÀÈ¢Þ ¤UÀªÀÄzÀªÀgÀÄ ¨É«PÀA£À ¤AiÀÄªÀÄUÀ¼À£ÀÄß ¥Á°¸À¢gÀÄªÀ CfðUÀ¼À ¸ÀASÉå | wAUÀ¼À CAvÀåPÉÌ C©üªÀÈ¢Þ ¤UÀªÀÄzÀªÀgÀªÀw¬ÄAzÀ ¨ÁQ EgÀÄªÀ MlÄÖ CfðUÀ¼À ¸ÀASÉå | PÁAiÀÄð ¥ÀæUÀwAiÀÄ°ègÀÄªÀ CfðUÀ¼À ¸ÀASÉå | PÁAiÀÄð PÉÊUÉwÛ PÉÆ¼Àî¨ÉÃPÁVgÀÄªÀ CfðUÀ¼À ¸ÀASÉå | PÁAiÀiÁðzÉÃ±À ¤ÃqÀ ¨ÉÃPÁVgÀÄªÀ CfðUÀ¼À ¸ÀASÉå | CAzÁdÄ ¥ÀnÖ vÀ0iÀiÁj ºÀAvÀzÀ°ègÀÄªÀ ¸ÀASÉå | wAUÀ¼À CAvÀåPÉÌ ¨É«PÀA ªÀw¬ÄAzÀ ¨ÁQ EgÀÄªÀ MlÄÖ CfðUÀ¼À ¸ÀASÉå
|  |  | 1 | 2 | 3 | 4=2-3 | 5=1+4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | GvÀÛgÀ | ªÀÄ¯ÉèÃ±ÀégÀA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | ºÉ¨Áâ¼À | 4 | 6 | 1 | 5 | 9 | 5 | 4 | 0 | 1 | 1 | 3 | 0 | 0 | 0 | 3
3 |  | ¦Ãtå | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | eÁ®ºÀ°î | 9 | 4 | 0 | 4 | 13 | 12 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| MlÄÖ |  | 13 | 10 | 1 | 9 | 22 | 17 | 5 | 0 | 1 | 1 | 4 | 0 | 0 | 0 | 4
5 | ¥ÀÆªÀð | EA¢gÁ£ÀUÀgÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | ²ªÁf£ÀUÀgÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | «zsÁ£À¸ËzsÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | ªÉÊmï¦üÃ¯ïØ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MlÄÖ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ¨ÉAUÀ¼ÀÆgÀÄ ªÀÄºÁ£ÀUÀgÀ GvÀÛgÀ PÉëÃvÀæ |  | 13 | 10 | 1 | 9 | 22 | 17 | 5 | 0 | 1 | 1 | 4 | 0 | 0 | 0 | 4
9 | zÀQët | dAiÀÄ£ÀUÀgÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | PÉÆÃgÀªÀÄAUÀ® | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  | ºÉZï.J¸ï.Dgï | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MlÄÖ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | ¥À²ÑªÀÄ | gÁeÁf£ÀUÀgÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  | gÁdgÁeÉÃ±Àéj £ÀUÀgÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | PÉAUÉÃj | 5 | 18 | 1 | 17 | 22 | 20 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
| MlÄÖ |  | 5 | 18 | 1 | 17 | 22 | 20 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
| ¨ÉAUÀ¼ÀÆgÀÄ ªÀÄºÁ£ÀUÀgÀ zÀQët PÉëÃvÀæ |  | 5 | 18 | 1 | 17 | 22 | 20 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
15 | ¨ÉAUÀ¼ÀÆgÀÄ UÁæ«ÄÃt | £É®ªÀÄAUÀ® | 14 | 58 | 11 | 47 | 61 | 59 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
16 |  | AiÀÄ®ºÀAPÀ | 17 | 57 | 2 | 55 | 72 | 71 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| MlÄÖ |  | 31 | 115 | 13 | 102 | 133 | 130 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3
17 | gÁªÀÄ£ÀUÀgÀ | gÁªÀÄ£ÀUÀgÀ | 13 | 27 | 0 | 27 | 40 | 37 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
18 |  | ªÀiÁUÀr | 1 | 88 | 1 | 87 | 88 | 86 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
19 |  | ZÀAzÁ¥ÀÄgÀ | 27 | 53 | 0 | 53 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 |  | PÀ£ÀPÀ¥ÀÄgÀ | 27 | 34 | 3 | 31 | 58 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MlÄÖ |  | 68 | 202 | 4 | 198 | 266 | 261 | 5 | 0 | 3 | 3 | 2 | 0 | 0 | 0 | 2
21 | PÉÆÃ¯ÁgÀ | PÀÉÆÃ¯ÁgÀ | 49 | 102 | 0 | 102 | 151 | 145 | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 6
22 |  | PÉ.f.J¥sï | 121 | 292 | 1 | 291 | 412 | 388 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24
23 |  | aPÀÌ§¼Áî¥ÀÄgÀ | 88 | 270 | 3 | 267 | 355 | 348 | 7 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 14
24 |  | aAvÁªÀÄtÂ | 84 | 268 | 3 | 265 | 349 | 323 | 26 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 19
| MlÄÖ |  | 342 | 932 | 7 | 925 | 1267 | 1204 | 63 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 63
25 | zÀÁªÀtUÉgÉ | zÀÁªÀtUÉgÉ | 129 | 346 | 9 | 337 | 466 | 417 | 49 | 0 | 0 | 0 | 44 | 5 | 0 | 0 | 49
26 |  | ºÀjºÀgÀ | 15 | 337 | 3 | 334 | 349 | 349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 |  | avÀæzÀÄUÀð | 184 | 540 | 9 | 531 | 715 | 658 | 57 | 0 | 0 | 0 | 57 | 0 | 0 | 0 | 57
28 |  | »jAiÀÄÆgÀÄ | 11 | 333 | 1 | 332 | 343 | 343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MlÄÖ |  | 339 | 1556 | 22 | 1534 | 1873 | 1767 | 106 | 0 | 0 | 0 | 101 | 5 | 0 | 0 | 106
29 | vÀÄªÀÄPÀÆgÀÄ | vÀÄªÀÄPÀÆgÀÄ | 5 | 280 | 1 | 279 | 284 | 267 | 17 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 17
30 |  | PÀÄtÂUÀ¯ï | 5 | 23 | 0 | 23 | 28 | 27 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
31 |  | w¥ÀlÆgÀÄ | 6 | 190 | 7 | 183 | 189 | 167 | 22 | 0 | 5 | 5 | 17 | 0 | 0 | 0 | 17
32 |  | ªÀÄzsÀÄVj | 43 | 221 | 1 | 220 | 263 | 263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MlÄÖ |  | 59 | 714 | 9 | 705 | 764 | 724 | 40 | 0 | 5 | 5 | 35 | 0 | 0 | 0 | 35
| ¨É«PÀA MlÄÖ |  | 857 | 3547 | 57 | 3490 | 4347 | 4123 | 224 | 0 | 11 | 11 | 208 | 5 | 0 | 0 | 213