## Website English
Bangalore Electricity Supply Company Limited
Progress & pending Application details of Gangakalyana upto May-22
All Corporations | [12 empty] | Annexure-1
Sl No | Circle | Division | Opening balance of applications as on 1-4-2022 | Total applications received during the year 2022-23 (up to May-22) | Total applications lapsed during the year 2022-23 (up to May-22) | Total applications added during the year 2022-23 (up to May-22) | Total Valid Applications | Total borewells energised during the year 2022-23 (up to May-22) | Applications pending as at the end of the year 2022-23 (up to May-22) | Work Completed Service Not availed | Formalities Not observed | Applications pending at Corporation End | Work Under Progress | Work to be taken Up | Work order to be issued | Estimate to be prepared | Applications pending at BESCOM End
|  |  | 1 | 2 | 3 | 4=2-3 | 5=1+4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | North | Malleshwaram | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | Hebbala | 4 | 2 | 0 | 2 | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1
3 |  | Peenya | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | Jalahalli | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
| Total |  | 5 | 2 | 0 | 2 | 7 | 5 | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2
5 | East | Indiranagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Shivajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | Vidhanasoudha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Whitefield | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BMANZ |  |  | 5 | 2 | 0 | 2 | 7 | 5 | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2
9 | South | Jaynagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Kormangala | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  | H S R | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | West | Rajajinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
13 |  | Rajarajeshwari nagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | Kengeri | 2 | 1 | 0 | 1 | 3 | 0 | 3 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 2 | 3
| Total |  | 2 | 1 | 0 | 1 | 3 | 0 | 3 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 2 | 3
| BMASZ |  | 2 | 1 | 0 | 1 | 3 | 0 | 3 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 2 | 3
15 | Blore Rural | Nelmangala | 2 | 7 | 0 | 7 | 9 | 8 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
16 |  | Yelhanka | 1 | 4 | 1 | 3 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1
| Total |  | 3 | 11 | 1 | 10 | 13 | 11 | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2
17 | Ramnagara | Ramnagara | 3 | 2 | 0 | 2 | 5 | 0 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 5
18 |  | Magadi | 2 | 4 | 2 | 2 | 4 | 2 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 2
19 |  | Chandapura | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 |  | Kanakpura | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
| Total |  | 5 | 7 | 2 | 5 | 10 | 3 | 7 | 0 | 5 | 5 | 2 | 0 | 0 | 0 | 2 | 7
21 | Kolar | Kolar | 6 | 31 | 0 | 31 | 37 | 7 | 30 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 30 | 30
22 |  | K G F | 24 | 19 | 0 | 19 | 43 | 29 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 14 | 14
23 |  | C B Pura | 14 | 18 | 0 | 18 | 32 | 23 | 9 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 9 | 9
24 |  | Chintamani | 19 | 18 | 0 | 18 | 37 | 32 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 5
| Total |  | 63 | 86 | 0 | 86 | 149 | 91 | 58 | 0 | 0 | 0 | 58 | 0 | 0 | 0 | 58 | 58
25 | Davangere | Davangere | 49 | 98 | 3 | 95 | 144 | 54 | 90 | 0 | 0 | 0 | 26 | 64 | 0 | 0 | 90 | 90
26 |  | Harihara | 0 | 27 | 0 | 27 | 27 | 24 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 3
27 |  | Chitradurga | 57 | 175 | 2 | 173 | 230 | 141 | 89 | 0 | 0 | 0 | 89 | 0 | 0 | 0 | 89 | 89
28 |  | Hiriyur | 0 | 82 | 0 | 82 | 82 | 78 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 4
| Total |  | 106 | 382 | 5 | 377 | 483 | 297 | 186 | 0 | 0 | 0 | 122 | 64 | 0 | 0 | 186 | 186
29 | Tumkur | Tumkur | 17 | 54 | 1 | 53 | 70 | 35 | 35 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 35 | 35
30 |  | Kunigal | 1 | 3 | 0 | 3 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 |  | Tiptur | 22 | 14 | 1 | 13 | 35 | 26 | 9 | 0 | 1 | 1 | 8 | 0 | 0 | 0 | 8 | 9
32 |  | Madhugiri | 0 | 24 | 0 | 24 | 24 | 12 | 12 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12 | 12
| Total |  | 40 | 95 | 2 | 93 | 133 | 77 | 56 | 0 | 1 | 1 | 55 | 0 | 0 | 0 | 55 | 56
| BESCOM Total |  | 224 | 584 | 10 | 574 | 798 | 484 | 314 | 0 | 7 | 7 | 241 | 66 | 0 | 0 | 307 | 314
|  | Assistant General Manager(Op-3) | [5 empty] | 11: Deputy General Manager(Op-1)
|  | BESCOM | [5 empty] | 11: BESCOM
Chief General Manager(Op)
BESCOM
314

## Website kannada
¨ÉAUÀ¼ÀÆgÀÄ «zÀÄåvï ¸ÀgÀ§gÁdÄ PÀA¥À¤ ¤AiÀÄ«ÄvÀ
2021-22 £ÉÃ ¸Á°£À K¦æ¯ï-2021 gÀ CAvÀåPÉÌ UÀAUÁPÀ¯Áåt AiÉÆÃd£ÀAiÀÄr «zÀÄåvï ¸ÀA¥ÀPÀð PÀ°à¹zÀ ºÁUÀÆ ¨ÁQ EgÀÄªÀ CfðUÀ¼À «ªÀgÀUÀ¼ÀÄ
J¯Áè C©üªÀÈ¢Þ ¤UÀªÀÄUÀ¼ÀÄ ¸ÉÃj
PÀæªÀÄ ¸ÀASÉå | ªÀÈvÀÛ | «¨sÁUÀ | 31.03.2021 gÀ CAvÀåPÉÌ ¨ÁQ EgÀÄªÀ CfðUÀ¼À ¸ÀASÉå | 2021-22 £ÉÃ ¸Á°£À (K¦æ¯ï-21 gÀ CAvÀåPÉÌ) £ÉÆÃAzÀtÂUÉÆAqÀ CfðUÀ¼À ¸ÀASÉå | 2021-22 £ÉÃ ¸Á°£À (K¦æ¯ï-21 gÀ CAvÀåPÉÌ) gÀzÁÝzÀ CfðUÀ¼À ¸ÀASÉå | 2021-22 £ÉÃ ¸Á°£À (K¦æ¯ï-21 gÀ CAvÀåPÉÌ) £ÉÆÃAzÀtÂUÉÆAqÀ MlÄÖ CfðUÀ¼À ¸ÀASÉå | MlÄÖ CfðUÀ¼À ¸ÀASÉå | 2021-22 £ÉÃ ¸Á°£À (K¦æ¯ï-21 gÀ CAvÀåPÉÌ) «zÀÄåvï ¸ÀA¥ÀPÀð ¥ÀqÉzÀ MlÄÖ CfðUÀ¼À ¸ÀASÉå | 2021-22 £ÉÃ ¸Á°£À (K¦æ¯ï-21 gÀ CAvÀåPÉÌ) ¨ÁQ EgÀÄªÀ MlÄÖ CfðUÀ¼À ¸ÀASÉå | ¨É«PÀA ªÀw¬ÄAzÀ PÉ®¸À ªÀÄÄV¢zÀÄÝ DzÀgÉ C©üªÀÈ¢Þ ¤UÀªÀÄzÀªÀgÀÄ «zÀÄåvï ¸ÀA¥ÀPÀð vÉUÉzÀÄPÉÆ¼Àî¢gÀÄªÀ CfðUÀ¼À ¸ÀASÉå | C©üªÀÈ¢Þ ¤UÀªÀÄzÀªÀgÀÄ ¨É«PÀA£À ¤AiÀÄªÀÄUÀ¼À£ÀÄß ¥Á°¸À¢gÀÄªÀ CfðUÀ¼À ¸ÀASÉå | wAUÀ¼À CAvÀåPÉÌ C©üªÀÈ¢Þ ¤UÀªÀÄzÀªÀgÀªÀw¬ÄAzÀ ¨ÁQ EgÀÄªÀ MlÄÖ CfðUÀ¼À ¸ÀASÉå | PÁAiÀÄð ¥ÀæUÀwAiÀÄ°ègÀÄªÀ CfðUÀ¼À ¸ÀASÉå | PÁAiÀÄð PÉÊUÉwÛ PÉÆ¼Àî¨ÉÃPÁVgÀÄªÀ CfðUÀ¼À ¸ÀASÉå | PÁAiÀiÁðzÉÃ±À ¤ÃqÀ ¨ÉÃPÁVgÀÄªÀ CfðUÀ¼À ¸ÀASÉå | CAzÁdÄ ¥ÀnÖ vÀ0iÀiÁj ºÀAvÀzÀ°ègÀÄªÀ ¸ÀASÉå | wAUÀ¼À CAvÀåPÉÌ ¨É«PÀA ªÀw¬ÄAzÀ ¨ÁQ EgÀÄªÀ MlÄÖ CfðUÀ¼À ¸ÀASÉå
|  |  | 1 | 2 | 3 | 4=2-3 | 5=1+4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | GvÀÛgÀ | ªÀÄ¯ÉèÃ±ÀégÀA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | ºÉ¨Áâ¼À | 4 | 2 | 0 | 2 | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
3 |  | ¦Ãtå | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | eÁ®ºÀ°î | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| MlÄÖ |  | 5 | 2 | 0 | 2 | 7 | 5 | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2
5 | ¥ÀÆªÀð | EA¢gÁ£ÀUÀgÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | ²ªÁf£ÀUÀgÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | «zsÁ£À¸ËzsÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | ªÉÊmï¦üÃ¯ïØ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MlÄÖ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ¨ÉAUÀ¼ÀÆgÀÄ ªÀÄºÁ£ÀUÀgÀ GvÀÛgÀ PÉëÃvÀæ |  | 5 | 2 | 0 | 2 | 7 | 5 | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2
9 | zÀQët | dAiÀÄ£ÀUÀgÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | PÉÆÃgÀªÀÄAUÀ® | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  | ºÉZï.J¸ï.Dgï | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MlÄÖ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | ¥À²ÑªÀÄ | gÁeÁf£ÀUÀgÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  | gÁdgÁeÉÃ±Àéj £ÀUÀgÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | PÉAUÉÃj | 2 | 1 | 0 | 1 | 3 | 0 | 3 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 2
| MlÄÖ |  | 2 | 1 | 0 | 1 | 3 | 0 | 3 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 2
| ¨ÉAUÀ¼ÀÆgÀÄ ªÀÄºÁ£ÀUÀgÀ zÀQët PÉëÃvÀæ |  | 2 | 1 | 0 | 1 | 3 | 0 | 3 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 2
15 | ¨ÉAUÀ¼ÀÆgÀÄ UÁæ«ÄÃt | £É®ªÀÄAUÀ® | 2 | 7 | 0 | 7 | 9 | 8 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
16 |  | AiÀÄ®ºÀAPÀ | 1 | 4 | 1 | 3 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
| MlÄÖ |  | 3 | 11 | 1 | 10 | 13 | 11 | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2
17 | gÁªÀÄ£ÀUÀgÀ | gÁªÀÄ£ÀUÀgÀ | 3 | 2 | 0 | 2 | 5 | 0 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0
18 |  | ªÀiÁUÀr | 2 | 4 | 2 | 2 | 4 | 2 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
19 |  | ZÀAzÁ¥ÀÄgÀ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 |  | PÀ£ÀPÀ¥ÀÄgÀ | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MlÄÖ |  | 5 | 7 | 2 | 5 | 10 | 3 | 7 | 0 | 5 | 5 | 2 | 0 | 0 | 0 | 2
21 | PÉÆÃ¯ÁgÀ | PÀÉÆÃ¯ÁgÀ | 6 | 31 | 0 | 31 | 37 | 7 | 30 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 30
22 |  | PÉ.f.J¥sï | 24 | 19 | 0 | 19 | 43 | 29 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 14
23 |  | aPÀÌ§¼Áî¥ÀÄgÀ | 14 | 18 | 0 | 18 | 32 | 23 | 9 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 9
24 |  | aAvÁªÀÄtÂ | 19 | 18 | 0 | 18 | 37 | 32 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5
| MlÄÖ |  | 63 | 86 | 0 | 86 | 149 | 91 | 58 | 0 | 0 | 0 | 58 | 0 | 0 | 0 | 58
25 | zÀÁªÀtUÉgÉ | zÀÁªÀtUÉgÉ | 49 | 98 | 3 | 95 | 144 | 54 | 90 | 0 | 0 | 0 | 26 | 64 | 0 | 0 | 90
26 |  | ºÀjºÀgÀ | 0 | 27 | 0 | 27 | 27 | 24 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3
27 |  | avÀæzÀÄUÀð | 57 | 175 | 2 | 173 | 230 | 141 | 89 | 0 | 0 | 0 | 89 | 0 | 0 | 0 | 89
28 |  | »jAiÀÄÆgÀÄ | 0 | 82 | 0 | 82 | 82 | 78 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4
| MlÄÖ |  | 106 | 382 | 5 | 377 | 483 | 297 | 186 | 0 | 0 | 0 | 122 | 64 | 0 | 0 | 186
29 | vÀÄªÀÄPÀÆgÀÄ | vÀÄªÀÄPÀÆgÀÄ | 17 | 54 | 1 | 53 | 70 | 35 | 35 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 35
30 |  | PÀÄtÂUÀ¯ï | 1 | 3 | 0 | 3 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 |  | w¥ÀlÆgÀÄ | 22 | 14 | 1 | 13 | 35 | 26 | 9 | 0 | 1 | 1 | 8 | 0 | 0 | 0 | 8
32 |  | ªÀÄzsÀÄVj | 0 | 24 | 0 | 24 | 24 | 12 | 12 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12
| MlÄÖ |  | 40 | 95 | 2 | 93 | 133 | 77 | 56 | 0 | 1 | 1 | 55 | 0 | 0 | 0 | 55
| ¨É«PÀA MlÄÖ |  | 224 | 584 | 10 | 574 | 798 | 484 | 314 | 0 | 7 | 7 | 241 | 66 | 0 | 0 | 307