## April-2022
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Progress of energisation of Drinking Water Supply for FY 2022-23 ( up to April-2022)
| Sl No | Zone/Circle/Division | No. of Applications pending as at the 31.03.2022 | No. of Applications registered | No. of Applications lapsed | Total Applications | No. of Applications serviced | No. of Applications pending | Applications pending with Local Bodies |  |  | Applications pending with BESCOM end
PÀæ. .¸ÀA | [8 empty] | Works completed from BESCOM end, but sevice not avalied | Formalilities not observed | Total applications pending from local bodies | Estimate to be under progress | Work order to be issued | Work to be taken up | Work under Progress | Total applications pending from BESCOM end
| 1 | 2 | 3 | 4 | 5 | 6=3+4-5 | 7 | 8=6-7 | 9 | 10 | 11=9+10 | 12 | 13 | 14 | 15 | 16=12+13+14+15
| 1 | Koramangala | 3 | 2 | 0 | 5 | 4 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| 2 | HSR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 3 | Jayanagar | 0 | 14 | 0 | 14 | 11 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
4 | South |  | 3 | 16 | 0 | 19 | 15 | 4 | 1 | 3 | 4 | 0 | 0 | 0 | 0 | 0
8 | 4 | Rajajinagar | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 5 | RR Nagar | 0 | 5 | 0 | 5 | 3 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
10 | 6 | Kengeri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | West |  | 4 | 5 | 0 | 9 | 7 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
| BMASZ |  | 7 | 21 | 0 | 28 | 22 | 6 | 1 | 5 | 6 | 0 | 0 | 0 | 0 | 0
1 | 1 | Malleswaram | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 2 | Hebbal | 0 | 5 | 0 | 5 | 2 | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0
| 3 | Peenya | 0 | 11 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | Jalahalli | 6 | 8 | 6 | 8 | 4 | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
| North |  | 7 | 24 | 6 | 25 | 18 | 7 | 3 | 4 | 7 | 0 | 0 | 0 | 0 | 0
5 | 8 | Indiranagar | 5 | 9 | 3 | 11 | 4 | 7 | 2 | 5 | 7 | 0 | 0 | 0 | 0 | 0
| 9 | Whitefield | 2 | 3 | 0 | 5 | 2 | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0
| 10 | Shivajinagar | 0 | 65 | 0 | 65 | 0 | 65 | 65 | 0 | 65 | 0 | 0 | 0 | 0 | 0
6 | 11 | Vidhanasuoudha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | East |  | 7 | 77 | 3 | 81 | 6 | 75 | 70 | 5 | 75 | 0 | 0 | 0 | 0 | 0
| BMANZ |  | 14 | 101 | 9 | 106 | 24 | 82 | 73 | 9 | 82 | 0 | 0 | 0 | 0 | 0
13 | 15 | Nelamangala | 8 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8
14 | 16 | Hosakote | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Nelamangala |  | 8 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8
15 | 17 | Ramanagara | 1 | 26 | 0 | 27 | 0 | 27 | 0 | 27 | 27 | 0 | 0 | 0 | 0 | 0
| 18 | Magadi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 19 | Kanakapura | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
| 20 | Chandapura | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ramanagara |  | 2 | 26 | 0 | 28 | 0 | 28 | 0 | 27 | 27 | 0 | 0 | 1 | 0 | 1
16 | 21 | Kolar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 22 | KGF | 8 | 1 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 1 | 8 | 9
18 | 23 | Chikkaballapur | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
19 | 24 | Chintamani | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Kolar |  | 8 | 2 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 1 | 9 | 10
| BRAZ |  | 18 | 28 | 0 | 46 | 0 | 46 | 0 | 27 | 27 | 0 | 0 | 2 | 17 | 19
20 | 25 | Davangere | 1 | 0 | 0 |  | 1 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 26 | Harihara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 27 | Chitradurga | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
23 | 28 | Hiriyuru | 0 | 6 | 0 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| Davanagere |  | 1 | 8 | 0 | 9 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
24 | 29 | Tumkur | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 30 | Kunigal | 1 | 5 | 0 | 6 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
25 | 31 | Tipur | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 32 | Madhugiri | 5 | 3 | 0 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
| Tumkur |  | 7 | 9 | 0 | 16 | 7 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9
| CTAZ |  | 8 | 17 | 0 | 25 | 12 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13
| BESCOM |  | 47 | 167 | 9 | 205 | 58 | 147 | 74 | 41 | 115 | 0 | 0 | 2 | 30 | 32

## may-2022
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Progress of energisation of Drinking Water Supply for FY 2022-23 ( up to May-2022)
| Sl No | Zone/Circle/Division | No. of Applications pending as at the 31.03.2022 | No. of Applications registered | No. of Applications lapsed | Total Applications | No. of Applications serviced | No. of Applications pending | Applications pending with Local Bodies |  |  | Applications pending with BESCOM end
PÀæ. .¸ÀA | [8 empty] | Works completed from BESCOM end, but sevice not avalied | Formalilities not observed | Total applications pending from local bodies | Estimate to be under progress | Work order to be issued | Work to be taken up | Work under Progress | Total applications pending from BESCOM end
| 1 | 2 | 3 | 4 | 5 | 6=3+4-5 | 7 | 8=6-7 | 9 | 10 | 11=9+10 | 12 | 13 | 14 | 15 | 16=12+13+14+15
| 1 | Koramangala | 3 | 2 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | HSR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 3 | Jayanagar | 0 | 15 | 0 | 15 | 12 | 3 | 2 | 1 | 3 | 0 | 0 | 0 | 0 | 0
4 | South |  | 3 | 17 | 0 | 20 | 17 | 3 | 2 | 1 | 3 | 0 | 0 | 0 | 0 | 0
8 | 4 | Rajajinagar | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 5 | RR Nagar | 0 | 7 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 6 | Kengeri | 0 | 13 | 0 | 13 | 0 | 13 | 5 | 8 | 13 | 0 | 0 | 0 | 0 | 0
11 | West |  | 4 | 20 | 0 | 24 | 11 | 13 | 5 | 8 | 13 | 0 | 0 | 0 | 0 | 0
| BMASZ |  | 7 | 37 | 0 | 44 | 28 | 16 | 7 | 9 | 16 | 0 | 0 | 0 | 0 | 0
1 | 1 | Malleswaram | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 2 | Hebbal | 0 | 11 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | Peenya | 0 | 11 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | Jalahalli | 6 | 19 | 6 | 19 | 15 | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0
| North |  | 7 | 41 | 6 | 42 | 38 | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0
5 | 8 | Indiranagar | 5 | 11 | 5 | 11 | 9 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0
| 9 | Whitefield | 2 | 3 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | Shivajinagar | 0 | 65 | 0 | 65 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 11 | Vidhanasuoudha | 0 | 7 | 0 | 7 | 2 | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0
7 | East |  | 7 | 86 | 5 | 88 | 81 | 7 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0
| BMANZ |  | 14 | 127 | 11 | 130 | 119 | 11 | 11 | 0 | 11 | 0 | 0 | 0 | 0 | 0
13 | 15 | Nelamangala | 8 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 16 | Hosakote | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Nelamangala |  | 8 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 17 | Ramanagara | 1 | 26 | 0 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 18 | Magadi | 0 | 20 | 0 | 20 | 12 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8
| 19 | Kanakapura | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
| 20 | Chandapura | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
| Ramanagara |  | 2 | 49 | 0 | 51 | 39 | 12 | 0 | 0 | 0 | 0 | 0 | 1 | 11 | 12
16 | 21 | Kolar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 22 | KGF | 8 | 4 | 0 | 12 | 3 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9
18 | 23 | Chikkaballapur | 0 | 16 | 0 | 16 | 5 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 11
19 | 24 | Chintamani | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Kolar |  | 8 | 20 | 0 | 28 | 8 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20
| BRAZ |  | 18 | 69 | 0 | 87 | 55 | 32 | 0 | 0 | 0 | 0 | 0 | 1 | 31 | 32
20 | 25 | Davangere | 1 | 0 | 0 |  | 1 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 26 | Harihara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 27 | Chitradurga | 0 | 6 | 0 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
23 | 28 | Hiriyuru | 0 | 9 | 0 | 9 | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Davanagere |  | 1 | 15 | 0 | 16 | 13 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
24 | 29 | Tumkur | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 30 | Kunigal | 1 | 5 | 0 | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
25 | 31 | Tipur | 1 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 32 | Madhugiri | 5 | 6 | 0 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
| Tumkur |  | 7 | 13 | 0 | 20 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| CTAZ |  | 8 | 28 | 0 | 36 | 28 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8
| BESCOM |  | 47 | 261 | 11 | 297 | 230 | 67 | 18 | 9 | 27 | 0 | 0 | 1 | 39 | 40

## June-2022
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Progress of Energisation of Drinking Water Supply for FY 2022-23 ( up to June-2022)
| Sl No | Zone/Circle/Division | No. of Applications pending as at the 31.03.2022 | No. of Applications registered | No. of Applications lapsed | Total Applications | No. of Applications serviced | No. of Applications pending | Applications pending with Local Bodies |  |  | Applications pending with BESCOM end
PÀæ. .¸ÀA | [8 empty] | Works completed from BESCOM end, but sevice not avalied | Formalilities not observed | Total applications pending from local bodies | Estimate to be under progress | Work order to be issued | Work to be taken up | Work under Progress | Total applications pending from BESCOM end
| 1 | 2 | 3 | 4 | 5 | 6=3+4-5 | 7 | 8=6-7 | 9 | 10 | 11=9+10 | 12 | 13 | 14 | 15 | 16=12+13+14+15
| 1 | Koramangala | 3 | 2 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | HSR | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 3 | Jayanagar | 0 | 17 | 2 | 15 | 14 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
4 | South |  | 3 | 27 | 2 | 28 | 27 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
8 | 4 | Rajajinagar | 4 | 1 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 5 | RR Nagar | 0 | 9 | 0 | 9 | 8 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
10 | 6 | Kengeri | 0 | 26 | 0 | 26 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | West |  | 4 | 36 | 0 | 40 | 39 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| BMASZ |  | 7 | 63 | 2 | 68 | 66 | 2 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0
1 | 1 | Malleswaram | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 2 | Hebbal | 0 | 31 | 0 | 31 | 22 | 9 | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 0
| 3 | Peenya | 0 | 19 | 1 | 18 | 17 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| 4 | Jalahalli | 6 | 19 | 6 | 19 | 15 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| North |  | 7 | 69 | 7 | 69 | 55 | 14 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 0
5 | 8 | Indiranagar | 5 | 11 | 5 | 11 | 9 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0
| 9 | Whitefield | 2 | 3 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | Shivajinagar | 0 | 101 | 0 | 101 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 11 | Vidhanasuoudha | 0 | 7 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | East |  | 7 | 122 | 5 | 124 | 122 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0
| BMANZ |  | 14 | 191 | 12 | 193 | 177 | 16 | 2 | 14 | 16 | 0 | 0 | 0 | 0 | 0
13 | 15 | Nelamangala | 8 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 16 | Hosakote | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Nelamangala |  | 8 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 17 | Ramanagara | 1 | 28 | 0 | 29 | 27 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
| 18 | Magadi | 0 | 20 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 19 | Kanakapura | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 20 | Chandapura | 0 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ramanagara |  | 2 | 51 | 0 | 53 | 51 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
16 | 21 | Kolar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 22 | KGF | 8 | 7 | 1 | 14 | 13 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
18 | 23 | Chikkaballapur | 0 | 16 | 0 | 16 | 15 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
19 | 24 | Chintamani | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Kolar |  | 8 | 24 | 1 | 31 | 29 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| BRAZ |  | 18 | 75 | 1 | 92 | 88 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 2 | 2
20 | 25 | Davangere | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 26 | Harihara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 27 | Chitradurga | 0 | 8 | 0 | 8 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
23 | 28 | Hiriyuru | 0 | 11 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Davanagere |  | 1 | 19 | 0 | 20 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
24 | 29 | Tumkur | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 30 | Kunigal | 1 | 5 | 0 | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
25 | 31 | Tipur | 1 | 5 | 0 | 6 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
26 | 32 | Madhugiri | 5 | 8 | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tumkur |  | 7 | 19 | 0 | 26 | 21 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| CTAZ |  | 8 | 38 | 0 | 46 | 40 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6
| BESCOM |  | 47 | 367 | 15 | 399 | 371 | 28 | 3 | 17 | 20 | 0 | 0 | 0 | 8 | 8

## July-2022
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Progress of Energisation of Drinking Water Supply for FY 2022-23 ( up to July-2022)
| Sl No | Zone/Circle/Division | No. of Applications pending as at the 31.03.2022 | No. of Applications registered | No. of Applications lapsed | Total Applications | No. of Applications serviced | No. of Applications pending | Applications pending with Local Bodies |  |  | Applications pending with BESCOM end
PÀæ. .¸ÀA | [8 empty] | Works completed from BESCOM end, but sevice not avalied | Formalilities not observed | Total applications pending from local bodies | Estimate to be under progress | Work order to be issued | Work to be taken up | Work under Progress | Total applications pending from BESCOM end
| 1 | 2 | 3 | 4 | 5 | 6=3+4-5 | 7 | 8=6-7 | 9 | 10 | 11=9+10 | 12 | 13 | 14 | 15 | 16=12+13+14+15
| 1 | Koramangala | 3 | 2 | 0 | 2 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | HSR | 0 | 8 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 3 | Jayanagar | 0 | 20 | 3 | 17 | 17 | 14 | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 0
4 | South |  | 3 | 30 | 3 | 27 | 30 | 27 | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 0
8 | 4 | Rajajinagar | 4 | 2 | 0 | 2 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 5 | RR Nagar | 0 | 9 | 0 | 9 | 9 | 8 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0
10 | 6 | Kengeri | 0 | 53 | 0 | 53 | 53 | 26 | 27 | 0 | 22 | 22 | 0 | 5 | 0 | 0
11 | West |  | 4 | 64 | 0 | 64 | 68 | 40 | 28 | 0 | 23 | 23 | 0 | 5 | 0 | 0
| BMASZ |  | 7 | 94 | 3 | 91 | 98 | 67 | 31 | 3 | 23 | 26 | 0 | 5 | 0 | 0
1 | 1 | Malleswaram | 1 | 1 | 0 | 1 | 2 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0
2 | 2 | Hebbal | 0 | 41 | 0 | 41 | 41 | 39 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0
| 3 | Peenya | 0 | 20 | 1 | 19 | 19 | 17 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0
| 4 | Jalahalli | 6 | 19 | 6 | 13 | 19 | 15 | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0
| North |  | 7 | 81 | 7 | 74 | 81 | 72 | 9 | 0 | 9 | 9 | 0 | 0 | 0 | 0
5 | 8 | Indiranagar | 5 | 11 | 5 | 6 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | Whitefield | 2 | 12 | 0 | 12 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | Shivajinagar | 0 | 101 | 0 | 101 | 101 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 11 | Vidhanasuoudha | 0 | 8 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | East |  | 7 | 132 | 5 | 127 | 134 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BMANZ |  | 14 | 213 | 12 | 201 | 215 | 206 | 9 | 0 | 9 | 9 | 0 | 0 | 0 | 0
13 | 15 | Nelamangala | 8 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 16 | Hosakote | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Nelamangala |  | 8 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 17 | Ramanagara | 1 | 29 | 0 | 29 | 30 | 27 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0
| 18 | Magadi | 0 | 22 | 0 | 22 | 22 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 19 | Kanakapura | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 20 | Chandapura | 0 | 3 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ramanagara |  | 2 | 54 | 0 | 54 | 56 | 53 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0
16 | 21 | Kolar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 22 | KGF | 8 | 7 | 1 | 6 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 23 | Chikkaballapur | 0 | 20 | 0 | 20 | 20 | 18 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2
19 | 24 | Chintamani | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Kolar |  | 8 | 28 | 1 | 27 | 35 | 33 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| BRAZ |  | 18 | 82 | 1 | 81 | 99 | 94 | 5 | 0 | 0 | 0 | 0 | 0 | 3 | 2
20 | 25 | Davangere | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 26 | Harihara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 27 | Chitradurga | 0 | 10 | 0 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 28 | Hiriyuru | 0 | 14 | 0 | 14 | 14 | 13 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| Davanagere |  | 1 | 24 | 0 | 24 | 25 | 24 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
24 | 29 | Tumkur | 0 | 2 | 0 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 30 | Kunigal | 1 | 6 | 0 | 6 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
25 | 31 | Tipur | 1 | 5 | 0 | 5 | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3
26 | 32 | Madhugiri | 5 | 10 | 0 | 10 | 15 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| Tumkur |  | 7 | 23 | 0 | 23 | 30 | 23 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7
| CTAZ |  | 8 | 47 | 0 | 47 | 55 | 47 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8
| BESCOM |  | 47 | 436 | 16 | 420 | 467 | 414 | 53 | 3 | 32 | 35 | 0 | 5 | 3 | 10

## August-2022
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Progress of Energisation of Drinking Water Supply for FY 2022-23 ( up to August-2022)
| Sl No | Zone/Circle/Division | No. of Applications pending as at the 31.03.2022 | No. of Applications registered | No. of Applications lapsed | Total Applications | No. of Applications serviced | No. of Applications pending | Applications pending with Local Bodies |  |  | Applications pending with BESCOM end
PÀæ. .¸ÀA | [8 empty] | Works completed from BESCOM end, but sevice not avalied | Formalilities not observed | Total applications pending from local bodies | Estimate to be under progress | Work order to be issued | Work to be taken up | Work under Progress | Total applications pending from BESCOM end
| 1 | 2 | 3 | 4 | 5 | 6=3+4-5 | 7 | 8=6-7 | 9 | 10 | 11=9+10 | 12 | 13 | 14 | 15 | 16=12+13+14+15
| 1 | Koramangala | 3 | 7 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | HSR | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 3 | Jayanagar | 0 | 23 | 3 | 20 | 15 | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0
4 | South |  | 3 | 38 | 3 | 38 | 33 | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0
8 | 4 | Rajajinagar | 4 | 2 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 5 | RR Nagar | 0 | 9 | 0 | 9 | 8 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
10 | 6 | Kengeri | 0 | 57 | 0 | 57 | 26 | 31 | 26 | 0 | 26 | 0 | 0 | 0 | 5 | 5
11 | West |  | 4 | 68 | 0 | 72 | 40 | 32 | 26 | 1 | 27 | 0 | 0 | 0 | 5 | 5
| BMASZ |  | 7 | 106 | 3 | 110 | 73 | 37 | 31 | 1 | 32 | 0 | 0 | 0 | 5 | 5
1 | 1 | Malleswaram | 1 | 2 | 0 | 3 | 2 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
2 | 2 | Hebbal | 0 | 41 | 0 | 41 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | Peenya | 0 | 20 | 3 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | Jalahalli | 6 | 19 | 6 | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| North |  | 7 | 82 | 9 | 80 | 79 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
5 | 8 | Indiranagar | 5 | 12 | 5 | 12 | 11 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| 9 | Whitefield | 2 | 13 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | Shivajinagar | 0 | 101 | 0 | 101 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 11 | Vidhanasuoudha | 0 | 9 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | East |  | 7 | 135 | 5 | 137 | 136 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| BMANZ |  | 14 | 217 | 14 | 217 | 215 | 2 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0
13 | 15 | Nelamangala | 8 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 16 | Hosakote | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Nelamangala |  | 8 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 17 | Ramanagara | 1 | 47 | 0 | 48 | 47 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
| 18 | Magadi | 0 | 23 | 0 | 23 | 22 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
| 19 | Kanakapura | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 20 | Chandapura | 0 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ramanagara |  | 2 | 73 | 0 | 75 | 73 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2
16 | 21 | Kolar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 22 | KGF | 8 | 7 | 1 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 23 | Chikkaballapur | 0 | 22 | 0 | 22 | 19 | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 3
19 | 24 | Chintamani | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Kolar |  | 8 | 30 | 1 | 37 | 34 | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 3
| BRAZ |  | 18 | 103 | 1 | 120 | 115 | 5 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 5
20 | 25 | Davangere | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 26 | Harihara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 27 | Chitradurga | 0 | 10 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 28 | Hiriyuru | 0 | 19 | 0 | 19 | 18 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Davanagere |  | 1 | 29 | 0 | 30 | 29 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1
24 | 29 | Tumkur | 0 | 2 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 30 | Kunigal | 1 | 7 | 0 | 8 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
25 | 31 | Tipur | 1 | 6 | 0 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
26 | 32 | Madhugiri | 5 | 12 | 0 | 17 | 15 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| Tumkur |  | 7 | 27 | 0 | 34 | 29 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| CTAZ |  | 8 | 56 | 0 | 64 | 58 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6
| BESCOM |  | 47 | 482 | 18 | 511 | 461 | 50 | 32 | 2 | 34 | 0 | 0 | 4 | 12 | 16

## Sep-2022
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Progress of Energisation of Drinking Water Supply for FY 2022-23 ( up to September-2022)
| Sl No | Zone/Circle/Division | No. of Applications pending as at the 31.03.2022 | No. of Applications registered | No. of Applications lapsed | Total Applications | No. of Applications serviced | No. of Applications pending | Applications pending with Local Bodies |  |  | Applications pending with BESCOM end
PÀæ. .¸ÀA | [8 empty] | Works completed from BESCOM end, but sevice not avalied | Formalilities not observed | Total applications pending from local bodies | Estimate to be under progress | Work order to be issued | Work to be taken up | Work under Progress | Total applications pending from BESCOM end
| 1 | 2 | 3 | 4 | 5 | 6=3+4-5 | 7 | 8=6-7 | 9 | 10 | 11=9+10 | 12 | 13 | 14 | 15 | 16=12+13+14+15
| 1 | Koramangala | 3 | 7 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | HSR | 0 | 13 | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 3 | Jayanagar | 0 | 34 | 3 | 31 | 18 | 13 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0
4 | South |  | 3 | 54 | 3 | 54 | 41 | 13 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0
8 | 4 | Rajajinagar | 4 | 5 | 0 | 9 | 7 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0
9 | 5 | RR Nagar | 0 | 9 | 0 | 9 | 8 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
10 | 6 | Kengeri | 0 | 59 | 0 | 59 | 52 | 7 | 0 | 2 | 2 | 0 | 0 | 0 | 5 | 5
11 | West |  | 4 | 73 | 0 | 77 | 67 | 10 | 2 | 3 | 5 | 0 | 0 | 0 | 5 | 5
| BMASZ |  | 7 | 127 | 3 | 131 | 108 | 23 | 15 | 3 | 18 | 0 | 0 | 0 | 5 | 5
1 | 1 | Malleswaram | 1 | 2 | 0 | 3 | 2 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
2 | 2 | Hebbal | 0 | 43 | 0 | 43 | 41 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
| 3 | Peenya | 0 | 20 | 3 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | Jalahalli | 6 | 21 | 6 | 21 | 19 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
| North |  | 7 | 86 | 9 | 84 | 79 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0
5 | 8 | Indiranagar | 5 | 12 | 5 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | Whitefield | 2 | 13 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | Shivajinagar | 0 | 101 | 0 | 101 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 11 | Vidhanasuoudha | 0 | 11 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | East |  | 7 | 137 | 5 | 139 | 139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BMANZ |  | 14 | 223 | 14 | 223 | 218 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0
13 | 15 | Nelamangala | 8 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 16 | Hosakote | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Nelamangala |  | 8 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 17 | Ramanagara | 1 | 47 | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 18 | Magadi | 0 | 23 | 0 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 19 | Kanakapura | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 20 | Chandapura | 0 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ramanagara |  | 2 | 73 | 0 | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 21 | Kolar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 22 | KGF | 8 | 7 | 1 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 23 | Chikkaballapur | 0 | 25 | 0 | 25 | 19 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6
19 | 24 | Chintamani | 0 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Kolar |  | 8 | 35 | 1 | 42 | 36 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6
| BRAZ |  | 18 | 108 | 1 | 125 | 119 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6
20 | 25 | Davangere | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 26 | Harihara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 27 | Chitradurga | 0 | 18 | 0 | 18 | 11 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7
23 | 28 | Hiriyuru | 0 | 27 | 0 | 27 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 1 | 8 | 9
| Davanagere |  | 1 | 45 | 0 | 46 | 30 | 16 | 0 | 0 | 0 | 0 | 0 | 1 | 15 | 16
24 | 29 | Tumkur | 0 | 2 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 30 | Kunigal | 1 | 7 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 31 | Tipur | 1 | 7 | 0 | 8 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
26 | 32 | Madhugiri | 5 | 14 | 1 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tumkur |  | 7 | 30 | 1 | 36 | 34 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| CTAZ |  | 8 | 75 | 1 | 82 | 64 | 18 | 0 | 0 | 0 | 0 | 0 | 1 | 17 | 18
| BESCOM |  | 47 | 533 | 19 | 561 | 509 | 52 | 15 | 8 | 23 | 0 | 0 | 1 | 28 | 29

## Oct-2022
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Progress of Energisation of Drinking Water Supply for FY 2022-23 ( up to October-2022)
| Sl No | Zone/Circle/Division | No. of Applications pending as at the 31.03.2022 | No. of Applications registered | No. of Applications lapsed | Total Applications | No. of Applications serviced | No. of Applications pending | Applications pending with Local Bodies |  |  | Applications pending with BESCOM end
PÀæ. .¸ÀA | [8 empty] | Works completed from BESCOM end, but sevice not avalied | Formalilities not observed | Total applications pending from local bodies | Estimate to be under progress | Work order to be issued | Work to be taken up | Work under Progress | Total applications pending from BESCOM end
| 1 | 2 | 3 | 4 | 5 | 6=3+4-5 | 7 | 8=6-7 | 9 | 10 | 11=9+10 | 12 | 13 | 14 | 15 | 16=12+13+14+15
| 1 | Koramangala | 3 | 8 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | HSR | 0 | 13 | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 3 | Jayanagar | 0 | 34 | 3 | 31 | 18 | 13 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0
4 | South |  | 3 | 55 | 3 | 55 | 42 | 13 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0
8 | 4 | Rajajinagar | 4 | 13 | 0 | 17 | 11 | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0
9 | 5 | RR Nagar | 0 | 26 | 1 | 25 | 12 | 13 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0
10 | 6 | Kengeri | 0 | 70 | 0 | 70 | 65 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
11 | West |  | 4 | 109 | 1 | 112 | 88 | 24 | 19 | 0 | 19 | 0 | 0 | 0 | 5 | 5
| BMASZ |  | 7 | 164 | 4 | 167 | 130 | 37 | 32 | 0 | 32 | 0 | 0 | 0 | 5 | 5
1 | 1 | Malleswaram | 1 | 8 | 0 | 9 | 3 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
2 | 2 | Hebbal | 0 | 43 | 0 | 43 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | Peenya | 0 | 20 | 3 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | Jalahalli | 6 | 21 | 6 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| North |  | 7 | 92 | 9 | 90 | 84 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
5 | 8 | Indiranagar | 5 | 13 | 5 | 13 | 12 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| 9 | Whitefield | 2 | 13 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | Shivajinagar | 0 | 101 | 0 | 101 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 11 | Vidhanasuoudha | 0 | 11 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | East |  | 7 | 138 | 5 | 140 | 139 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| BMANZ |  | 14 | 230 | 14 | 230 | 223 | 7 | 1 | 6 | 7 | 0 | 0 | 0 | 0 | 0
13 | 15 | Nelamangala | 8 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 16 | Hosakote | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8
| Nelamangala |  | 8 | 8 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8
15 | 17 | Ramanagara | 1 | 63 | 0 | 64 | 48 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0
| 18 | Magadi | 0 | 23 | 0 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 19 | Kanakapura | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 20 | Chandapura | 0 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ramanagara |  | 2 | 89 | 0 | 91 | 75 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0
16 | 21 | Kolar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 22 | KGF | 8 | 7 | 1 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 23 | Chikkaballapur | 0 | 25 | 1 | 24 | 21 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
19 | 24 | Chintamani | 0 | 8 | 0 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
| Kolar |  | 8 | 40 | 2 | 46 | 40 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6
| BRAZ |  | 18 | 137 | 2 | 153 | 123 | 30 | 0 | 16 | 16 | 0 | 0 | 0 | 14 | 14
20 | 25 | Davangere | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 26 | Harihara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 27 | Chitradurga | 0 | 21 | 0 | 21 | 20 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
23 | 28 | Hiriyuru | 0 | 27 | 0 | 27 | 25 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| Davanagere |  | 1 | 48 | 0 | 49 | 46 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
24 | 29 | Tumkur | 0 | 2 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 30 | Kunigal | 1 | 8 | 0 | 9 | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
25 | 31 | Tipur | 1 | 10 | 1 | 10 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
26 | 32 | Madhugiri | 5 | 15 | 1 | 19 | 18 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Tumkur |  | 7 | 35 | 2 | 40 | 35 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| CTAZ |  | 8 | 83 | 2 | 89 | 81 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8
| BESCOM |  | 47 | 614 | 22 | 639 | 557 | 82 | 33 | 22 | 55 | 0 | 0 | 0 | 27 | 27

## Nov-2022
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Progress of Energisation of Drinking Water Supply for FY 2022-23 ( up to November-2022)
| Sl No | Zone/Circle/Division | No. of Applications pending as at the 31.03.2022 | No. of Applications registered | No. of Applications lapsed | Total Applications | No. of Applications serviced | No. of Applications pending | Applications pending with Local Bodies |  |  | Applications pending with BESCOM end
PÀæ. .¸ÀA | [8 empty] | Works completed from BESCOM end, but sevice not avalied | Formalilities not observed | Total applications pending from local bodies | Estimate to be under progress | Work order to be issued | Work to be taken up | Work under Progress | Total applications pending from BESCOM end
| 1 | 2 | 3 | 4 | 5 | 6=3+4-5 | 7 | 8=6-7 | 9 | 10 | 11=9+10 | 12 | 13 | 14 | 15 | 16=12+13+14+15
| 1 | Koramangala | 3 | 8 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | HSR | 0 | 13 | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 3 | Jayanagar | 0 | 42 | 5 | 37 | 29 | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0
4 | South |  | 3 | 63 | 5 | 61 | 53 | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0
8 | 4 | Rajajinagar | 4 | 14 | 0 | 18 | 17 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
9 | 5 | RR Nagar | 0 | 26 | 1 | 25 | 12 | 13 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0
10 | 6 | Kengeri | 0 | 73 | 0 | 73 | 65 | 8 | 3 | 0 | 3 | 0 | 0 | 0 | 5 | 5
11 | West |  | 4 | 113 | 1 | 116 | 94 | 22 | 17 | 0 | 17 | 0 | 0 | 0 | 5 | 5
| BMASZ |  | 7 | 176 | 6 | 177 | 147 | 30 | 25 | 0 | 25 | 0 | 0 | 0 | 5 | 5
1 | 1 | Malleswaram | 1 | 8 | 0 | 9 | 3 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
2 | 2 | Hebbal | 0 | 49 | 0 | 49 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | Peenya | 0 | 23 | 3 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | Jalahalli | 6 | 21 | 6 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| North |  | 7 | 101 | 9 | 99 | 93 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
5 | 8 | Indiranagar | 5 | 16 | 5 | 16 | 15 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| 9 | Whitefield | 2 | 19 | 0 | 21 | 16 | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0
| 10 | Shivajinagar | 0 | 101 | 0 | 101 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 11 | Vidhanasuoudha | 0 | 11 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | East |  | 7 | 147 | 5 | 149 | 143 | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0
| BMANZ |  | 14 | 248 | 14 | 248 | 236 | 12 | 6 | 6 | 12 | 0 | 0 | 0 | 0 | 0
13 | 15 | Nelamangala | 8 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 16 | Hosakote | 0 | 16 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8
| Nelamangala |  | 8 | 16 | 0 | 24 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8
15 | 17 | Ramanagara | 1 | 63 | 16 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 18 | Magadi | 0 | 23 | 0 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 19 | Kanakapura | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 20 | Chandapura | 0 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ramanagara |  | 2 | 89 | 16 | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 21 | Kolar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 22 | KGF | 8 | 7 | 1 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 23 | Chikkaballapur | 0 | 25 | 1 | 24 | 22 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
19 | 24 | Chintamani | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Kolar |  | 8 | 40 | 2 | 46 | 44 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| BRAZ |  | 18 | 145 | 18 | 145 | 135 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10
20 | 25 | Davangere | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 26 | Harihara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 27 | Chitradurga | 0 | 25 | 0 | 25 | 23 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
23 | 28 | Hiriyuru | 0 | 27 | 0 | 27 | 26 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Davanagere |  | 1 | 52 | 0 | 53 | 50 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
24 | 29 | Tumkur | 0 | 2 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 30 | Kunigal | 1 | 8 | 0 | 9 | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
25 | 31 | Tipur | 1 | 10 | 1 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 32 | Madhugiri | 5 | 15 | 1 | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tumkur |  | 7 | 35 | 2 | 40 | 38 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| CTAZ |  | 8 | 87 | 2 | 93 | 88 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| BESCOM |  | 47 | 656 | 40 | 663 | 606 | 57 | 31 | 6 | 55 | 0 | 0 | 0 | 20 | 20

## Dec-2022
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Progress of Energisation of Drinking Water Supply for FY 2022-23 ( up to December-2022)
| Sl No | Zone/Circle/Division | No. of Applications pending as at the 31.03.2022 | No. of Applications registered | No. of Applications lapsed | Total Applications | No. of Applications serviced | No. of Applications pending | Applications pending with Local Bodies |  |  | Applications pending with BESCOM end
PÀæ. .¸ÀA | [8 empty] | Works completed from BESCOM end, but sevice not avalied | Formalilities not observed | Total applications pending from local bodies | Estimate to be under progress | Work order to be issued | Work to be taken up | Work under Progress | Total applications pending from BESCOM end
| 1 | 2 | 3 | 4 | 5 | 6=3+4-5 | 7 | 8=6-7 | 9 | 10 | 11=9+10 | 12 | 13 | 14 | 15 | 16=12+13+14+15
| 1 | Koramangala | 3 | 8 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | HSR | 0 | 14 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 3 | Jayanagar | 0 | 43 | 5 | 38 | 35 | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0
4 | South |  | 3 | 65 | 5 | 63 | 60 | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0
8 | 4 | Rajajinagar | 4 | 31 | 0 | 35 | 25 | 10 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0
9 | 5 | RR Nagar | 0 | 29 | 1 | 28 | 26 | 2 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0
10 | 6 | Kengeri | 0 | 75 | 2 | 73 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | West |  | 4 | 135 | 3 | 136 | 124 | 12 | 11 | 1 | 12 | 0 | 0 | 0 | 0 | 0
| BMASZ |  | 7 | 200 | 8 | 199 | 184 | 15 | 14 | 1 | 15 | 0 | 0 | 0 | 0 | 0
1 | 1 | Malleswaram | 1 | 9 | 3 | 7 | 4 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2 | 2 | Hebbal | 0 | 70 | 0 | 70 | 53 | 17 | 0 | 17 | 17 | 0 | 0 | 0 | 0 | 0
| 3 | Peenya | 0 | 24 | 3 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | Jalahalli | 6 | 21 | 6 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| North |  | 7 | 124 | 12 | 119 | 99 | 20 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0
5 | 8 | Indiranagar | 5 | 21 | 5 | 21 | 17 | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0
| 9 | Whitefield | 2 | 19 | 0 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | Shivajinagar | 0 | 108 | 0 | 108 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 11 | Vidhanasuoudha | 0 | 14 | 0 | 14 | 13 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
7 | East |  | 7 | 162 | 5 | 164 | 159 | 5 | 4 | 1 | 5 | 0 | 0 | 0 | 0 | 0
| BMANZ |  | 14 | 286 | 17 | 283 | 258 | 25 | 4 | 21 | 25 | 0 | 0 | 0 | 0 | 0
13 | 15 | Nelamangala | 8 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 16 | Hosakote | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Nelamangala |  | 8 | 16 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 17 | Ramanagara | 1 | 63 | 16 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 18 | Magadi | 0 | 23 | 0 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 19 | Kanakapura | 1 | 2 | 0 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2
| 20 | Chandapura | 0 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ramanagara |  | 2 | 91 | 16 | 77 | 75 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2
16 | 21 | Kolar | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
17 | 22 | KGF | 8 | 7 | 1 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 23 | Chikkaballapur | 0 | 25 | 1 | 24 | 23 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
19 | 24 | Chintamani | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Kolar |  | 8 | 41 | 2 | 47 | 45 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| BRAZ |  | 18 | 148 | 18 | 148 | 144 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4
20 | 25 | Davangere | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 26 | Harihara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 27 | Chitradurga | 0 | 33 | 0 | 33 | 30 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3
23 | 28 | Hiriyuru | 0 | 30 | 0 | 30 | 27 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3
| Davanagere |  | 1 | 63 | 0 | 64 | 58 | 6 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 6
24 | 29 | Tumkur | 0 | 3 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 30 | Kunigal | 1 | 9 | 0 | 10 | 9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
25 | 31 | Tipur | 1 | 10 | 1 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 32 | Madhugiri | 5 | 17 | 1 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tumkur |  | 7 | 39 | 2 | 44 | 42 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| CTAZ |  | 8 | 102 | 2 | 108 | 100 | 8 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 8
| BESCOM |  | 47 | 736 | 45 | 738 | 686 | 52 | 18 | 22 | 40 | 0 | 0 | 6 | 6 | 12

## Jan-2023
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Progress of Energisation of Drinking Water Supply for FY 2022-23 ( up to Jan-2023)
| Sl No | Zone/Circle/Division | No. of Applications pending as at the 31.03.2022 | No. of Applications registered | No. of Applications lapsed | Total Applications | No. of Applications serviced | No. of Applications pending | Applications pending with Local Bodies |  |  | Applications pending with BESCOM end
PÀæ. .¸ÀA | [8 empty] | Works completed from BESCOM end, but sevice not avalied | Formalilities not observed | Total applications pending from local bodies | Estimate to be under progress | Work order to be issued | Work to be taken up | Work under Progress | Total applications pending from BESCOM end
| 1 | 2 | 3 | 4 | 5 | 6=3+4-5 | 7 | 8=6-7 | 9 | 10 | 11=9+10 | 12 | 13 | 14 | 15 | 16=12+13+14+15
| 1 | Koramangala | 3 | 21 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | HSR | 0 | 14 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 3 | Jayanagar | 0 | 61 | 6 | 55 | 38 | 17 | 17 | 0 | 17 | 0 | 0 | 0 | 0 | 0
4 | South |  | 3 | 96 | 6 | 93 | 76 | 17 | 17 | 0 | 17 | 0 | 0 | 0 | 0 | 0
8 | 4 | Rajajinagar | 4 | 37 | 0 | 41 | 34 | 7 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0
9 | 5 | RR Nagar | 0 | 36 | 1 | 35 | 27 | 8 | 7 | 1 | 8 | 0 | 0 | 0 | 0 | 0
10 | 6 | Kengeri | 0 | 77 | 2 | 75 | 73 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
11 | West |  | 4 | 150 | 3 | 151 | 134 | 17 | 14 | 3 | 17 | 0 | 0 | 0 | 0 | 0
| BMASZ |  | 7 | 246 | 9 | 244 | 210 | 34 | 31 | 3 | 34 | 0 | 0 | 0 | 0 | 0
1 | 1 | Malleswaram | 1 | 10 | 3 | 8 | 5 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2 | 2 | Hebbal | 0 | 77 | 0 | 77 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | Peenya | 0 | 35 | 3 | 32 | 21 | 11 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0
| 4 | Jalahalli | 6 | 27 | 6 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| North |  | 7 | 149 | 12 | 144 | 130 | 14 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 0
5 | 8 | Indiranagar | 5 | 21 | 5 | 21 | 20 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| 9 | Whitefield | 2 | 19 | 0 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | Shivajinagar | 0 | 108 | 0 | 108 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 11 | Vidhanasuoudha | 0 | 17 | 0 | 17 | 15 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0
7 | East |  | 7 | 165 | 5 | 167 | 164 | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0
| BMANZ |  | 14 | 314 | 17 | 311 | 294 | 17 | 3 | 14 | 17 | 0 | 0 | 0 | 0 | 0
13 | 15 | Nelamangala | 8 | 2 | 0 | 10 | 8 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
14 | 16 | Hosakote | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Nelamangala |  | 8 | 18 | 0 | 26 | 24 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
15 | 17 | Ramanagara | 1 | 69 | 16 | 54 | 48 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
| 18 | Magadi | 0 | 23 | 0 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 19 | Kanakapura | 1 | 2 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 20 | Chandapura | 0 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ramanagara |  | 2 | 97 | 16 | 83 | 77 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
16 | 21 | Kolar | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 22 | KGF | 8 | 7 | 1 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 23 | Chikkaballapur | 0 | 26 | 1 | 25 | 23 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
19 | 24 | Chintamani | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Kolar |  | 8 | 42 | 2 | 48 | 46 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| BRAZ |  | 18 | 157 | 18 | 157 | 147 | 10 | 0 | 8 | 8 | 0 | 0 | 0 | 2 | 2
20 | 25 | Davangere | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 26 | Harihara | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6
22 | 27 | Chitradurga | 0 | 37 | 0 | 37 | 32 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
23 | 28 | Hiriyuru | 0 | 32 | 1 | 31 | 30 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Davanagere |  | 1 | 75 | 1 | 75 | 63 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12
24 | 29 | Tumkur | 0 | 4 | 0 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| 30 | Kunigal | 1 | 9 | 0 | 10 | 9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
25 | 31 | Tipur | 1 | 10 | 1 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 32 | Madhugiri | 5 | 19 | 1 | 23 | 21 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| Tumkur |  | 7 | 42 | 2 | 47 | 42 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| CTAZ |  | 8 | 117 | 3 | 122 | 105 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 17
| BESCOM |  | 47 | 834 | 47 | 834 | 756 | 78 | 34 | 25 | 59 | 0 | 0 | 0 | 19 | 19

## Feb-2023
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Progress of Energisation of Drinking Water Supply for FY 2022-23 ( up to Feb-2023)
| Sl No | Zone/Circle/Division | No. of Applications pending as at the 31.03.2022 | No. of Applications registered | No. of Applications lapsed | Total Applications | No. of Applications serviced | No. of Applications pending | Applications pending with Local Bodies |  |  | Applications pending with BESCOM end
PÀæ. .¸ÀA | [8 empty] | Works completed from BESCOM end, but sevice not avalied | Formalilities not observed | Total applications pending from local bodies | Estimate to be under progress | Work order to be issued | Work to be taken up | Work under Progress | Total applications pending from BESCOM end
| 1 | 2 | 3 | 4 | 5 | 6=3+4-5 | 7 | 8=6-7 | 9 | 10 | 11=9+10 | 12 | 13 | 14 | 15 | 16=12+13+14+15
| 1 | Koramangala | 3 | 41 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | HSR | 0 | 41 | 0 | 41 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 3 | Jayanagar | 0 | 64 | 8 | 56 | 51 | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0
4 | South |  | 3 | 146 | 8 | 141 | 136 | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0
8 | 4 | Rajajinagar | 4 | 40 | 0 | 44 | 41 | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0
9 | 5 | RR Nagar | 0 | 41 | 1 | 40 | 34 | 6 | 1 | 5 | 6 | 0 | 0 | 0 | 0 | 0
10 | 6 | Kengeri | 0 | 80 | 2 | 78 | 73 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0
11 | West |  | 4 | 161 | 3 | 162 | 148 | 14 | 4 | 10 | 14 | 0 | 0 | 0 | 0 | 0
| BMASZ |  | 7 | 307 | 11 | 303 | 284 | 19 | 9 | 10 | 19 | 0 | 0 | 0 | 0 | 0
1 | 1 | Malleswaram | 1 | 10 | 6 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 2 | Hebbal | 0 | 89 | 0 | 89 | 82 | 7 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0
| 3 | Peenya | 0 | 35 | 3 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | Jalahalli | 6 | 32 | 6 | 32 | 27 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0
| North |  | 7 | 166 | 15 | 158 | 146 | 12 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0
5 | 8 | Indiranagar | 5 | 21 | 5 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | Whitefield | 2 | 19 | 0 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | Shivajinagar | 0 | 108 | 0 | 108 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 11 | Vidhanasuoudha | 0 | 17 | 0 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | East |  | 7 | 165 | 5 | 167 | 167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BMANZ |  | 14 | 331 | 20 | 325 | 313 | 12 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0
13 | 15 | Nelamangala | 8 | 3 | 0 | 11 | 8 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
14 | 16 | Hosakote | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Nelamangala |  | 8 | 19 | 0 | 27 | 24 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
15 | 17 | Ramanagara | 1 | 69 | 16 | 54 | 48 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
| 18 | Magadi | 0 | 24 | 0 | 24 | 23 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 19 | Kanakapura | 1 | 2 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 20 | Chandapura | 0 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ramanagara |  | 2 | 98 | 16 | 84 | 77 | 7 | 0 | 6 | 6 | 0 | 0 | 0 | 1 | 1
16 | 21 | Kolar | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 22 | KGF | 8 | 8 | 1 | 15 | 14 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
18 | 23 | Chikkaballapur | 0 | 35 | 1 | 34 | 30 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
19 | 24 | Chintamani | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Kolar |  | 8 | 52 | 2 | 58 | 53 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| BRAZ |  | 18 | 169 | 18 | 169 | 154 | 15 | 0 | 9 | 9 | 0 | 0 | 0 | 6 | 6
20 | 25 | Davangere | 1 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 26 | Harihara | 0 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 27 | Chitradurga | 0 | 43 | 0 | 43 | 42 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
23 | 28 | Hiriyuru | 0 | 32 | 1 | 31 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Davanagere |  | 1 | 82 | 1 | 82 | 81 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
24 | 29 | Tumkur | 0 | 5 | 0 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 30 | Kunigal | 1 | 12 | 0 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
25 | 31 | Tipur | 1 | 10 | 1 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 32 | Madhugiri | 5 | 19 | 1 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tumkur |  | 7 | 46 | 2 | 51 | 46 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
| CTAZ |  | 8 | 128 | 3 | 133 | 127 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6
| BESCOM |  | 47 | 935 | 52 | 930 | 878 | 52 | 9 | 31 | 40 | 0 | 0 | 0 | 12 | 12

## Mar-2023
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Progress of Energisation of Drinking Water Supply for FY 2022-23 ( up to Mar-2023)
| Sl No | Zone/Circle/Division | No. of Applications pending as at the 31.03.2022 | No. of Applications registered | No. of Applications lapsed | Total Applications | No. of Applications serviced | No. of Applications pending | Applications pending with Local Bodies |  |  | Applications pending with BESCOM end
PÀæ. .¸ÀA | [8 empty] | Works completed from BESCOM end, but sevice not avalied | Formalilities not observed | Total applications pending from local bodies | Estimate to be under progress | Work order to be issued | Work to be taken up | Work under Progress | Total applications pending from BESCOM end
| 1 | 2 | 3 | 4 | 5 | 6=3+4-5 | 7 | 8=6-7 | 9 | 10 | 11=9+10 | 12 | 13 | 14 | 15 | 16=12+13+14+15
| 1 | Koramangala | 3 | 41 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | HSR | 0 | 43 | 0 | 43 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 3 | Jayanagar | 0 | 70 | 8 | 62 | 58 | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0
4 | South |  | 3 | 154 | 8 | 149 | 145 | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0
8 | 4 | Rajajinagar | 4 | 53 | 0 | 57 | 48 | 9 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0
9 | 5 | RR Nagar | 0 | 46 | 1 | 45 | 38 | 7 | 2 | 5 | 7 | 0 | 0 | 0 | 0 | 0
10 | 6 | Kengeri | 0 | 85 | 4 | 81 | 78 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
11 | West |  | 4 | 184 | 5 | 183 | 164 | 19 | 11 | 8 | 19 | 0 | 0 | 0 | 0 | 0
| BMASZ |  | 7 | 338 | 13 | 332 | 309 | 23 | 15 | 8 | 23 | 0 | 0 | 0 | 0 | 0
1 | 1 | Malleswaram | 1 | 15 | 6 | 10 | 5 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0
2 | 2 | Hebbal | 0 | 90 | 0 | 90 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | Peenya | 0 | 35 | 3 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | Jalahalli | 6 | 37 | 10 | 33 | 32 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| North |  | 7 | 177 | 19 | 165 | 159 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
5 | 8 | Indiranagar | 5 | 24 | 5 | 24 | 21 | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0
| 9 | Whitefield | 2 | 19 | 0 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | Shivajinagar | 0 | 118 | 0 | 118 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 11 | Vidhanasuoudha | 0 | 19 | 0 | 19 | 17 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0
7 | East |  | 7 | 180 | 5 | 182 | 177 | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0
| BMANZ |  | 14 | 357 | 24 | 347 | 336 | 11 | 5 | 6 | 11 | 0 | 0 | 0 | 0 | 0
13 | 15 | Nelamangala | 8 | 3 | 0 | 11 | 8 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
14 | 16 | Hosakote | 0 | 20 | 0 | 20 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Nelamangala |  | 8 | 23 | 0 | 31 | 27 | 4 | 0 | 3 | 3 | 0 | 0 | 0 | 1 | 1
15 | 17 | Ramanagara | 1 | 82 | 16 | 67 | 48 | 19 | 0 | 19 | 19 | 0 | 0 | 0 | 0 | 0
| 18 | Magadi | 0 | 27 | 0 | 27 | 24 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
| 19 | Kanakapura | 1 | 2 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 20 | Chandapura | 0 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ramanagara |  | 2 | 114 | 16 | 100 | 78 | 22 | 0 | 19 | 19 | 0 | 0 | 0 | 3 | 3
16 | 21 | Kolar | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 22 | KGF | 8 | 9 | 1 | 16 | 14 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
18 | 23 | Chikkaballapur | 0 | 36 | 1 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 24 | Chintamani | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Kolar |  | 8 | 54 | 2 | 60 | 58 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| BRAZ |  | 18 | 191 | 18 | 191 | 163 | 28 | 0 | 22 | 22 | 0 | 0 | 0 | 6 | 6
20 | 25 | Davangere | 1 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 26 | Harihara | 0 | 8 | 0 | 8 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
22 | 27 | Chitradurga | 0 | 51 | 0 | 51 | 47 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
23 | 28 | Hiriyuru | 0 | 32 | 1 | 31 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Davanagere |  | 1 | 92 | 1 | 92 | 87 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
24 | 29 | Tumkur | 0 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 30 | Kunigal | 1 | 12 | 0 | 13 | 10 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
25 | 31 | Tipur | 1 | 10 | 1 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 32 | Madhugiri | 5 | 25 | 1 | 29 | 23 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6
| Tumkur |  | 7 | 52 | 2 | 57 | 48 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9
| CTAZ |  | 8 | 144 | 3 | 149 | 135 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 14
| BESCOM |  | 47 | 1030 | 58 | 1019 | 943 | 76 | 20 | 36 | 56 | 0 | 0 | 0 | 20 | 20