## April-2023
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Progress of Energisation of Drinking Water Supply for FY 2023-24 ( up to April-2023)
| Sl No | Zone/Circle/Division | No. of Applications pending as at the 31.03.2023 | No. of Applications registered | No. of Applications lapsed | Total Applications | No. of Applications serviced | No. of Applications pending | Applications pending with Local Bodies |  |  | Applications pending with BESCOM end
PÀæ. .¸ÀA | [8 empty] | Works completed from BESCOM end, but sevice not avalied | Formalilities not observed | Total applications pending from local bodies | Estimate to be under progress | Work order to be issued | Work to be taken up | Work under Progress | Total applications pending from BESCOM end
| 1 | 2 | 3 | 4 | 5 | 6=3+4-5 | 7 | 8=6-7 | 9 | 10 | 11=9+10 | 12 | 13 | 14 | 15 | 16=12+13+14+15
| 1 | Koramangala | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | HSR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 3 | Jayanagar | 4 | 7 | 0 | 11 | 2 | 9 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0
4 | South |  | 4 | 7 | 0 | 11 | 2 | 9 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0
8 | 4 | Rajajinagar | 9 | 23 | 0 | 32 | 3 | 29 | 29 | 0 | 29 | 0 | 0 | 0 | 0 | 0
9 | 5 | RR Nagar | 7 | 10 | 1 | 16 | 6 | 10 | 1 | 9 | 10 | 0 | 0 | 0 | 0 | 0
10 | 6 | Kengeri | 3 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | West |  | 19 | 33 | 1 | 51 | 12 | 39 | 30 | 9 | 39 | 0 | 0 | 0 | 0 | 0
| BMASZ |  | 23 | 40 | 1 | 62 | 14 | 48 | 39 | 9 | 48 | 0 | 0 | 0 | 0 | 0
1 | 1 | Malleswaram | 5 | 2 | 0 | 7 | 2 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0
2 | 2 | Hebbal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | Peenya | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | Jalahalli | 1 | 1 | 0 | 2 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| North |  | 6 | 3 | 0 | 9 | 3 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
5 | 8 | Indiranagar | 3 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | Whitefield | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | Shivajinagar | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 11 | Vidhanasuoudha | 2 | 3 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | East |  | 5 | 4 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BMANZ |  | 11 | 7 | 0 | 18 | 12 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
13 | 15 | Nelamangala | 3 | 1 | 0 | 4 | 0 | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
14 | 16 | Hosakote | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Nelamangala |  | 4 | 1 | 0 | 5 | 1 | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
15 | 17 | Ramanagara | 19 | 0 | 0 | 19 | 3 | 16 | 0 | 13 | 13 | 0 | 0 | 0 | 3 | 3
| 18 | Magadi | 3 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 19 | Kanakapura | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2
| 20 | Chandapura | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ramanagara |  | 22 | 2 | 0 | 24 | 6 | 18 | 0 | 13 | 13 | 0 | 0 | 2 | 3 | 5
16 | 21 | Kolar | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
17 | 22 | KGF | 2 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
18 | 23 | Chikkaballapur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 24 | Chintamani | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Kolar |  | 2 | 2 | 0 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| BRAZ |  | 28 | 5 | 0 | 33 | 9 | 24 | 0 | 17 | 17 | 0 | 0 | 2 | 5 | 7
20 | 25 | Davangere | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 26 | Harihara | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 27 | Chitradurga | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 28 | Hiriyuru | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Davanagere |  | 5 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 29 | Tumkur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 30 | Kunigal | 3 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
25 | 31 | Tipur | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
26 | 32 | Madhugiri | 6 | 2 | 0 | 8 | 1 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7
| Tumkur |  | 9 | 5 | 0 | 14 | 3 | 11 | 0 | 3 | 3 | 0 | 0 | 0 | 8 | 8
| CTAZ |  | 14 | 5 | 0 | 19 | 8 | 11 | 0 | 3 | 3 | 0 | 0 | 0 | 8 | 8
| BESCOM |  | 76 | 57 | 1 | 132 | 43 | 89 | 39 | 35 | 74 | 0 | 0 | 2 | 13 | 15

## May-2023
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Progress of Energisation of Drinking Water Supply for FY 2023-24 ( up to May-2023)
| Sl No | Zone/Circle/Division | No. of Applications pending as at the 31.03.2023 | No. of Applications registered | No. of Applications lapsed | Total Applications | No. of Applications serviced | No. of Applications pending | Applications pending with Local Bodies |  |  | Applications pending with BESCOM end
PÀæ. .¸ÀA | [8 empty] | Works completed from BESCOM end, but sevice not avalied | Formalilities not observed | Total applications pending from local bodies | Estimate to be under progress | Work order to be issued | Work to be taken up | Work under Progress | Total applications pending from BESCOM end
| 1 | 2 | 3 | 4 | 5 | 6=3+4-5 | 7 | 8=6-7 | 9 | 10 | 11=9+10 | 12 | 13 | 14 | 15 | 16=12+13+14+15
| 1 | Koramangala | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | HSR | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 3 | Jayanagar | 4 | 10 | 0 | 14 | 5 | 9 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0
4 | South |  | 4 | 11 | 0 | 15 | 6 | 9 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0
8 | 4 | Rajajinagar | 9 | 26 | 1 | 34 | 28 | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0
9 | 5 | RR Nagar | 7 | 15 | 5 | 17 | 9 | 8 | 6 | 2 | 8 | 0 | 0 | 0 | 0 | 0
10 | 6 | Kengeri | 3 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | West |  | 19 | 41 | 6 | 54 | 40 | 14 | 12 | 2 | 14 | 0 | 0 | 0 | 0 | 0
| BMASZ |  | 23 | 52 | 6 | 69 | 46 | 23 | 21 | 2 | 23 | 0 | 0 | 0 | 0 | 0
1 | 1 | Malleswaram | 5 | 2 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 2 | Hebbal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | Peenya | 0 | 11 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | Jalahalli | 1 | 1 | 0 | 2 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| North |  | 6 | 14 | 0 | 20 | 19 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
5 | 8 | Indiranagar | 3 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | Whitefield | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | Shivajinagar | 0 | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 11 | Vidhanasuoudha | 2 | 12 | 0 | 14 | 5 | 9 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0
7 | East |  | 5 | 16 | 0 | 21 | 12 | 9 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0
| BMANZ |  | 11 | 30 | 0 | 41 | 31 | 10 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0
13 | 15 | Nelamangala | 3 | 1 | 0 | 4 | 0 | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
14 | 16 | Hosakote | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Nelamangala |  | 4 | 1 | 0 | 5 | 1 | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
15 | 17 | Ramanagara | 19 | 15 | 0 | 34 | 3 | 31 | 0 | 28 | 28 | 0 | 0 | 0 | 3 | 3
| 18 | Magadi | 3 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 19 | Kanakapura | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
| 20 | Chandapura | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ramanagara |  | 22 | 18 | 0 | 40 | 6 | 34 | 0 | 28 | 28 | 0 | 0 | 0 | 6 | 6
16 | 21 | Kolar | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 22 | KGF | 2 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
18 | 23 | Chikkaballapur | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
19 | 24 | Chintamani | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Kolar |  | 2 | 4 | 0 | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
| BRAZ |  | 28 | 23 | 0 | 51 | 10 | 41 | 0 | 32 | 32 | 0 | 0 | 0 | 9 | 9
20 | 25 | Davangere | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 26 | Harihara | 1 | 1 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
22 | 27 | Chitradurga | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 28 | Hiriyuru | 0 | 2 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Davanagere |  | 5 | 3 | 0 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
24 | 29 | Tumkur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 30 | Kunigal | 3 | 1 | 0 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
25 | 31 | Tipur | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
26 | 32 | Madhugiri | 6 | 4 | 0 | 10 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8
| Tumkur |  | 9 | 8 | 0 | 17 | 4 | 13 | 0 | 3 | 3 | 0 | 0 | 0 | 10 | 10
| CTAZ |  | 14 | 11 | 0 | 25 | 10 | 15 | 0 | 3 | 3 | 0 | 0 | 0 | 12 | 12
| BESCOM |  | 76 | 116 | 6 | 186 | 97 | 89 | 21 | 47 | 68 | 0 | 0 | 0 | 21 | 21

## June-2023
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Progress of Energisation of Drinking Water Supply for FY 2023-24 ( up to June-2023)
| Sl No | Zone/Circle/Division | No. of Applications pending as at the 31.03.2023 | No. of Applications registered | No. of Applications lapsed | Total Applications | No. of Applications serviced | No. of Applications pending | Applications pending with Local Bodies |  |  | Applications pending with BESCOM end
PÀæ. .¸ÀA | [8 empty] | Works completed from BESCOM end, but sevice not avalied | Formalilities not observed | Total applications pending from local bodies | Estimate to be under progress | Work order to be issued | Work to be taken up | Work under Progress | Total applications pending from BESCOM end
| 1 | 2 | 3 | 4 | 5 | 6=3+4-5 | 7 | 8=6-7 | 9 | 10 | 11=9+10 | 12 | 13 | 14 | 15 | 16=12+13+14+15
| 1 | Koramangala | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | HSR | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 3 | Jayanagar | 4 | 13 | 5 | 12 | 6 | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0
4 | South |  | 4 | 15 | 5 | 14 | 8 | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0
8 | 4 | Rajajinagar | 9 | 28 | 1 | 36 | 30 | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0
9 | 5 | RR Nagar | 7 | 16 | 5 | 18 | 16 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
10 | 6 | Kengeri | 3 | 4 | 0 | 7 | 6 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
11 | West |  | 19 | 48 | 6 | 61 | 52 | 9 | 7 | 2 | 9 | 0 | 0 | 0 | 0 | 0
| BMASZ |  | 23 | 63 | 11 | 75 | 60 | 15 | 13 | 2 | 15 | 0 | 0 | 0 | 0 | 0
1 | 1 | Malleswaram | 5 | 3 | 0 | 8 | 7 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
2 | 2 | Hebbal | 0 | 10 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | Peenya | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | Jalahalli | 1 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| North |  | 6 | 30 | 0 | 36 | 35 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
5 | 8 | Indiranagar | 3 | 8 | 0 | 11 | 3 | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0
| 9 | Whitefield | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | Shivajinagar | 0 | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 11 | Vidhanasuoudha | 2 | 12 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | East |  | 5 | 24 | 0 | 29 | 21 | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0
| BMANZ |  | 11 | 54 | 0 | 65 | 56 | 9 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0
13 | 15 | Nelamangala | 3 | 2 | 0 | 5 | 0 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0
14 | 16 | Hosakote | 1 | 4 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Nelamangala |  | 4 | 6 | 0 | 10 | 5 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0
15 | 17 | Ramanagara | 19 | 15 | 0 | 34 | 6 | 28 | 0 | 28 | 28 | 0 | 0 | 0 | 0 | 0
| 18 | Magadi | 3 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 19 | Kanakapura | 0 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 20 | Chandapura | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ramanagara |  | 22 | 18 | 0 | 40 | 12 | 28 | 0 | 28 | 28 | 0 | 0 | 0 | 0 | 0
16 | 21 | Kolar | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 22 | KGF | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 23 | Chikkaballapur | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 24 | Chintamani | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Kolar |  | 2 | 4 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BRAZ |  | 28 | 28 | 0 | 56 | 23 | 33 | 0 | 33 | 33 | 0 | 0 | 0 | 0 | 0
20 | 25 | Davangere | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 26 | Harihara | 1 | 1 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
22 | 27 | Chitradurga | 4 | 1 | 0 | 5 | 4 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
23 | 28 | Hiriyuru | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Davanagere |  | 5 | 4 | 0 | 9 | 7 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1
24 | 29 | Tumkur | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 0
| 30 | Kunigal | 3 | 1 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 31 | Tipur | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4
26 | 32 | Madhugiri | 6 | 11 | 0 | 17 | 6 | 11 | 0 | 8 | 8 | 2 | 0 | 0 | 1 | 3
| Tumkur |  | 9 | 30 | 0 | 39 | 10 | 29 | 0 | 22 | 22 | 2 | 0 | 4 | 1 | 7
| CTAZ |  | 14 | 34 | 0 | 48 | 17 | 31 | 0 | 23 | 23 | 2 | 0 | 4 | 2 | 8
| BESCOM |  | 76 | 179 | 11 | 244 | 156 | 88 | 22 | 58 | 80 | 2 | 0 | 4 | 2 | 8

## July-2023
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Progress of Energisation of Drinking Water Supply for FY 2023-24 ( up to July-2023)
| Sl No | Zone/Circle/Division | No. of Applications pending as at the 31.03.2023 | No. of Applications registered | No. of Applications lapsed | Total Applications | No. of Applications serviced | No. of Applications pending | Applications pending with Local Bodies |  |  | Applications pending with BESCOM end
PÀæ. .¸ÀA | [8 empty] | Works completed from BESCOM end, but sevice not avalied | Formalilities not observed | Total applications pending from local bodies | Estimate to be under progress | Work order to be issued | Work to be taken up | Work under Progress | Total applications pending from BESCOM end
| 1 | 2 | 3 | 4 | 5 | 6=3+4-5 | 7 | 8=6-7 | 9 | 10 | 11=9+10 | 12 | 13 | 14 | 15 | 16=12+13+14+15
| 1 | Koramangala | 0 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | HSR | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 3 | Jayanagar | 4 | 20 | 7 | 17 | 11 | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0
4 | South |  | 4 | 25 | 7 | 22 | 16 | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0
8 | 4 | Rajajinagar | 9 | 36 | 6 | 39 | 31 | 8 | 1 | 7 | 8 | 0 | 0 | 0 | 0 | 0
9 | 5 | RR Nagar | 7 | 18 | 5 | 20 | 17 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
10 | 6 | Kengeri | 3 | 5 | 0 | 8 | 7 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
11 | West |  | 19 | 59 | 11 | 67 | 55 | 12 | 1 | 11 | 12 | 0 | 0 | 0 | 0 | 0
| BMASZ |  | 23 | 84 | 18 | 89 | 71 | 18 | 7 | 11 | 18 | 0 | 0 | 0 | 0 | 0
1 | 1 | Malleswaram | 5 | 3 | 0 | 8 | 7 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
2 | 2 | Hebbal | 0 | 10 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | Peenya | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | Jalahalli | 1 | 2 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| North |  | 6 | 31 | 0 | 37 | 36 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
5 | 8 | Indiranagar | 3 | 8 | 0 | 11 | 3 | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0
| 9 | Whitefield | 0 | 12 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | Shivajinagar | 0 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 11 | Vidhanasuoudha | 2 | 15 | 0 | 17 | 14 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
7 | East |  | 5 | 41 | 0 | 46 | 35 | 11 | 8 | 3 | 11 | 0 | 0 | 0 | 0 | 0
| BMANZ |  | 11 | 72 | 0 | 83 | 71 | 12 | 8 | 4 | 12 | 0 | 0 | 0 | 0 | 0
13 | 15 | Nelamangala | 3 | 5 | 0 | 8 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
14 | 16 | Hosakote | 1 | 4 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Nelamangala |  | 4 | 9 | 0 | 13 | 5 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
15 | 17 | Ramanagara | 19 | 16 | 0 | 35 | 7 | 28 | 0 | 16 | 16 | 0 | 0 | 0 | 12 | 12
| 18 | Magadi | 3 | 1 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 19 | Kanakapura | 0 | 6 | 0 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
| 20 | Chandapura | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ramanagara |  | 22 | 23 | 0 | 45 | 15 | 30 | 0 | 16 | 16 | 0 | 2 | 0 | 12 | 14
16 | 21 | Kolar | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 22 | KGF | 2 | 2 | 0 | 4 | 2 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
18 | 23 | Chikkaballapur | 0 | 3 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
19 | 24 | Chintamani | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Kolar |  | 2 | 7 | 0 | 9 | 6 | 3 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 1
| BRAZ |  | 28 | 39 | 0 | 67 | 26 | 41 | 0 | 26 | 26 | 0 | 2 | 0 | 13 | 15
20 | 25 | Davangere | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 26 | Harihara | 1 | 2 | 0 | 3 | 2 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
22 | 27 | Chitradurga | 4 | 2 | 0 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
23 | 28 | Hiriyuru | 0 | 4 | 0 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| Davanagere |  | 5 | 8 | 0 | 13 | 8 | 5 | 0 | 1 | 1 | 0 | 0 | 0 | 4 | 4
24 | 29 | Tumkur | 0 | 24 | 0 | 24 | 0 | 24 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0
| 30 | Kunigal | 3 | 2 | 0 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
25 | 31 | Tipur | 0 | 8 | 0 | 8 | 3 | 5 | 0 | 0 | 0 | 0 | 2 | 0 | 3 | 5
26 | 32 | Madhugiri | 6 | 20 | 3 | 23 | 8 | 15 | 0 | 10 | 10 | 0 | 0 | 0 | 5 | 5
| Tumkur |  | 9 | 54 | 3 | 60 | 15 | 45 | 0 | 34 | 34 | 0 | 2 | 0 | 9 | 11
| CTAZ |  | 14 | 62 | 3 | 73 | 23 | 50 | 0 | 35 | 35 | 0 | 2 | 0 | 13 | 15
| BESCOM |  | 76 | 257 | 21 | 312 | 191 | 121 | 15 | 76 | 91 | 0 | 4 | 0 | 26 | 30

## Aug-2023
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Progress of Energisation of Drinking Water Supply for FY 2023-24 ( up to Aug-2023)
| Sl No | Zone/Circle/Division | No. of Applications pending as at the 31.03.2023 | No. of Applications registered | No. of Applications lapsed | Total Applications | No. of Applications serviced | No. of Applications pending | Applications pending with Local Bodies |  |  | Applications pending with BESCOM end
PÀæ. .¸ÀA | [8 empty] | Works completed from BESCOM end, but sevice not avalied | Formalilities not observed | Total applications pending from local bodies | Estimate to be under progress | Work order to be issued | Work to be taken up | Work under Progress | Total applications pending from BESCOM end
| 1 | 2 | 3 | 4 | 5 | 6=3+4-5 | 7 | 8=6-7 | 9 | 10 | 11=9+10 | 12 | 13 | 14 | 15 | 16=12+13+14+15
| 1 | Koramangala | 0 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
| 2 | HSR | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
3 | 3 | Jayanagar | 4 | 26 | 7 | 23 | 17 | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 17 | 0
4 | South |  | 4 | 31 | 7 | 28 | 22 | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 22 | 0
8 | 4 | Rajajinagar | 9 | 38 | 11 | 36 | 35 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 35 | 0
9 | 5 | RR Nagar | 7 | 18 | 6 | 19 | 17 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 17 | 0
10 | 6 | Kengeri | 3 | 5 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0
11 | West |  | 19 | 61 | 17 | 63 | 60 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 60 | 0
| BMASZ |  | 23 | 92 | 24 | 91 | 82 | 9 | 6 | 3 | 9 | 0 | 0 | 0 | 0 | 0 | 82 | 0
1 | 1 | Malleswaram | 5 | 8 | 0 | 13 | 7 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 7 | 0
2 | 2 | Hebbal | 0 | 12 | 0 | 12 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0
| 3 | Peenya | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0
| 4 | Jalahalli | 1 | 2 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
| North |  | 6 | 38 | 0 | 44 | 36 | 8 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 36 | 0
5 | 8 | Indiranagar | 3 | 10 | 0 | 13 | 3 | 10 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 3 | 0
| 9 | Whitefield | 0 | 12 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0
| 10 | Shivajinagar | 0 | 10 | 0 | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0
6 | 11 | Vidhanasuoudha | 2 | 18 | 3 | 17 | 14 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0
7 | East |  | 5 | 50 | 3 | 52 | 35 | 17 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 35 | 0
| BMANZ |  | 11 | 88 | 3 | 96 | 71 | 25 | 10 | 6 | 16 | 0 | 0 | 0 | 0 | 0 | 71 | 0
13 | 15 | Nelamangala | 3 | 5 | 0 | 8 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 16 | Hosakote | 1 | 4 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0
| Nelamangala |  | 4 | 9 | 0 | 13 | 5 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 5 | 0
15 | 17 | Ramanagara | 19 | 27 | 0 | 46 | 7 | 39 | 0 | 27 | 27 | 0 | 0 | 0 | 12 | 12 | 7 | 0
| 18 | Magadi | 3 | 1 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
| 19 | Kanakapura | 0 | 6 | 0 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
| 20 | Chandapura | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ramanagara |  | 22 | 34 | 0 | 56 | 15 | 41 | 0 | 27 | 27 | 0 | 0 | 0 | 12 | 12 | 15 | 0
16 | 21 | Kolar | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
17 | 22 | KGF | 2 | 2 | 0 | 4 | 2 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
18 | 23 | Chikkaballapur | 0 | 4 | 0 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0
19 | 24 | Chintamani | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| Kolar |  | 2 | 8 | 0 | 10 | 6 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 6 | 0
| BRAZ |  | 28 | 51 | 0 | 79 | 26 | 53 | 0 | 37 | 37 | 0 | 0 | 0 | 14 | 14 | 28 | -2
20 | 25 | Davangere | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 26 | Harihara | 1 | 3 | 0 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 0
22 | 27 | Chitradurga | 4 | 6 | 0 | 10 | 9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 9 | 0
23 | 28 | Hiriyuru | 0 | 5 | 0 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 0
| Davanagere |  | 5 | 14 | 0 | 19 | 15 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 4 | 15 | 0
24 | 29 | Tumkur | 0 | 24 | 0 | 24 | 0 | 24 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 30 | Kunigal | 3 | 5 | 0 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0
25 | 31 | Tipur | 0 | 9 | 0 | 9 | 4 | 5 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 5 | 4 | 0
26 | 32 | Madhugiri | 6 | 28 | 3 | 31 | 8 | 23 | 0 | 10 | 10 | 2 | 0 | 0 | 11 | 13 | 8 | 0
| Tumkur |  | 9 | 66 | 3 | 72 | 16 | 56 | 0 | 34 | 34 | 2 | 2 | 2 | 16 | 22 | 16 | 0
| CTAZ |  | 14 | 80 | 3 | 91 | 31 | 60 | 0 | 34 | 34 | 2 | 2 | 3 | 19 | 26 | 31 | 0
| BESCOM |  | 76 | 311 | 30 | 357 | 210 | 136 | 16 | 80 | 96 | 2 | 2 | 3 | 33 | 40 | 221 | -11
80

## Sept-2023
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Progress of Energisation of Drinking Water Supply for FY 2023-24 ( up to Sept-2023)
| Sl No | Zone/Circle/Division | No. of Applications pending as at the 31.03.2023 | No. of Applications registered | No. of Applications lapsed | Total Applications | No. of Applications serviced | No. of Applications pending | Applications pending with Local Bodies |  |  | Applications pending with BESCOM end
PÀæ. .¸ÀA | [8 empty] | Works completed from BESCOM end, but sevice not avalied | Formalilities not observed | Total applications pending from local bodies | Estimate to be under progress | Work order to be issued | Work to be taken up | Work under Progress | Total applications pending from BESCOM end
| 1 | 2 | 3 | 4 | 5 | 6=3+4-5 | 7 | 8=6-7 | 9 | 10 | 11=9+10 | 12 | 13 | 14 | 15 | 16=12+13+14+15
| 1 | Koramangala | 0 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | HSR | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 3 | Jayanagar | 4 | 26 | 7 | 23 | 17 | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0
4 | South |  | 4 | 31 | 7 | 28 | 22 | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0
8 | 4 | Rajajinagar | 9 | 39 | 11 | 37 | 35 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
9 | 5 | RR Nagar | 7 | 18 | 6 | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 6 | Kengeri | 3 | 6 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | West |  | 19 | 63 | 17 | 65 | 63 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
| BMASZ |  | 23 | 94 | 24 | 93 | 85 | 8 | 6 | 2 | 8 | 0 | 0 | 0 | 0 | 0
1 | 1 | Malleswaram | 5 | 8 | 1 | 12 | 9 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2 | 2 | Hebbal | 0 | 13 | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | Peenya | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | Jalahalli | 1 | 8 | 1 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| North |  | 6 | 45 | 2 | 49 | 46 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
5 | 8 | Indiranagar | 3 | 10 | 8 | 5 | 3 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0
| 9 | Whitefield | 0 | 12 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | Shivajinagar | 0 | 10 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 11 | Vidhanasuoudha | 2 | 24 | 3 | 23 | 20 | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0
7 | East |  | 5 | 56 | 11 | 50 | 45 | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0
| BMANZ |  | 11 | 101 | 13 | 99 | 91 | 8 | 5 | 3 | 8 | 0 | 0 | 0 | 0 | 0
13 | 15 | Nelamangala | 3 | 5 | 0 | 8 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
14 | 16 | Hosakote | 1 | 4 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Nelamangala |  | 4 | 9 | 0 | 13 | 5 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
15 | 17 | Ramanagara | 19 | 27 | 0 | 46 | 20 | 26 | 0 | 26 | 26 | 0 | 0 | 0 | 0 | 0
| 18 | Magadi | 3 | 2 | 0 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| 19 | Kanakapura | 0 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 20 | Chandapura | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ramanagara |  | 22 | 35 | 0 | 57 | 30 | 27 | 0 | 26 | 26 | 0 | 0 | 0 | 1 | 1
16 | 21 | Kolar | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 22 | KGF | 2 | 2 | 0 | 4 | 2 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
18 | 23 | Chikkaballapur | 0 | 8 | 0 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
19 | 24 | Chintamani | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Kolar |  | 2 | 12 | 0 | 14 | 9 | 5 | 0 | 2 | 2 | 0 | 0 | 0 | 3 | 3
| BRAZ |  | 28 | 56 | 0 | 84 | 44 | 40 | 0 | 36 | 36 | 0 | 0 | 0 | 4 | 4
20 | 25 | Davangere | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 26 | Harihara | 1 | 3 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 27 | Chitradurga | 4 | 14 | 0 | 18 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 8
23 | 28 | Hiriyuru | 0 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Davanagere |  | 5 | 22 | 0 | 27 | 19 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 8
24 | 29 | Tumkur | 0 | 30 | 0 | 30 | 0 | 30 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 0
| 30 | Kunigal | 3 | 6 | 0 | 9 | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
25 | 31 | Tipur | 0 | 9 | 0 | 9 | 4 | 5 | 0 | 1 | 1 | 0 | 0 | 0 | 4 | 4
26 | 32 | Madhugiri | 6 | 41 | 7 | 40 | 20 | 20 | 0 | 14 | 14 | 0 | 0 | 0 | 6 | 6
| Tumkur |  | 9 | 86 | 7 | 88 | 32 | 56 | 0 | 45 | 45 | 0 | 0 | 0 | 11 | 11
| CTAZ |  | 14 | 108 | 7 | 115 | 51 | 64 | 0 | 45 | 45 | 0 | 0 | 8 | 11 | 19
| BESCOM |  | 76 | 359 | 44 | 391 | 271 | 120 | 11 | 86 | 97 | 0 | 0 | 8 | 15 | 23