## 01-09-2021
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Schedule Interruptions for the month of September 2021
Details of works to avail Line Clear for CAPEX, RC, Service connection, OH to UG conversion, Self execution maintenance works
Sl No | Circle | Division | Sub Dvn | OM Unit | Station Name | Feeder No /Name | IF LT Work DTC code capacity | Nomenclature of Works | CAPEX/ Maintenance | Work order No and Date | Sanctioned Date | Date of LC planned | Areas affected | No: of consumers affected |  | Duration of LC required |  |  | Remarks (changeover arranged details) | Work Belongs to Station / BESCOM | LC Taken or Not (Yes / No) | Issue | Remarks | Station/Feeder charged time |  |  | Confirmed by BESCOM / KPTCL | Remarks (If time extended)
[14 empty] | HT consumers | LT consumers | from | To | Total interruption period in | [5 empty] | From | To | Total interruption period in
1 | RAMANAGARA | CHANDAPURA DIVISION | AT1 | Attibele | Attibele | F15-ATTIBELE-URBAN |  | Tree trimming & 11 KV jump replacement. | Maintenance Work |  |  | 01-09-2021 | Attibele Town towards Sarjapura Road |  |  | 10:00 | 14:00 | 4:00
2 | RAMANAGARA | CHANDAPURA DIVISION | AT1 | Attibele Indutrial Area | Attibele,Chandapura | F13-NIRANTHARA-JYOTHI, F22-AGS,F04-YADAVANAHALLI, F21-KHB of ATB MUSS & F07-ATTIBELE of CDP MUSS |  | Tree trimming & 11 KV jump replacement. | Maintenance Work |  |  | 01-09-2021 | Yadavanhalli, Jigala,Guddahatti, Raghavendra Layout (Guestline), Guddahatti Gate, Guddahatti Road, Yadavanahalli Gate & KHB 3rd Phase & Oxford Hospital & Sri Sai Hospital (Guestline) |  |  | 10:00 | 14:00 | 4:00
3 | RAMANAGARA | CHANDAPURA DIVISION | AT1 | Sarjapura | Sarjapura | F05-MUGLOOR-URBAN & F11-NJY HANDENAHALLY |  | Tree trimming & 11 KV/LT jump replacement. GOS maintaminance, LT lead relacement, Jungle cutting | Maintenance Work |  |  | 01-09-2021 | Sabic Industry ,Andenahalli |  |  | 11:00 | 14:00 | 3:00
4 | RAMANAGARA | CHANDAPURA DIVISION | AT1 | Mayasandra | Attibele,Samandhuru | F20 NJY kamblipura , F5 mayasandra, F05 Halehalli , F6 Kodlipura |  | Tree trimming & 11 KV/LT jump replacement. GOS maintaminance, LT lead relacement, Jungle cutting | Maintenance Work |  |  | 01-09-2021 | Kamablipura, Musthasandra, mayasandra, Kodlipura, Halehalli, Harohalli , M medihalli, Thattnahalli village |  |  | 11:00 | 14:00 | 3:00
5 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | BP1 | O&M-2 | BAGEPALLI | F8 TB CROSS | 11 kv Branch line | B.A.Venkatesh S/o Amaranarayanawamy,Hosahudya. | Maintenance Work | T-26207 /03.07.2021 |  | 01-09-2021 | Gantamvaripalli,Hosahudya,Narepalli,TB Cross,Abakavaripalli.Adiganapalli. |  |  | 15:00 | 16:00 | 1:00
6 | NORTH | MALLESHWARAM | C1 | Rajajinagar 2ndstage | NRS | F09 Nandhini | DTC211 212 | LT AB Cable | CAPEX |  |  | 01-09-2021 | NILGIRI PAPANNA BLOCK |  |  | 10:00 | 17:00 | 7:00
7 | NORTH | MALLESHWARAM | C2 | Malleshwaram | A STATION | F8 S S PURAM | LT Line with DTC No12 & 13 | MAINTENANCE & ATTENDING HAZARDOUS AT POLES | Maintenance Work |  |  | 01-09-2021 | 2ND MAIN ROAD. SWASTIC COMPLEX |  |  | 10:30 | 14:00 | 3:30
8 | NORTH | MALLESHWARAM | C6 | Mathikere | IISC | F6 | 11 KV Feeder DTC TC 165, TC 63, TC 64, TC 293, TC 305, HT 114, TC 20, TC 78, TC 35 | Overhead to UG Works | CAPEX |  |  | 01-09-2021 | Triveni Road & Diwanarapalya |  |  | 10:30 | 18:00 | 7:30
9 | NORTH | HEBBAL | C7 | Yelahanka new town | KHB | F12 | 11 KV FeederDTC-247,DTC-228,DTC-229, DTC-17,DTC-745 | Conversion of 11KV OH to UG Line for F12 ( KHB Muss) BLR- Feeder in Yelahanka New Town O&M 19 of C7 Sub Division, Hebbal Division | CAPEX |  |  | 01-09-2021 | Chikkabommasandra |  |  | 10:00 | 17:00 | 7:00
10 | NORTH | HEBBAL | C7 | Yelahanka old town | ATTUR | F10 | 11 KV Feeder DTC SaiBaba temple Road/ Railway Parallel Road | Conversion of 11KV OH to UG Line for F10 ( Yelakhanka Muss) IAF BLR- Feeder in Yelahanka Old Town O&M 19A of C7 Sub Division, Hebbal Division | CAPEX |  |  | 01-09-2021 | SaiBaba Colony Road/ Railway Parallel Road |  |  | 10:00 | 17:00 | 7:00
11 | DAVANAGERE CIRCLE | CHITRADURGA DIVISION | CD2 | Bheemasamudra | HIREGUNTANUR_66 | F10Beeravara NJY | 11 KV Feeder | Maintenance work | Maintenance Work |  |  | 01-09-2021 | Dyamenahalli,Beeravara,K. Ballekatte,Katral,Katral Thimmapanahalli,Kodagavalli,Kyasapura,Neelayanahatti,Sadrahalli, |  |  | 13:00 | 15:00 | 2:00
12 | DAVANAGERE CIRCLE | CHITRADURGA DIVISION | CD2 | Bheemasamudra | HIREGUNTANUR_66 | F13Malali NJY | 11 KV Feeder | Maintenance work | Maintenance Work |  |  | 01-09-2021 | Kadleguddu,Megalahalli,Bheemasamudra,Bommenahalli,Bommenahalli Gollarahatti,Vaddarapalya,Malali,Nallikatte, |  |  | 13:00 | 15:00 | 2:00
13 | RAMANAGARA | CHANDAPURA DIVISION | CH1 | Bommasandra | Yarandahalli | F3 Tygotech |  | Tree trimming, Maintenance of GOS, loose span restrining, Bent pole straightening | Maintenance Work |  |  | 01-09-2021 | Tegutech , BIA |  |  | 10:00 | 12:00 | 2:00
14 | RAMANAGARA | CHANDAPURA DIVISION | CH1 | Bommasandra | Yarandahalli | F8 Bulzar |  | Tree trimming, Maintenance of GOS, loose span restrining, Bent pole straightening | Maintenance Work |  |  | 01-09-2021 | Bommasandra Indl area |  |  | 10:00 | 12:00 | 2:00
15 | RAMANAGARA | CHANDAPURA DIVISION | CH1 | Chandapura | Chandapura | F11 Vakil layout |  | Tree trimming, Maintenance of GOS, loose span restrining, Bent pole straightening | Maintenance Work |  |  | 01-09-2021 | Vakil Layout , Tirumagodnanahalli Village |  |  | 10:00 | 12:00 | 2:00
16 | RAMANAGARA | CHANDAPURA DIVISION | CH1 | Chandapura | Chandapura | F08-Keerthi layout |  | Tree trimming, Maintenance of GOS, loose span restrining, Bent pole straightening | Maintenance Work |  |  | 01-09-2021 | Keeerthi Layout, Teachers Colony, Chandapura |  |  | 10:00 | 12:00 | 2:00
17 | RAMANAGARA | CHANDAPURA DIVISION | CH1 | Chandapura | Chandapura | F15- Thirumagondanahalli |  | Tree trimming, Maintenance of GOS, loose span restrining, Bent pole straightening | Maintenance Work |  |  | 01-09-2021 | Tirumagondanahalli Village , Neraluru , Vakil Layout |  |  | 10:00 | 12:00 | 2:00
18 | RAMANAGARA | RAMANAGARA DIVISION | CP2 | Honganoor | CHANNAPATNA | F-21 HODIKEHOSAHALLI |  | MAINTENANCE | Maintenance Work |  |  | 01-09-2021 | HODIKEHOSAHALLI, SUNNAGATTA, NEELASANDRA |  |  | 10:45 | 13:40 | 2:55
19 | BRC | NELAMANGALA DIVISION | DB1 | O&M-2 | 66/11KV D.Cross | F10-Vasavi | DTC DTC 1 | H.M.Mangala W/o N.Kumaraja Palanajogihalli DBPUR | Maintenance Work | G 20734 01.07.2021. |  | 01-09-2021 | Palanajogihalli |  |  | 10:00 | 17:00 | 7:00
20 | BRC | NELAMANGALA DIVISION | DB1 | O&M-2 | 66/11KV D.Cross | F01-Local2 | DTC DTC 1 | N.Krishnappa T.Narayanappa Chikkapete DBPUR | Maintenance Work | G 26921 01.07.2021 |  | 01-09-2021 | Chikkapete |  |  | 10:00 | 17:00 | 7:00
21 | EAST | INDIRANAGAR | E10 | BGH | ITI | F16 ITI | 11 kv Branch line DTC 725,DTC 459,DTC 83, DTC 495 | Dismantling | CAPEX | 405/20/OH to UG/IND/14-192/G-1016 |  | 01-09-2021 | B Narayanapura, Anugraha L/o, Satya Colony |  |  | 10:00 | 16:00 | 6:00 | Full Feeder LC
22 | EAST | INDIRANAGAR | E11 | Akshay Nagar | ITI | F1 IPDS | 11 Kv Feeder 1.New 3 Way Non Das RMU 1 Near ITI to New 3 Way Non Das RMU 2 Near Manam nagar. 2.Ex 3 Way RMU near Kranthi Sweets VL-01 to F1 IPDS SP FDTC - BANANA TC - 57 250KVA. 3.New 3 way RMU - 04 near SABARMATHI ENCLAVE OD-2. 4.C/O F1 - RM Nagar 5 way RMU Feeder RAK CERAMICS RMU OD-2 | 400 Sqmm Charging | CAPEX | 405/20/OH TO UG/IND/14-192/F-3135/31.03.2020 |  | 01-09-2021 | Manam Nagar Road |  |  | 10:00 | 16:00 | 6:00
23 | EAST | INDIRANAGAR | E11 | RM NAGAR | ITI | F10 HOYSALA NAGAR | 11 kv Branch Line & LT Line With DTC 1.OPP JUICE POINT RMU-6 V/L-2 to SRI DEVI APPT. 2.SRI DEVI APPT. to OPP BHARAT PETROL PUMP SPUN POLE. 3.OPP BHARAT PETROL PUMP SPUN POLE to DOMINAS PIZZA. 4.DOMINAS PIZZA to ANNAI RESIDENCY. 5.AYURVEDIC HOSPITAL to RK APPT BLOCK-10. 6.RK APPT BLOCK-10 to RK APPT BLOCK 10-B 7.OPP JUICE POINT RMU-6 V/L-3 to VARS NOTHING HILLS-1. 8.VARS NOTHING HILLS-1 to VARS NOTHING HILLS-2. 9.VARS NOTHING HILLS-2 to FDTC-300( OPP SRI RAM AGENCY) | 1.95 Sqmm Cable Charging & GOS. 2.240 Sqmm&AB Cable Charging | CAPEX |  |  | 01-09-2021 | 7TH MAIN HOYSALA NAGAR, 4TH MAIN HOYSALA |  |  | 10:00 | 16:00 | 6:00
24 | EAST | INDIRANAGAR | E11 | Bhattarhalli | ITI | F7 KIADB | 11 kv Branch Line 1. F-07 5W RMU 8 O/D-2 to F-07 3 RMU 9 Ds Max 2. F-07 3 RMU 9 Ds Max to F-07 5W RMU 10 Ananda Sadan 3.F-07 5W RMU 10 O/D-2 to F-07 3W RMU 11 Adorno Bhavan | 400 SQMM & RMU's | CAPEX |  |  | 01-09-2021 | Subhash nagar , TC palya , Bhatrahalli, halehalli , garden city college sorounding areas |  |  | 10:00 | 16:00 | 6:00
25 | EAST | SHIVAJINAGAR | E5 | Lingarajapura | BANASWADI | F09 | 8 | HT UG cable raising and structure work uinder OH to UG conversion project | CAPEX | G-45751 |  | 01-09-2021 | K. K. Halli, Sukh Sagar Hotel |  |  | 10:00 | 17:00 | 7:00 | -
26 | EAST | INDIRANAGAR | E6 | DMLR | LEELA | F12 LEELA | 11 kv Branch line Full Feeder | HT UG Cable commissioning | CAPEX | 405/20/OH to UG/IND/14-192/G-1018 |  | 01-09-2021 | Domlur |  |  | 10:00 | 16:00 | 6:00
27 | EAST | INDIRANAGAR | E6 | INR | NGEF S/S | F07 NGEF | 11 kv Branch line TC165, TC129, TC315,TC42, TC 252 | HT UG Cable commissioning | CAPEX | 405/21/INR/OH to UG/14-192/H-1304 |  | 01-09-2021 | Hoysala Nagar |  |  | 10:00 | 16:00 | 6:00
28 | EAST | SHIVAJINAGAR | E9 | Kothanur | Geddalahalli | F-06 | TC - S.MASHANA | OH to UG Conversion | CAPEX | 1627942 & 01.04.2021 |  | 01-09-2021 | LAWYER LAYOUT |  |  | 0:00 | 120:00 | 120:00 | -
29 | RAMANAGARA | KANAKAPURA DIVISION | HA1 | JAKKASANDRA | HANUMANTHANAGARA | F10 KEERANAGERE |  | JUNGLE CLEARNCE | Maintenance Work |  |  | 01-09-2021 | T HOSAHALLI |  |  | 11:00 | 16:00 | 5:00
30 | RAMANAGARA | CHANDAPURA DIVISION | JN1 | Jigani | 66/11KV Jigani | F02 Harapanahalli |  | GOS Maintanance works and tree trimming works | Maintenance Work |  |  | 01-09-2021 | Hrapanahlli,Koppa Gate,Vatika ,Spring wood,Sattarasabdinne |  |  | 10:00 | 14:00 | 4:00
31 | WEST | KENGERI | K2 | DB Kallu | NG Halli | F-12-HT | Spur Line TC-86,69,75,STCK2-388 ,18 &43 | Estimate for conversion of 11KV OH Line to HT UG Cable of F12 feeder from NG Halli muss in Doddabidarakallu O&M-3, K2 Sub divin, Kengeri Divin, Bangalore | CAPEX | I-15412 I-15612 I-15712 ,DT:22-02-2021 |  | 01-09-2021 | SUVARNANAGAR,SUVARNANAGAR BUS STOP |  |  | 10:00 | 17:00 | 7:00
32 | WEST | KENGERI | K2 | Herohalli | Byadarahalli | F-3 -LT | Spur Line TC-217,272 | Estimate for conversion of LT OH to LT AB Cable of F3 feeder from Byadarahalli muss in Herohalli O&M-1, K2 Sub divin, Kengeri Divin, Bangalore-91 | CAPEX | I-15404 I-15704 I-15604 ,DT:13-01-2021 |  | 01-09-2021 | Hosahalli |  |  | 10:00 | 17:00 | 7:00
33 | WEST | KENGERI | K2 | Andrahalli | NG Halli | F-7-LT | Spur Line TC-57,NFTC Mamata,87 | Estimate for conversion of LT OH to LT AB Cable of F07 feeder from NG Halli muss in Andrahalli O&M-2, K2 Sub divin, Kengeri Divin, Bangalore-91 | CAPEX | I-15407 I-15707 I-15607 Dt:13-01-2021 |  | 01-09-2021 | T.G. PALYA GOV.SCHOOL |  |  | 10:00 | 17:00 | 7:00
34 | WEST | KENGERI | K4 | Anjananagara | SIR MV | F13 | Full Feeder | Estimate FOR CONVERSION OF 11KV OH LINE INTO UGCABLE SYSTEM OF EXISTING F-9 FEEDER(RHCSLAYOUT) FEEDING FROM SIR M V MUSS INANJANANAGARA O&M UNIT-1, K-4 SUB DIVISION ON RATE CONTRACT BASIS | CAPEX | I-15028 I-15228 I-15328 Dt:25.02.2021 |  | 01-09-2021 | SIR MV 5th Block, Ambednagar,Ullal Bus Stand, BDA Colony |  |  | 9:00 | 17:00 | 8:00
35 | RAMANAGARA | KANAKAPURA DIVISION | KP1 | O&M-2 | Chatra_66 | Agrahara NJY |  | Maintenance | Maintenance Work |  |  | 01-09-2021 | Budiguppe , Kallahalli, Agrahara |  |  | 11:00 | 13:00 | 2:00
36 | RAMANAGARA | KANAKAPURA DIVISION | KP2 | Hookunda | Hookunda | F05-Doddakoppa Agri |  | Jungle Cutting and line maintenance | Maintenance Work |  |  | 01-09-2021 | Thagadegowdanadoddy, Doddakoppa, Balepuradoddy, Kotekoppa, Arepalya |  |  | 11:10 | 17:00 | 5:50
37 | TUMKUR CIRCLE | TUMKUR DIVISION | KYT | KYATHSANDRA | 66/11kV MUSS Hirehalli | HF-10 SS Mutt & HF-09 M N PALYA | 11 KV Feeder | For replacement of existing 11 KV overhead lines by 11 KV Covered condcutor in Kyathsandra Section | Maintenance Work |  |  | 01-09-2021 | Siddaganga Mutt, Karekal Palya, B M Palya, Basavapatna, Basaveshwara Extn, Joss Toll |  |  | 10:00 | 18:00 | 8:00
38 | RAMANAGARA | MAGADI | MA1 | O&M-2 | 66/11KV MAGADI | MF3 KALYA, MF5 CHAKRABHVAI, MF6 KENCHANAHALLI, MF16 CHANDURAYANAHALLI |  | Kship work | Maintenance Work |  |  | 01-09-2021 | Kalya , kalya Colony hhg palya hosaplaya |  |  | 10:00 | 13:00 | 3:00
39 | KOLAR CIRCLE | KGF DIVISION | ML1 | KUDIYANUR | lakkur | F-04 chanagarayapura | 11 kv Branch line | Est for APS to 10Kw for farm house in favour of Sri.Ravindra S/o Ramaiah at Chalaganahalli in Kudiyanur Sec. | CAPEX & Other Works |  |  | 01-09-2021 | chalaganahalli (v) limit |  |  | 11:00 | 12:00 | 1:00
40 | NORTH | PEENYA | N7 | Mahalakshmi layout /kurubarahalli | MAHALAKSHMI LAYOUT | F5 HAMSASAGAR | 11 kv Branch line DTC 03 NOS | OH TO LT AB CABLECONVERSION WORK | CAPEX | 2020/PD/14-1927/ H-1916/13.01.21 |  | 01-09-2021 | MLA Office back side road, 14th Main M.L.Puram, 2nd Stage Surrounding Area |  |  | 10:00 | 18:00 | 8:00
41 | WEST | RAJAJINAGAR | N8 | NAGARABHAVI | CHANDRALAYOUT | F-07 | 167,709,731 | Conversion of 11KV Overhead line into HT Ug Cable inFeeder CL F7 (O&M Nagarbhvai) N8 Sub Division,Rajaji nagar Division Bangalore West Circle, BMAZ (South), BESCOM under PHASE-I on Total turnkey under Rate Contract (RC.05) on Percentage basis quoting. | CAPEX | 2020/RN/14-1927/N-106353/12.01.2021 |  | 01-09-2021 | MALAGAL, RAMA KRISHNAPPA LYT | 0 | 350 | 10:30 | 17:30 | 7:00 | Works includes Srtinging of LT ab Cable one day and connecting servicing connections and load balancing one day
42 | TUMKUR CIRCLE | MADHUGIRI DIVISION | PG1 | Venkatapura | Venkatapura 66/11KV | F08 Venkatapura NJY | DTC 6 | Awarding of Water supply works under rate contract PTK Basis Pavagada S/d Madhugiri Division at Venkatapura Village near Muthyalamma Temple in Venkatapura section | CAPEX & Other Works | S-49041/07.07.2021 |  | 01-09-2021 | Venkatapura, Neralakunte, Krishnapura |  |  | 10:00 | 17:00 | 7:00
43 | RAMANAGARA | RAMANAGARA DIVISION | RM2 | Kylancha | Shivanahalli_66kv | F6 kavanapura njy |  | Tree trimming | Maintenance Work |  |  | 01-09-2021 | SRS ROAD |  |  | 10:00 | 14:00 | 4:00
44 | SOUTH | JAYANAGAR | S1 | Jayanagar 8th Block | Jayanagar | F7- Jayanagar | DTC popular bajaj loop | A/P/S to the premises of S V Ramesh | CAPEX & Other Works | 16.11.2020 |  | 01-09-2021 | 12th Cross, 7th Block, Jayanagar |  |  | 11:00 | 12:30 | 1:30
45 | SOUTH | JAYANAGAR | S1 | Jayanagar 8th Block | Jayanagar | F7- Jayanagar | DTC Kruzal House loop | A/P/S to the premises of M R Hamsasree | CAPEX & Other Works | 05.03.2021 |  | 01-09-2021 | 27th cross, 6th Block, Jayanagar |  |  | 11:00 | 12:30 | 1:30
46 | SOUTH | JAYANAGAR | S1 | Jayanagar 8th Block | Jayanagar | F02-Jayanagara | DTC S 89.92.184.88.85.87.86 | AB CABLE LAYING + CHARGING | CAPEX | 14.1927/K-8758-28.6.21 |  | 01-09-2021 | 4th block, 7th Main, 8th Main, 6th B main, 6th C Main,5th Main |  |  | 10:00 | 17:30 | 7:30
47 | SOUTH | HSR | S12 | THALGHATTPURA | Sobha Forest View | F4 | 11 KV Feeder DTC 6 | Annapurna Upnal No 24,Katha No306/24 Hosahalli Village Uttarahalli HobliBengaluru | Maintenance Work | N- 11748/ 28.04.2021 |  | 01-09-2021 | BSK 6th stage, Hosahalli, part of Ganigarapala |  |  | 10:30 | 15:30 | 5:00 | Iskon F05
48 | SOUTH | HSR | S12 | THALGHATTPURA | Khodays | F11 | 11 KV Feeder DTC 26 | M/s Adithya Tantia and Prithi Tantia at #215,216 KH No 215&216, Doddakallasandra,Uttarahalli Hobli Bengaluru | Maintenance Work | M-13898/23.03.2021 |  | 01-09-2021 | Narayana nagar 1st Block |  |  | 10:30 | 15:30 | 5:00 | Khodays F12
49 | SOUTH | JAYANAGAR | S14 | JP NAGAR O&M | SARAKKI | F21 | 11 KV Feeder | RABBIT RELEASED AND LT ABC | CAPEX | J-8834/15-12-2020 & K-8787/13-08-2021 |  | 01-09-2021 | JP NAGAR 24TH MAIN ROAD , AYODYA NAGAR , JP NAGAR 5TH PHASE RAJAKALUVE |  |  | 10:00 | 17:30 | 7:30
50 | SOUTH | JAYANAGAR | S18 | U2 Chikkallasandra | Arehally | F08 | 11 KV Feeder | 3GOS Structure Work | CAPEX | 1572828 23.11.2020 |  | 01-09-2021 | Munireddy L/O |  |  | 10:00 | 17:00 | 7:00
51 | SOUTH | JAYANAGAR | S2 | U-2 SAMPANGI RAMANAGAR | BMTC | F02 | DTC DTC NO:220 | LT AB CABLE STRINGING | CAPEX | K-8762 DATE:28.6.2021 1874-78 DATE:09.07-2021 |  | 01-09-2021 | CSI COMPOUND |  |  | 10:00 | 17:00 | 7:00
52 | SOUTH | JAYANAGAR | S2 | U-3 SHANTHINAGAR | BMTC | F10 | DTC DTC NO:362 | LT AB CABLE STRINGING | CAPEX | K-8768 DATE:28.6.2021 1839-43 DATE:09.07-2021 |  | 01-09-2021 | RRMR EXTENSION COMMON BUS STAND TC-490 |  |  | 10:00 | 17:00 | 7:00
53 | SOUTH | HSR | S20 | HSR | HSR | F21 | 11 KV Feeder DTC 2 | CONVERSION OF O/H TO UG CABLE WORK-STRUCTURE WORK AND AB CABLE WORK | CAPEX | 14.192/M-12501 16.206/L-12551 DT:11.09.2020 |  | 01-09-2021 | KSRP QUATRES VENKATAPURA |  |  | 10:00 | 17:00 | 7:00
54 | SOUTH | JAYANAGAR | S6 | Puttenahalli Unit-5 | 66/11KV RBI | F12-PUTTENAHALLI | 11 KV Feeder | 3 GOS STRUCTURE WORK | CAPEX | OH-UG/ 14:1927/ Ph-11/ RC-06/S6/ H-9981/30.3.2020 |  | 01-09-2021 | Puttenahalli main rd, bank of baroda colony, nataraja l/o, wilson garden society, Chengama raj l/o, Srirama l/o, 24th mn, acchappa l/o, |  |  | 10:00 | 17:30 | 7:30
55 | SOUTH | JAYANAGAR | S9 | PADMANABHA NAGAR | Padmanabhanagar | F08-Rajiv Nagar | DTC TC-54 | LT AB Cable Laying+Charging | CAPEX | 14.1927/J-9011/17.12.2020 & 14.1927/J-9034/15.03.2021 |  | 01-09-2021 | 7th Main,2nd Cross |  |  | 10:00 | 17:00 | 7:00
56 | SOUTH | JAYANAGAR | S9 | PADMANABHA NAGAR | Padmanabhanagar | F09-Padmanabhanagar | DTC TC-75 | LT AB Cable Laying+Charging | CAPEX | 14.1927/J-9033/15.03.2021 & 14.1927/J-9012/17.12.2020 |  | 01-09-2021 | Indian Petrol bunk R.K.Layout |  |  | 10:00 | 17:00 | 7:00
57 | TUMKUR CIRCLE | TUMKUR DIVISION | TK1 | central section | Tumkur | Tumkur-1(TF-4) Tumkur3 TF5 | 11 KV feeder | conversion of overhead by UG cable | CAPEX | U-31623/25.9.2018 |  | 01-09-2021 | kotithopu road, belagumba road, N.R.colony, horpete road, FMc road, MG road N.r colony, Ashoka road k.R extn, BH road |  |  | 11:00 | 17:00 | 6:00 | full Feeder
58 | TUMKUR CIRCLE | TUMKUR DIVISION | TK2 | SARASWATHIPURAM | 66/11 KV Muss Tumkur | TF-1 Vijaya Nagara | 11 KV Feeder DTC 87 | Execution of the works of conversion of Overheads by UG cables for 11 kV Feeders, running new 11 kV UG cable for feeder load bifurcation, conversion of LT overhead line and service main by LT UG cables providing LT feeder piller boxes RMUs and other allied works and indicated in the tender documents in LOT-1 of Tumkur town of facilitating quality and reliable power supply on total turn key under percentage rate contract basis | CAPEX & Other Works | U-31643/20.11.18 |  | 01-09-2021 | BH Road,Siddaganga Extn.,Radha krishna road, SS Puram,M.C Colony, Raghavendra ITI, Municipal Layout, Dobhi Ghatt, CSI Layout, Gandhi Nagara, Town hall and Surrounding places. |  |  | 11:00 | 17:00 | 6:00 | 3C*400 sqmm HT UG cable charging
59 | TUMKUR CIRCLE | TUMKUR DIVISION | TK2 | Jayanagara | Baddihally | BF01, BF02, BF05, BF07 | 11 kv Branch line DTC 21 | 11KV TRUNK LINE JUNGLE CUTTING | Maintenance Work |  |  | 01-09-2021 | K.PALASANDRA, GULAHARIVE, KITTAGANAHALLY, SANKAPURA, SANKAPURA PALYA, MANCHAGONDANAHALLY, GOWRIPURA, D.N.PALYA |  |  | 11:00 | 14:00 | 3:00
60 | TUMKUR CIRCLE | TUMKUR DIVISION | TK2 | SARASWATHIPURAM | MELEKOTE | MF1, MF2,MF10, MF11, MF12, MF4,MF5,MF9,MF25 | 11 KV Feeder DTC 383 | Smart City Ring Road Pole Shifting Work | CAPEX & Other Works | Work Om No EE(ELE)/AEE/O/TA32019-2020/5670.72/20-08-2019 Work Om No EE(ELE)/AEE/O/TA32019-2020/4204-07/09-07-2019 Work Om No EE(ELE)/AEE/O/TA32019-2020/4200-03/09-07-2019 Work Om No EE(ELE)/AEE/O/TA32019-2020/4196.99/09-07-2019 Work Om No EE(ELE)/AEE/O/TA32019-2020/4196.99/09-07-2019 Work Om No EE(ELE)/AEE/O/TA32019-2020/4216.19/09-07-2030 |  | 01-09-2021 | Melekote, Gangasandra, Tuda layout, Danah Palace, UGD, Tippunagara, Nazarabadh, Veerasagara, Kuripalya, Goodshed, Shanthinagara, Upparahalli, Sadhashivanagara, Amarajyothi Nagara, Kumutaiah Badavane, Ramajoyes Nagara, Saraswathipuram 1ST and 2nd stage, Banashankari 1st and 2nd stage, Yadava Nagara, Maralooru, Maralooru Janatha Colony,Pragathi Badavane, Geddalahally, Gubbi Gate, Kuntammana Thota Dibburu,BH Palya, PH Colony, Vinoba Nagara, EdgaMohalla, Hegade Colony, Tilak Park, Jaipura, KHB Colony, bandimane Choutry |  |  | 7:12 | 17:30 | 10:18
61 | WEST | RR NAGAR | W7 | U-20 O&M 20- RAJARAJESHWARI NAGAR | RR Nagar | F-1 SACHIDANAND NAGAR | DTC 163 | Micro plan feeder | Maintenance Work |  |  | 01-09-2021 | BEML 5th Stage area |  |  | 10:00 | 13:00 | 3:00
62 | TUMKUR CIRCLE | TIPTUR DIVISION | CN1 | O&M-1 | CN HALLI_110/11 KV | F2 CN HALLI, F11 MUDDENAHALLI | 11 kv Branch line DTC 85 | Replacement of existing 11 Kv Over Head Line by 11 Kv Cover conductor at Varios Location on F2 C N Halli Feeder | Capex | C-57303/08.06.2021 |  | 01-09-2021 | CN HALLI TOWN, MUDDENAHALLI |  |  | 10:00 | 17:00 | 7:00
63 | WEST | RAJAJINAGAR | N8 | S G Kaval | Byadarahalli | F-08 | NA | Conversion from HT OH to HTUG Work | CAPEX | 2020/RN/14-1927/N-106361/12.01.2021 |  | 01-09-2021 | RHCS Layout, Annaporneshwari nagar, Health Layout, D Group Layout, Narasapura, Benachakal palya, Muddinapalya main road, Erana palya, Near reliance fresh gowramma Layout and sounding areas | 0 | 8450 | 10:30 | 17:30 | 7:00
64 | WEST | RAJAJINAGAR | N1 | 2nd BLOCK RAJAJI NAGAR | NRS | F1 | 2,19,40, | Estimate for conversion of LT Overhead line to LT AB Cable in F1 Feeder of NRS MUSS in O&M-2, N1 Sub-division | CAPEX | 2020/RN/14-1927/N-106242/24.09.2020 |  | 01-09-2021 | 1ST BLK | 3 | 1063 | 10:30 | 17:30 | 7:00
65 | TUMKUR CIRCLE | MADHUGIRI DIVISION | KR1 | O&M-1 | Koratagere 66/11kV | F05 Koratagere Town, F18 Urdagere Cross, F01, F03, F04, F09, F06, F07 | DTC 66 | For Providing Switch phase the Street light Control Switch in Koratagere Town limits in O&M-1 Section | CAPEX | R-34482/12.02.2021 |  | 01-09-2021 | Koratagere Town |  |  | 10:00 | 17:00 | 7:00
66 | TUMKUR CIRCLE | TIPTUR DIVISION | TU1 | o&m1 | Talkere | F01 Mangikuppe F02 Talkere F03 Ayarahalli F06 Honkere NJY | 11 KV Feeder | Link line from Donkihalli Bare to Donkihalli G hatti Gate to reduce the over load of F03 overload Feeder | Maintenance Work | B-21401 30.01.2021 |  | 01-09-2021 | Talkere, Donkihalli G Hatti, Donkihalli, D Kalkere, Ayarahalli, Doddaghoraghatta, Chikkaghorghatta, Siddanahatti, Aladevarahatti,Harikaranahalli. |  |  | 10:00 | 17:00 | 7:00
67 | TUMKUR CIRCLE | TIPTUR DIVISION | TU1 | o&m2 | Turuvekere Talkere | F05 Puttamadihalli F04 Anemale F03 Ayarahalli F06 Honkere NJY F17 Badarikashrama | 11 KV Feeder | Reconducting Of Existing F04 Anemale Feeder and Reconducting Of DTC's | Capex | B-37874 09.03.2021 |  | 01-09-2021 | Talkere, Donkihalli G Hatti, Donkihalli, D Kalkere, Ayarahalli, aralikere, sunklapura, dwaranahalli, anemale, mangikuppe |  |  | 10:00 | 17:00 | 7:00
68 | TUMKUR CIRCLE | TIPTUR DIVISION | TU1 | o&m2 | Turuvekere | F1 Mallagatta F3 Hemavathi F8 Anekere F13 Turuvekere F15 Gonitumkur F16 Court | 11 KV Feeder | Shifting Of Poles in Dabbeghatta Road due Road Widening | Maintenance Work |  |  | 01-09-2021 | Turuvekere town, Marasarakottige Mallaghatta, kodigehalli, T Hosahalli, Anekere, Kolghatta, Chikkaturuvekere, Guddenahalli, |  |  | 10:00 | 18:00 | 8:00
69 | DAVANAGERE CIRCLE | HIRIYUR DIVISION | HY1 | HARIYABBE | PD KOTE_66 | F05-HALAGALADDI NJY ,F02-PD-KOTE | 11 KV Feeder | Running 11 Kv Line from Pd ko T0 muss to hoskere limits | Maintenance Work |  |  | 01-09-2021 | maddihally,P.D.Kote,Kanajanahally,Benakanahally,hoskere |  |  | 10:00 | 17:00 | 7:00
70 | DAVANAGERE CIRCLE | HIRIYUR DIVISION | HY1 | HARIYABBE | PD KOTE_66 | F05-HALAGALADDI NJY ,F02-PD-KOTE | 11 KV Feeder | Running 11 Kv Line from Pd ko T0 muss to Benakanahally limits | Maintenance Work |  |  | 01-09-2021 | maddihally,P.D.Kote,Kanajanahally,Benakanahally,hoskere |  |  | 10:00 | 17:00 | 7:00
71 | WEST | RAJAJINAGAR | N6 | 1- KAMAKSHI PALYA | Vijayanagar | F7 | TC-21,20,13,22,28,26,29,33,34,37,38,39,172,173,184,220,231,253,281,283,294,300,301,304,662,664,756,804,863,839,886 | ESTIMATE FOR CONVERSION OF LT OVERHEAD LINE TO LT AB CABLE IN F -07 FEEDER OF VIJAYA NAGAR MUSS IN O&M-01 OF N6 SUB DIVISION | CAPEX | 4330-38/ 30.11.2020 |  | 01-09-2021 | MANIVILLA GARDEN , KAMAKSHIPALYA, VINAYAKA NAGARA, SHIVAFARM, SHIVA TEMPLE , ANDANAPPA LAYOUT, MARIYAPPA ROAD, KAMAKSHIPALYA |  | 6500 | 10:30 | 17:30 | 7:00 | Work will be taken up as schelduled from 1ST SEP 2021
72 | WEST | RAJAJINAGAR | N6 | 3 - SUNKADAKATTE | SRIGANDHA KAVALU | F-6 | TC-542,222,904, 295,744,352,375,353,N6HT-72, 869, 890, 929, N6HT-104, 134, 774, 302, N6HT-33, 133, 581, 581, 740,327, 328, 349,942,860, 135, 852, 228, 895, 831,946, 916, 735, 684, 131, 157, 302, N6HT33, 133,581, 740, 327,328,943,818,N6HT7, 938, 850,816, 342, 126,215, 125,343, 341, 893,54 | ESTIMATE FOR CONVERSION OF HT OVERHEAD LINE TO HT UG CABLE IN F -06 FEEDER OF SRIGANDHA KAVALU MUSS IN O&M-02 OF N6 SUB DIVISION | CAPEX | N-106352/ |  | 01-09-2021 | LAKSHMANA NAGARA, SANJEEVINI NAGARA, VIGNESHWARA NAGARA, HEGGANAHALLI, HEGGANAHALLI CROSS, SUNKADAKATTE, PIPELINE RAOAD SUNAKADAKATTE. |  | 4000 | 10:30 | 17:30 | 7:00 | Work will be taken up as schelduled from 1ST SEP 2021
73 | WEST | RAJAJINAGAR | N8 | S G Kaval | S G Kaval | F-10 | NA | Conversion from HT OH to HTUG Work | CAPEX | 2020/RN/14-1927/N-106330/02.11.2020 |  | 01-09-2021 | RHCS Layout, Annaporneshwari nagar, Health Layout, D Group Layout and sounding areas | 0 | 7860 | 10:30 | 17:30 | 7:00
74 | TUMKUR CIRCLE | MADHUGIRI DIVISION | SR1 | BARGURU | P D KOTE | F4 CHIRATHAHALLY & F10 laKKANAHALLI | SDP HT RECONDUCTING DTC 30 | For Relacement of 2/4 ACSR by Rabbit conductor for a distance of 1.8 Km 11KV line of F4 Chirathahallie Feeder, Chirathahalli to Hanmanthnagarai limit in Baragur Section CSD Sira | CAPEX | R-33041/18.02.2021 |  | 01-09-2021 | KARIDASARAHALLI & CHIRATHALLY |  |  | 12:00 | 18:00 | 6:00
75 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | KADABA | KADABA-110/11KV | F10-DASARAKALLAHALLI NJY ,F04 Honnashettyhally, F05 Bmallenahally, F7 Kadaba, F08 Byalahally | 11 KV Feeder DTC 74 | Bifercater load of F-10 Dasarakallahalli NJY Feeder to Reduce intereption to kadaba twonlimits in kadaba section nittur | Capex | Y-401 30.03.21 |  | 01-09-2021 | KADABA,K,RAMPURA,KOMMANAHALLI,BYADAGERE |  |  | 10:00 | 18:00 | 8:00 | DUE TO RAIN LC NOT AVAILED
76 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | KADABA | KGTEMPLE -110/11KV | F-12 Konnakere njy, F-2 suragenahally, f-5koppa, F-4 kunnala | 11 KV Feeder DTC 132 | For Replacing of Existing Detoriated 4 ACSR Conductor by Good Rabbit ACSR Conductor 11 KV HT Line From D Kunnala to Jeeganahalli Gollarahatti Village Limits of F4 Kunnala Feeder in Kadaba Section (DP- 06 No, 9 Mtr PSCC Pole 95 Nos Rabbit Wire-19.525 KM) | CAPEX | Y-24412/26.03.21 |  | 01-09-2021 | Koppa,kunnala,lingammanahally,konnemadanahally,konnakere,jeeganahally |  |  | 10:00 | 18:00 | 8:00 | DUE TO RAIN LC NOT AVAILED
77 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | KADABA | KGTEMPLE -110/11KV | F-12 Konnakere njy, F-2 suragenahally, f-5koppa, F-4 kunnala | 11 KV Feeder DTC 75 | For Providing Evacation of New 11 KV Link Line Konnakere to Konnanakere Village Limits to Biforcate Load From F5 B Mallenahalli Feeder From Kadaba Muss in Kadaba Section Nittur Sub Division (DP Set-10, 9Mt Pole-58 No, Rabbit Wire-7.605 KM) | Maintenance Work | Y-24371/26.03.21 |  | 01-09-2021 | Koppa,kunnala,lingammanahally,konnemadanahally,konnakere,jeeganahally |  |  | 10:00 | 18:00 | 8:00 | DUE TO RAIN LC NOT AVAILED
78 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | NITTUR | NITTUR220/110/11 KV | F16-SOPANAHALLI.F19-BOMMENAHALLI,F3-SAGAGARANAHALLI,F4-M.S.HALLI,F2-YALLAPURA,F5-HEMAVATHI,F6-THYAGATUR | 11 KV Feeder DTC 215 | For Providing Evacation of New 11 KV Link Line NITTUR MUSS to ADALAGERE PUMP HOUSE Village Limits to Biforcate Load From F3-SAGARANAHALLI FeederIN NITTUR Muss in NITTUR Section Nittur Sub Division (DP Set-10, 9Mt Pole-58 No, Rabbit Wire-7.605 KM) | Maintenance Work | Y-24373/26.3.21 |  | 01-09-2021 | SAGARANAHALLI,THYAGATUR,M.S.HALLI,YALLAPURA,BOMMENAHALLI,KUNDURANAHALLI. |  |  | 10:00 | 18:00 | 8:00
79 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | NITTUR | NITTUR220/110/11 KV | F15-NITTUR,F8-HESARAHALLI,F7-BENACHIGERE,F9-BELAVATHA | 11 KV Feeder DTC 183 | For replacement of existing 11 KV over head lines by 11 KV covered conductor from various locations in Nittur Section. | CAPEX | W-1243/18.3.2020 |  | 01-09-2021 | NITTUR,Mathighatta.HESARAHALLI |  |  | 10:00 | 18:00 | 8:00
80 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | KADABA | KADABA-110/11KV | F03-BELAVATHA, F013 thogarighatta, F11 Belavatha NJY | 11 KV Feeder DTC 84 | Kadaba Muss To Belavatha Village limits Biforcate Over loaded F-9 Belavatha Feeder | Capex | Y-402 31.03.21 |  | 01-09-2021 | ADAGONDANAHALLI , BELAVATHA,LAKSHMIPURA |  |  | 10:00 | 18:00 | 8:00 | DUE TO RAIN LC NOT AVAILED
81 | TUMKUR CIRCLE | TUMKUR DIVISION | YD1 | Yediyur | Yadiyur 66/11 | F-1 Siddalingeshwara Feeder | F-1 Siddalingeshwara Feeder DTC 10 | Estimate for Providing Continous power Supply 2KM Surrounding Yadiyuru Town Limits From F-1 Siddalingeshwara Feeder Feeding From Yadiyuru MUSS Pertaining to Yadiyuru Section Yadiyuru S/D. | CAPEX & Other Works | D-451/08.07.2021 |  | 01-09-2021 | Yadiyuru,Chakenahalli,Doddamadhure,Jaladhigere,Hemavathi,Beerganahalli |  |  | 10:00 | 17:00 | 7:00
82 | TUMKUR CIRCLE | TUMKUR DIVISION | YD1 | Yediyur | Yadiyur 66/11 | F-1 Siddalingeshwara Feeder | F-1 Siddalingeshwara Feeder DTC 12 | Estimate for Providing Continous power Supply 2KM Surrounding Yadiyuru Town Limits From F-1 Siddalingeshwara Feeder and Bifurcation of IP Sets Pertaining to Yadiyuru Section Yadiyuru S/D. | CAPEX & Other Works | D-452/08.07.2021 |  | 01-09-2021 | Yadiyuru,Chakenahalli,Doddamadhure,Jaladhigere,Hemavathi,Beerganahalli |  |  | 10:00 | 17:00 | 7:00
83 | DAVANAGERE CIRCLE | CHITRADURGA DIVISION | HD1 | O&M-1 | Hosadurga MUSS | F5 Kanthapura | 11 KV Feeder | GK Works | Maintenance Work |  |  | 01-09-2021 | Kathapura Areas |  |  | 12:00 | 16:00 | 4:00
84 | WEST | RAJAJINAGAR | N8 | Mallathahalli | Sir MV | F-01 | 340, 341 | Conversion of 11KV Overhead line into HT Ug Cable inFeeder F-01 (O&M Mallathahalli) N8 Sub Division,Rajaji nagar Division Bangalore West Circle, BMAZ (South), BESCOM under PHASE-I on Total turnkey under Rate Contract (RC.05) on Percentage basis quoting. | CAPEX | 2020/RN/14-1927/N-106255/02.11.2020 |  | 01-09-2021 | Railway Layout and surrounding areas | 0 | 350 | 10:30 | 17:30 | 7:00 | Works includes Srtinging of LT ab Cable one day and connecting servicing connections and load balancing one day