## 02-09-2021
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Schedule Interruptions for the month of September 2021
Details of works to avail Line Clear for CAPEX, RC, Service connection, OH to UG conversion, Self execution maintenance works
Sl No | Circle | Division | Sub Dvn | OM Unit | Station Name | Feeder No /Name | IF LT Work DTC code capacity | Nomenclature of Works | CAPEX/ Maintenance | Work order No and Date | Sanctioned Date | Date of LC planned | Areas affected | No: of consumers affected |  | Duration of LC required |  |  | Remarks (changeover arranged details) | Work Belongs to Station / BESCOM | LC Taken or Not (Yes / No) | Issue | Remarks | Station/Feeder charged time |  |  | Confirmed by BESCOM / KPTCL | Remarks (If time extended)
[14 empty] | HT consumers | LT consumers | from | To | Total interruption period in | [5 empty] | From | To | Total interruption period in
1 | RAMANAGARA | CHANDAPURA DIVISION | AT1 | Dommasandra | Dommasandra | F05-NERIGA, F09-CHAMBENAHALLI & F11-NIRANTHARA-JYOTHI |  | Tree trimming & 11 KV/LT jump replacement. GOS maintaminance, LT lead relacement, Jungle cutting | Maintenance Work |  |  | 02-09-2021 | Kuthganhalli,Kamanahalli,Chikkanahalli,Madapanahalli,Koogur,Banahalli |  |  | 0:00 | 48:00 | 48:00
2 | RAMANAGARA | CHANDAPURA DIVISION | AT1 | Dommasandra | Dommasandra | F02-DOMMASANDRA& F07-VAKIL-LAYOUT |  | Tree trimming & 11 KV/LT jump replacement. GOS maintaminance, LT lead relacement, Jungle cutting | Maintenance Work |  |  | 02-09-2021 | Dommasandra, Sompura gate, TISB school |  |  | 0:00 | 48:00 | 48:00
3 | RAMANAGARA | CHANDAPURA DIVISION | AT1 | Mayasandra | Chandapura | F11 Vakil layout |  | Tree trimming & 11 KV/LT jump replacement. GOS maintaminance, LT lead relacement, Jungle cutting | Maintenance Work |  |  | 02-09-2021 | Bandapura, M Madivala, Halehuru, Adisonnahatti,M agrahara, Aishwarya layout 1 &2, Trove layout, |  |  | 0:00 | 48:00 | 48:00
4 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | BP1 | CHELLUR | CHELURU | F1 CHELURU | 11 kv Branch line | Gopalreddy S/o Venkataravanappa,Cheluru. | Maintenance Work | T-26214/ 06.07.2021 |  | 02-09-2021 | Pemmaihagaripalli,Byrapanapalli,Sherkhankote,Gangireddypalya,Pathur,Cheluru,Hosahudya, |  |  | 12:00 | 14:00 | 2:00
5 | NORTH | MALLESHWARAM | C1 | Rajajinagar 2ndstage | NRS | F09 Nandhini | DTC213 214 | LT AB Cable | CAPEX |  |  | 02-09-2021 | ROBERTSON BLOCK, R.C.PURA 1ST MAIN ROAD. |  |  | 10:00 | 17:00 | 7:00
6 | NORTH | MALLESHWARAM | C1 | Prakash nagar | NRS | F4-DEVAIAH PARK | DTC435 | Maintenance | Maintenance Work |  |  | 02-09-2021 | 11TH ,12TH , 13, 14 TH MAIN GAYATHRINAGAR |  |  | 10:00 | 14:00 | 4:00
7 | NORTH | MALLESHWARAM | C1 | Prakash nagar | NRS | F-11 PRAKASH NAGAR | DTC411 | Maintenance | Maintenance Work |  |  | 02-09-2021 | AD BLOCK |  |  | 10:00 | 12:00 | 2:00
8 | NORTH | JALAHALLI | c3 | Jalahally | Gokul | F1-Gangamma Circle | Maintenance DTC 2221 | 11 KV Maintenance | Maintenance Work |  |  | 02-09-2021 | Muneshwaraswamy layout |  |  | 13:00 | 14:00 | 1:00
9 | NORTH | HEBBAL | C5 | Kavalbyrasandra | LR Bande | F12-V-NAGENAHALLI | 11 KV FeederAll Dtcs | tree trimming and gos maintenance | Maintenance Work |  |  | 02-09-2021 | V Nagenahalli, C N Halli. |  |  | 11:00 | 13:00 | 2:00
10 | NORTH | HEBBAL | C5 | Kavalbyrasandra | LR Bande | F14-MODI-ROAD | 11 KV FeederAll Dtcs | tree trimming and gos maintenance | Maintenance Work |  |  | 02-09-2021 | D J Halli, Modi road, Modi Market. Hanifa masjid Road. |  |  | 11:00 | 13:00 | 2:00
11 | NORTH | MALLESHWARAM | C6 | Mathikere | RMV | F4 & F8 | 11 KV Feeder DTC TC 22, TC 26, TC 281, TC 24, TC 56, TC 371, HT 11, Tc 285 | Overhead to UG Works | CAPEX |  |  | 02-09-2021 | New BEL Road |  |  | 10:30 | 18:00 | 7:30
12 | NORTH | HEBBAL | C7 | new town | Attur | F09 | 11 kv Branch line DTC 303, 304, 674, 139 & 138. | Convertion of Existing OH to UG cable of F9 feeder of Yelahanka MUSS. | CAPEX |  |  | 02-09-2021 | 22 & 23rd cross Judicial Layout |  |  | 10:00 | 17:00 | 7:00
13 | NORTH | HEBBAL | C7 | Yelahanka new town | ATTUR | F6 | 11 KV FeederDTC-403, DTC-389,DTC-591,DTC-658,DTC-567 | Conversion of 11KV OH to UG Line for F6 ( Yelakhanka Muss) Maruthi Nagar BLR- Feeder in Yelahanka New Town O&M 19 of C7 Sub Division, Hebbal Division | CAPEX |  |  | 02-09-2021 | Sheshasdripuram College Road |  |  | 10:00 | 17:00 | 7:00
14 | NORTH | HEBBAL | C7 | Yelahanka new town | KHB | F5 | 11 KV Feeder DTC Doddabellapur Main Road | Estimate for Conversion of Existing11 KV HT OverHead Line into HT UG cable pertaining to F-5 Feeder KHB MUSS, Feeding to different locations of C-7 Sub-division ,under Phase-II on total Turnkey Basis Under RC-10. | CAPEX |  |  | 02-09-2021 | Doddabellapur Main Road |  |  | 10:00 | 17:00 | 7:00
15 | NORTH | HEBBAL | C7 | Yelahanka old town | ATTUR | F10 | 11 kv Branch line DTC Masjid/Chowdeshwari kalyanamantapa Road | Conversion of 11KV OH to UG Line for F10 ( Yelakhanka Muss) IAF BLR- Feeder in Yelahanka Old Town O&M 19A of C7 Sub Division, Hebbal Division | CAPEX |  |  | 02-09-2021 | Masjid/Chowdeshwari kalyanamantapa Road |  |  | 10:00 | 17:00 | 7:00
16 | NORTH | HEBBAL | C7 | Yelahanka old town | PUTTENAHALLI | F13 | 11 kv Branch line DTC TC 470, SPTC 1, HT 677, HT 266 | Conversion of 11KV OH to UG Line for F13 ( Puttenahalli Muss) Venkatala BLR Feeder in Yelahanka Old Town O&M 19A of C7 Sub Division, Hebbal Division | CAPEX |  |  | 02-09-2021 | Bagalur Main Road |  |  | 10:00 | 17:00 | 7:00
17 | NORTH | HEBBAL | C7 | Yelahanka old town | PUTTENAHALLI | F12 | 11 kv Branch line DTC TC 418, TC 555, TC 58, HT NEW, HT 224, HT 718, 719, | Conversion of 11KV OH to UG Line for F12 ( Puttenahalli Muss) MARUTHI NAGAR BLR Feeder in Yelahanka Old Town O&M 19A of C7 Sub Division, Hebbal Division | CAPEX |  |  | 02-09-2021 | Kogilu Main Road from Andhra Bank to Prakruthi Nagar |  |  | 10:00 | 17:00 | 7:00
18 | NORTH | HEBBAL | C8 | Sahakar nagar | SKN | F3 | 11 kv Branch lineAll Dtcs | OH to UG | CAPEX |  |  | 02-09-2021 | AMRUTH NAGAR, JAKKUR CIRCLE |  |  | 9:00 | 17:00 | 8:00
19 | NORTH | HEBBAL | C8 | Sahakar nagar | SKN | F12 | 11 kv Branch lineAll Dtcs | OH to UG | CAPEX |  |  | 02-09-2021 | SAHAKARANAGAR C BLOCK |  |  | 9:00 | 17:00 | 8:00
20 | NORTH | HEBBAL | C8 | Sahakar nagar | SKN | F11 | 11 kv Branch lineAll Dtcs | OH to UG | CAPEX |  |  | 02-09-2021 | SAHAKARANAGAR B BLOCK |  |  | 9:00 | 17:00 | 8:00
21 | NORTH | HEBBAL | C8 | Sahakar nagar | SKN | F8 | 11 kv Branch lineAll Dtcs | OH to UG | CAPEX |  |  | 02-09-2021 | G K V K |  |  | 9:00 | 17:00 | 8:00
22 | NORTH | HEBBAL | C8 | Sahakar nagar | SKN | F20 | 11 kv Branch lineAll Dtcs | OH to UG | CAPEX |  |  | 02-09-2021 | THIRUMENAHALLI VILLAGE, KOGILU |  |  | 9:00 | 17:00 | 8:00
23 | NORTH | HEBBAL | C8 | JAKKUR | SKN | F20 | 11 kv Branch line DTC 858182498 | CONVERTION OH/UG | CAPEX |  |  | 02-09-2021 | JAKKUR |  |  | 10:00 | 17:00 | 7:00
24 | NORTH | HEBBAL | C8 | JAKKUR | SKN | F14 | 11 kv Branch line DTC 87,732, | CONVERTION OH/UG | CAPEX |  |  | 02-09-2021 | SAMPIGEHALLI |  |  | 10:00 | 17:00 | 7:00
25 | NORTH | HEBBAL | C8 | JAKKUR | SKN | F21 | 11 kv Branch line DTC 108476217 | CONVERTION OH/UG | CAPEX |  |  | 02-09-2021 | AGRAHARA LAYOUT |  |  | 10:00 | 17:00 | 7:00
26 | NORTH | HEBBAL | C8 | JAKKUR | shoba | F3 | 11 kv Branch line DTC 8380802803 | CONVERTION OH/UG | CAPEX |  |  | 02-09-2021 | CHOKKANAHALLI |  |  | 10:00 | 17:00 | 7:00
27 | NORTH | HEBBAL | C8 | JAKKUR | shoba | F11 | 11 kv Branch line DTC 538100390 | CONVERTION OH/UG | CAPEX |  |  | 02-09-2021 | THIRUMENAHALLI |  |  | 10:00 | 17:00 | 7:00
28 | NORTH | HEBBAL | C8 | JAKKUR | shoba | F10 | 11 kv Branch line DTC 690657352353 | CONVERTION OH/UG | CAPEX |  |  | 02-09-2021 | HEGDENAGARA |  |  | 10:00 | 17:00 | 7:00
29 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | CB2 | NANDI | Cbpura I/A MUSS | F1-Muddenahalli, F16-Kanganahalli | full line | Estimat for APS to Irrigation pump set installation in the name of Krishnappa S/o Suddappa, Sy no:47 at Suddahalli Village in Nandi section RSD CBPUR | CAPEX & Other Works | OM No:-1706-08 dtd:-19-07-2021 |  | 02-09-2021 | All villages of F1 and F16 |  |  | 10:00 | 15:00 | 5:00
30 | DAVANAGERE CIRCLE | CHITRADURGA DIVISION | CD2 | Hiregutanur | HIREGUNTANUR_66 | F12Hosahalli NJY | 11 KV Feeder | Maintenance work | Maintenance Work |  |  | 02-09-2021 | Hireguntanuru,Hireguntanuru Gollarahatti,Rattihalli, |  |  | 13:00 | 15:00 | 2:00
31 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | CG1 | O&M1 | TAVAREKERE_66 | F06-MASANIKERE NJY | 11 KV Feeder | Maintenance work | Maintenance Work | - |  | 02-09-2021 | MASANIKERE, GANGAGONDANAHALLI, MALLESHWARA, HANUMALAPURA, KALKERE, JAMMAPURA, BEEDUGONDANAHALLI SANNATHANDA |  |  | 10:00 | 17:00 | 7:00
32 | RAMANAGARA | CHANDAPURA DIVISION | CH1 | Bommasandra | Jigani | F47 Vakil Layout |  | Tree trimming, Maintenance of GOS, loose span restrining, Bent pole straightening | Maintenance Work |  |  | 02-09-2021 | Srirampura, Vakil Encasa |  |  | 10:00 | 12:00 | 2:00
33 | RAMANAGARA | CHANDAPURA DIVISION | CH1 | Bommasandra | Jigani | F47 Vakil Layout |  | Tree trimming, Maintenance of GOS, loose span restrining, Bent pole straightening | Maintenance Work |  |  | 02-09-2021 | Srirampura, Vakil Encasa |  |  | 10:00 | 12:00 | 2:00
34 | RAMANAGARA | CHANDAPURA DIVISION | CH1 | Bommasandra | Yarandahalli | F21 R K Town ship |  | Tree trimming, Maintenance of GOS, loose span restrining, Bent pole straightening | Maintenance Work |  |  | 02-09-2021 | Yarandhalli Village , R K Township |  |  | 10:00 | 12:00 | 2:00
35 | RAMANAGARA | CHANDAPURA DIVISION | CH1 | Chandapura | Chandapura | F1- Marsoor |  | Tree trimming, Maintenance of GOS, loose span restrining, Bent pole straightening | Maintenance Work |  |  | 02-09-2021 | Marsoor, Iggaluru Village , Madiwala |  |  | 10:00 | 12:00 | 2:00
36 | RAMANAGARA | CHANDAPURA DIVISION | CH1 | Surya City | Surya Nagar | F2-Surya Nagar Ph2 |  | Tree trimming, Maintenance of GOS, loose span restrining, Bent pole straightening | Maintenance Work |  |  | 02-09-2021 | Suryanagara 2nd Phase |  |  | 10:00 | 12:00 | 2:00
37 | RAMANAGARA | CHANDAPURA DIVISION | CH1 | Chandapura | Surya Nagar | F4 Division Office Road |  | Tree trimming, Maintenance of GOS, loose span restrining, Bent pole straightening | Maintenance Work |  |  | 02-09-2021 | Division Office Road , Suryacity Ph-1 |  |  | 10:00 | 12:00 | 2:00
38 | RAMANAGARA | RAMANAGARA DIVISION | CP1 | O&M -III | 66/11 KVMUSS ,Sankalagere | F3 KOLURU NJY |  | For preventive maintainance of HT and LT lines & DTCs | Maintenance Work |  |  | 02-09-2021 | Hosurudoddi, devarahalli, valageredoddi, byrapatnadoddi, anigere, seebanahalli, mudagere, koluru |  |  | 10:00 | 15:00 | 5:00
39 | RAMANAGARA | RAMANAGARA DIVISION | CP2 | Saraguru | AKKUR | F-15 VYDYANATHESWARA |  | MAINTENANCE | Maintenance Work |  |  | 02-09-2021 | NERALURU |  |  | 12:00 | 14:00 | 2:00
40 | BRC | HOSAKOTE | DH1 | Budigere | Budigere | F-3 Nallur | 11KV Feeder | Maintance work with Jungle trimming | Maintenance Work |  |  | 02-09-2021 | nallu. Jonahalli .reddihalli kaggalahalli nagenahalli |  |  | 12:00 | 15:00 | 3:00
41 | BRC | HOSAKOTE | DH1 | Avathi | 66/11KV DEVANAHALLI | F26 GOBBARAGUNTE | 11 KV Feeder | VIILLAGE DTC RE PUBLISHMENT,JUNGLE CUTING AND LINE MAINTAINCE | Maintenance Work |  |  | 02-09-2021 | GUDAVANAHALLI,GOBBARAGUNTE, KORMANGALA |  |  | 10:00 | 12:00 | 2:00
42 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | DV1 | O&M - 4 | DAVANAGERE_66 | F02-MCCB | 11 KV Feeder | SHIFTING OF HT/LT LINE CONDUCTOR AND PROVIDING INTERMMIDIATE POLE | Maintenance Work | - |  | 02-09-2021 | SHAMANUR ROAD |  |  | 10:00 | 16:00 | 6:00
43 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | DV1 | O&M - 3 | DAVANGERE_SRS_220 | F15-RANGANATHA | 11 KV Feeder | Suez work | Maintenance Work | - |  | 02-09-2021 | Vidyanagara, Tharabalu Badavane |  |  | 10:00 | 17:00 | 7:00
44 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | DV1 | O&M - 6 | 66/11 KV MUSS DVG | F-12 BASAVESHWARA | 11 KV Feeder | PURPOSE PRELEFT FOOT BATH CONCREATING SMART CITY WORK OPPOSSITE SUKSHEMA HOSPITAL | CAPEX & Other Works | - |  | 02-09-2021 | SS LAYOUT A &B BLOCK SHANTHI NAGAR KUNDAVADA ROAD WATER WORKS CMC BASAVESHWARA LAYOUT MAHALAKSHMI LAYOUT BALAJI NAGAR KUNDAVADA LAKE |  |  | 10:00 | 17:00 | 7:00
45 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | DV1 | O&M - 6 | 66/11 KV MUSS DVG | F-12 BASAVESHWARA | 11 KV Feeder | PIPE LINE 24X7 WATER SUPPLY JALASIRI WORK NETAJI STADIUM ROAD SS LAYOUT A BLOCK PIPE LYING ROAD CROSS | Maintenance Work | - |  | 02-09-2021 | SS LAYOUT A &B BLOCK SHANTHI NAGAR KUNDAVADA ROAD WATER WORKS CMC BASAVESHWARA LAYOUT MAHALAKSHMI LAYOUT BALAJI NAGAR KUNDAVADA LAKE |  |  | 10:00 | 17:00 | 7:00
46 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | DV1 | O&M - 6 | 66/11 KV MUSS DVG | F-12 BASAVESHWARA | 11 KV Feeder | PIPE LINE 24X7 WATER SUPPLY JALASIRI WORK LAKSHMI FLOOR TO CHURCH ROAD | Maintenance Work | - |  | 02-09-2021 | SS LAYOUT A &B BLOCK SHANTHI NAGAR KUNDAVADA ROAD WATER WORKS CMC BASAVESHWARA LAYOUT MAHALAKSHMI LAYOUT BALAJI NAGAR KUNDAVADA LAKE |  |  | 10:00 | 17:00 | 7:00
47 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | DV1 | O&M - 6 | 66/11 KV MUSS DVG | F-12 BASAVESHWARA | 11 KV Feeder | PIPE LINE 24X7 WATER SUPPLY JALASIRI WORK GAP CLOSING AND INTERLINKING WORK | Maintenance Work | - |  | 02-09-2021 | SS LAYOUT A &B BLOCK SHANTHI NAGAR KUNDAVADA ROAD WATER WORKS CMC BASAVESHWARA LAYOUT MAHALAKSHMI LAYOUT BALAJI NAGAR KUNDAVADA LAKE |  |  | 10:00 | 17:00 | 7:00
48 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | DV1 | O&M - 4 | DAVANAGERE_66 | F02-MCCB | 11 KV Feeder | FREE LEFT PURPOSE FOOT PATH CONCRETING WORK | Maintenance Work | - |  | 02-09-2021 | SHAMANUR ROAD |  |  | 10:00 | 16:00 | 6:00
49 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | DV3 | O&M - 1 | SRS DAVANAGERE_220 | F21-NJ TARALABALU | 11 KV Feeder | Maintenance of Microplan feeder | Maintenance Work | - |  | 02-09-2021 | Shiramagondanahalli, Naganur, NK badavane, 6th & 7th Mile stone, Bisleri, Banashankari Badavane 2nd stage |  |  | 10:00 | 18:00 | 8:00
50 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | DV3 | Elebethur | Kadajji_66 | F04-Sriram | LT Line with DTC No | Maintenance of Microplan feeder-jungle clearance, DTC Meter shifting | Maintenance Work | - |  | 02-09-2021 | Kadajji, Putuganal, Bethur, Basavanal, Rampura |  |  | 10:00 | 16:00 | 6:00
51 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | DV3 | Elebethur | Obajjihalli_66 | F05-Watersupply | LT Line with DTC No | Maintenance of feeder-jungle clearance | Maintenance Work | - |  | 02-09-2021 | Obajjihalli, Arasapura, Kadlebalu, Maganahalli, Badinayakana Tanda |  |  | 10:00 | 16:00 | 6:00
52 | EAST | INDIRANAGAR | E10 | KGP | NGEF S/S | F2 NGEF/F17 BTP | 11 kv Branch line DTC 619, 10th Cross TC, 13th Cross TC, 8th Cross TC | Dismantling | CAPEX | 405/20/OH to UG/IND/14-192/G-1015 |  | 02-09-2021 | 7th A Cross,10th Cross, Abbya reddy layout Main road, Railway Compound |  |  | 10:00 | 16:00 | 6:00 | Part Feeder
53 | EAST | INDIRANAGAR | E11 | Akshay Nagar | ITI | F1 RMNagar | 11 kv Branch Line 1.Proposed 5 Way Das RMU Near KRISHNA SAGAR VL-01 to PRAKASH HOUSE FDCT-452 250KVA. 2.PRAKASH HOUSE FDCT-452 250KVA to New Appt SDTC 100 KVA. 3.New Appt SDTC 100 KVA to Brlliant public School FDTC 451 A250 KVA | GOS & 95 Sqmm Charging | CAPEX |  |  | 02-09-2021 | SR HOMES |  |  | 10:00 | 16:00 | 6:00
54 | EAST | SHIVAJINAGAR | E5 | Lingarajapura | HBR | F11 | 7 | HT UG cable raising and structure work uinder OH to UG conversion project | CAPEX | G-45746 |  | 02-09-2021 | Kachakaranahalli Village |  |  | 10:00 | 17:00 | 7:00 | -
55 | EAST | INDIRANAGAR | E6 | JBN | HAL S/S | F6 HAL | 11 kv Branch line TC 690, 657,Hanumantha TC, Masnjunath temple TC | Dismantling | CAPEX | 405/20/OH to UG/IND/14-192/G-1022 |  | 02-09-2021 | NR Colony |  |  | 10:00 | 16:00 | 6:00
56 | EAST | SHIVAJINAGAR | E8 | BW-1 | Banasawadi | F13-OMBR | Dtc No 500 | arranging power supply to an extent of 34 Kw in Favour of Munni Reddy | CAPEX & Other Works | 970509 /04.08.2021 |  | 02-09-2021 | B Chansandra |  |  | 11:00 | 14:00 | 3:00 | -
57 | EAST | SHIVAJINAGAR | E9 | Kothanur | Geddalahalli | F-07 | TC - 21 | OH to UG Conversion | CAPEX | 1627944 & 01.04.2021 |  | 02-09-2021 | AVALAHALLI MAIN ROAD |  |  | 0:00 | 120:00 | 120:00 | -
58 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | GB1 | O&M-2 | Gowribidanuru 220/66/11 | F15-NJY-ALAKAPURA | 11 KV Feeder DTC 87 | GOS Maintainance,Jungle cutting& LOOSE SPAN Restringing & DTC Mainatanace | Maintenance Work |  |  | 02-09-2021 | Alakapura , Idaguru, hanumenahalli , beemanahalli, balagere husenapaura , hanumenahalli |  |  | 14:00 | 16:00 | 2:00
59 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | GB1 | ALIPURA | Thondebavi 66/11 | F11-NJY-BEVINAHALLI | 11 KV Feeder DTC 163 | GOS Maintainance,Jungle cutting& LOOSE SPAN Restringing | Maintenance Work |  |  | 02-09-2021 | bevinahalli, allipura dodda mallakere, kamaganahalli, veerammanhalli , maratipalya , veerammanahalli , taridalu |  |  | 14:00 | 16:00 | 2:00
60 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | GD1 | GUDIBANDE | Gudibande_66 | F01-Hampasandra | 11 KV Feeder DTC 171 | GOS Maintainance,Jungle cutting | Maintenance Work |  |  | 02-09-2021 | Garaducharlahalli,Hampasandra,UpparahalliKodavalahalli,Kondareddyhalli,Machahalli,Pasupalodu,Lakkenahalli |  |  | 9:00 | 12:00 | 3:00
61 | RAMANAGARA | KANAKAPURA DIVISION | HA1 | JAKKASANDRA | HANUMANTHANAGARA | F05 HANUMANTHANAGARA |  | JUNGLE CLEARNCE | Maintenance Work |  |  | 02-09-2021 | CHILLUR PANCHAYATHI |  |  | 11:00 | 16:00 | 5:00
62 | BRC | HOSAKOTE | HK1 | Devanagundi | DEVANAGUNDI_66 | F01 K.AGRAHARA , F2 SHIVANAPURA AND F03 | 11 KV Feeder | 11KV LINE SHIFTING WORK | Maintenance Work |  |  | 02-09-2021 | F01 K.AGRAHARA , F2 SHIVANAPURA AND F03 K AREHALLI ALL THESE 3 FEEDERS WILL BE UNDER THIS LC WORK. Doddadunnasandra Cross |  |  | 10:00 | 16:00 | 6:00
63 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | JL1 | Pallagatte | Pallagatte_66 | F09-Ayyanahalli | 11 KV Feeder | Maintenance work | Maintenance Work | - |  | 02-09-2021 | Tarehalli, gode, goddadalinganahalli, mustugarahalli, miniragahalli, iyyanahalli, basavapura, chennapura, kodadagudda, suraddihalli, palanayakanakote, kallenahalli, suragondahalli, palanayakanakote, kallenahalli, medakeranahlli and suragondahalli hosuru |  |  | 10:00 | 18:00 | 8:00
64 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | JL1 | O&M - 2 | HM Hole_66 | F11-Sangenahalli | 11 KV Feeder | Maintenance work | Maintenance Work | - |  | 02-09-2021 | Kalledevapura, basappanahatti, sangenahalli, gowrammanahalli, donnehalli, bennehalli, akanuru, subhash nagara, hosahatti, mudlamachikere, siddihalli, musturu and mudalamachikere |  |  | 10:00 | 15:00 | 5:00
65 | RAMANAGARA | CHANDAPURA DIVISION | JN1 | Jigani | 66/11KV Jigani | F06 Vabasandra |  | GOS Maintanance works and tree trimming works | Maintenance Work |  |  | 02-09-2021 | Kyalasanahalli,Bndenallasandra |  |  | 10:00 | 14:00 | 4:00
66 | WEST | KENGERI | K1 | Kumbalagudu | HEJJALA_66 | F11-KHB HAMPAPURA-1 | DTC DT-01,02. | TREE TRIMMING | Maintenance Work |  |  | 02-09-2021 | HAMPAPURA VILLAGE KHB LAYOUT |  |  | 10:00 | 12:00 | 2:00
67 | WEST | KENGERI | K1 | Kengeri | RR Nagara | F10 | Spur Line | Estimate for Conversion of HT Overhead to HT UG Cable for F10 Feeder Global Village Feeder emanating from RR Nagara MUSS in O&M U-22 kengeri of K1 Sub Dvn, Kengeri Dvn. Under (RC 14) Total turnkey basis | CAPEX | I-15018 I-15218 I-15318 |  | 02-09-2021 | Bhoomika Layout,Patangiri, BHEL Layout |  |  | 9:00 | 17:00 | 8:00
68 | WEST | KENGERI | K1 | Ramohalli | Bandemutt Station | F5 - Hunasemaradapalya | DTC DT-368 | Tree trimming, DTC maintenance | Maintenance Work |  |  | 02-09-2021 | Aralimara TC_Challeghatta |  |  | 10:30 | 12:30 | 2:00
69 | WEST | KENGERI | K2 | Andrahalli | NG Halli | F-6 -HT | Full Feeder TC-88,16,161,80 | Estimate for conversion of 11KV OH Line to HT UG Cable of F6 feeder from NG Halli muss in Andrahalli O&M-2, K2 Sub divin, Kengeri Divin, Bangalore. | CAPEX | I-15418 I-15618 I-15718 ,DT:25-02-2021 |  | 02-09-2021 | Andhrahalli Govt School,Andhrahalli circle |  |  | 10:00 | 17:00 | 7:00
70 | WEST | KENGERI | K2 | Andrahalli | NG Halli | F-7-LT | Spur Line TC-123,172&166 | Estimate for conversion of LT OH to LT AB Cable of F07 feeder from NG Halli muss in Andrahalli O&M-2, K2 Sub divin, Kengeri Divin, Bangalore-91 | CAPEX | I-15407 I-15707 I-15607 Dt:13-01-2021 |  | 02-09-2021 | T.G. PALYA GOV.SCHOOL |  |  | 10:00 | 17:00 | 7:00
71 | WEST | KENGERI | K2 | Herohalli | Byadarahalli | F-3 -LT | Spur Line TC-270,TC-52 | Estimate for conversion of LT OH to LT AB Cable of F3 feeder from Byadarahalli muss in Herohalli O&M-1, K2 Sub divin, Kengeri Divin, Bangalore-91 | CAPEX | I-15404 I-15704 I-15604 ,DT:13-01-2021 |  | 02-09-2021 | Hosahalli |  |  | 10:00 | 17:00 | 7:00
72 | WEST | KENGERI | K4 | KST | SIR MV | F15 | Spur Line | Estimate for Conversion of HT Overhead to HT UG Cable forF15 Feeder KHB PLATINUM FEEDER, SIR M V MUSS, inO&M U21 K4 Sub Dvn, Kengeri Dvn.RC 14 | CAPEX | I-15025 I-15225 I-15325 Dt:22.02.2021 |  | 02-09-2021 | Gandi Nagar |  |  | 9:00 | 17:00 | 8:00
73 | WEST | KENGERI | K4 | RR Layout | SIR MV | F3 | Spur Line | Estimate prepared for convertion of OH to HT UG Cable for F3Feeder Dubasipalya of Sir M V MUSS in O&M-24 RRLayoutof K-4 Subdivison Nagadevanhalli Bangalore-56 | CAPEX | I-15032 I-15232 I-15332 Dt:25.02.2021 |  | 02-09-2021 | Dubasipally, Medsole Hospital Road |  |  | 9:00 | 17:00 | 8:00
74 | KOLAR CIRCLE | KGF DIVISION | KG1 | ROBERTSONPET-2 | Andersonpet | MF-10.f-9 | 11 KV Feeder | Est for APS to lgt. Inst. Of 15 HP of Smt. Naryanamma w/o chandrappa at Adampalli in R Pet-2 kgf s/d | CAPEX & Other Works |  |  | 02-09-2021 | Krishnavaram,Mallampalli,adampalli,gorlchinahalli |  |  | 10:00 | 11:00 | 1:00
75 | TUMKUR CIRCLE | MADHUGIRI DIVISION | KH1 | O&M-1 | Kodigenahalli | F03 Kodigenahally | DTC 23 | For replacement of existing 11 KV overhead lines by 11 KV Covered condcutor from Cremation tapping pole to Eshwara temple 63 KVA TC in O&M-1 | CAPEX | S-5561 |  | 02-09-2021 | Kodigenahalli |  |  | 10:00 | 17:00 | 7:00
76 | RAMANAGARA | KANAKAPURA DIVISION | KP1 | O&M-3 | V R Doddy_66 | F5-Somedyapanahalli |  | Maintenance | Maintenance Work |  |  | 02-09-2021 | Murukani,Somedyapanahalli,Belikottanuru,H kottanuru |  |  | 10:00 | 11:30 | 1:30
77 | TUMKUR CIRCLE | TUMKUR DIVISION | KYT | KYATHSANDRA | 66/11kV MUSS Hirehalli | HF-10 SS Mutt & HF-09 M N PALYA | 11 KV Feeder | For replacement of existing 11 KV overhead lines by 11 KV Covered condcutor in Kyathsandra Section | Maintenance Work |  |  | 02-09-2021 | Siddaganga Mutt, Karekal Palya, B M Palya, Basavapatna, Basaveshwara Extn, Joss Toll |  |  | 10:00 | 18:00 | 8:00
78 | KOLAR CIRCLE | KGF DIVISION | MB1 | M N HALLY | Mulbagal | MF14, MF17, MF13 | 11 kv Branch line DTC 5 | For Shifting of HT/LT Line passing due to NH234 road widening from Machanahalli cross to Chapurahalli kere limits on request of Executive Engineer Project Sub-dvn KRRDA. AND MAINTAINANCE WORKS | Maintenance Work |  |  | 02-09-2021 | ALANGUR, SONNAVADI, MN HALLI, TR HALLI. |  |  | 10:00 | 16:00 | 6:00
79 | KOLAR CIRCLE | KGF DIVISION | MB1 | AVANI | AVANI | AF2, AF3 | 11 KV Feeder DTC 98 | 11 KV LINES R&M | Maintenance Work |  |  | 02-09-2021 | DEVARAYASAMUDRA, KR CIRCLE, |  |  | 11:00 | 12:00 | 1:00
80 | KOLAR CIRCLE | KGF DIVISION | MB1 | NANGLI | nagali | F10 | 11 KV Feeder DTC 42 | for shifting of 11kv line at nagali town | Maintenance Work |  |  | 02-09-2021 | nagali town |  |  | 11:30 | 12:30 | 1:00
81 | KOLAR CIRCLE | KGF DIVISION | MB1 | O&M1 | Mulbagal | F15-TOWN | 11 KV Feeder DTC 140 | FOR 21KW MSB INSTALLATION OF VENKATARAVANAPPA BUSALAKUNTE. | Maintenance Work |  |  | 02-09-2021 | Amarajyothi School surrounding,mulbagal town |  |  | 11:00 | 11:30 | 0:30
82 | KOLAR CIRCLE | KGF DIVISION | MB1 | THAYLUR | Thaylur | F4, F6,F9 | 11 KV Feeder DTC 90 | 11 KV LINES R&M | Maintenance Work |  |  | 02-09-2021 | THAYALUR, EMMENTHA. |  |  | 11:00 | 12:00 | 1:00
83 | KOLAR CIRCLE | KGF DIVISION | MB1 | O&M2 | H.Gollahalli | F2,F3,F4,F9 | 11 KV Feeder DTC 90 | For Shifting of HT/LT Line passing due to Ambedkar Bhavana on REQUEST OF RAMESH Siddaghatta AND MAINTAINANCE WORKS | Maintenance Work |  |  | 02-09-2021 | vammasandra lingapura area |  |  | 11:00 | 12:00 | 1:00
84 | KOLAR CIRCLE | KGF DIVISION | ML1 | LAKKUR | lakkur | F-09 anikarahalli | 11 kv Branch line | Est for APS to 15HP Rose Green house in the name of Sri.Venkatesh S/o Muiyappa at Vappachalli in Lakkur Sec. | CAPEX & Other Works |  |  | 02-09-2021 | vapachahalli |  |  | 10:00 | 11:00 | 1:00
85 | WEST | RAJAJINAGAR | N3 | INDUSTRIAL TOWN | NRS | F3 | 366 | HT UG CABLE | CAPEX | P-113455 |  | 02-09-2021 | WARD NO 107- Shivanahalli, ,8th main, | 1 | 215 | 10:00 | 17:30 | 7:30
86 | WEST | RAJAJINAGAR | N3 | 10 | NRS | F3 | 444 | HT UG CABLE | CAPEX | P-113455 |  | 02-09-2021 | WARD NO 107- Shivanahalli, ,8th main, | 0 | 254 | 10:00 | 17:30 | 7:30
87 | WEST | RAJAJINAGAR | N3 | 11 | NRS | F5 | 517 | HT UG CABLE | CAPEX | P-113455 |  | 02-09-2021 | WARD NO 107- Shivanahalli, ,8th main, | 0 | 256 | 10:00 | 17:30 | 7:30
88 | WEST | RAJAJINAGAR | N3 | 12 | NRS | F6 | 36 | HT UG CABLE | CAPEX | P-113455 |  | 02-09-2021 | WARD NO 107- Shivanahalli, ,8th main, | 0 | 263 | 10:00 | 17:30 | 7:30
89 | WEST | RAJAJINAGAR | N3 | 13 | NRS | F7 | 664 | HT UG CABLE | CAPEX | P-113455 |  | 02-09-2021 | WARD NO 107- Shivanahalli, ,8th main, | 0 | 259 | 10:00 | 17:30 | 7:30
90 | NORTH | PEENYA | N5 | T.DASRAHALLI | MEILAYOUT_66 | F06-TUMKUR MAIN ROAD | DTC NO-53Charging of LT ABC | Charging of LT ABC | CAPEX |  |  | 02-09-2021 | Kempegowda nagara |  |  | 10:00 | 18:00 | 8:00
91 | NORTH | PEENYA | N5 | T.DASRAHALLI | MEILAYOUT_66 | F06-TUMKUR MAIN ROAD | DTC NO-73Charging of LT ABC | Charging of LT ABC | CAPEX |  |  | 02-09-2021 | Kempegowda nagara |  |  | 10:00 | 18:00 | 8:00
92 | NORTH | PEENYA | N5 | T.DASRAHALLI | WELCASTSTEEL_66 | F09 -Ramesh Road | DTC NO-9,332STRINGING of LT ABC | STRINGING of LT ABC | CAPEX |  |  | 02-09-2021 | Pipeline road ,prashanthnagara surroundings |  |  | 10:00 | 18:00 | 8:00
93 | NORTH | PEENYA | N5 | SHETTYHALLI | MEILAYOUT_66 | Fdr:7 PIPE LINE T-DASARAHALLY | FULL FEEDER DTC | OH to UG PENDING WORK converrison work DTC wise | CAPEX | H-1859 & DT-19.10.2020 |  | 02-09-2021 | Kalyananagar, Pipe line road,1st main road |  |  | 10:00 | 17:30 | 7:30
94 | NORTH | PEENYA | N5 | SHETTYHALLI | MEILAYOUT_66 | F1-AGBG LAYOUT | DTC TC-94 & TC95 | OH to UG PENDING WORK converrison work DTC wise | CAPEX |  |  | 02-09-2021 | AGBG LAYOUT |  |  | 10:00 | 17:30 | 7:30
95 | NORTH | PEENYA | N5 | T.DASRAHALLI | WELCASTSTEEL_66 | F09 -Ramesh Road | 11KV spur line DTC OH to UG cable work | OH to UG cable work | CAPEX |  |  | 02-09-2021 | Pipeline road ,prashanthnagara surroundings, selection corner, BWSS pump house |  |  | 10:00 | 18:00 | 8:00
96 | NORTH | PEENYA | N7 | Mahalakshmi layout /kurubarahalli | MAHALAKSHMI LAYOUT | F5 HAMSASAGAR | 11 kv Branch line DTC 03 NOS | OH TO LT AB CABLECONVERSION WORK | CAPEX | 2020/PD/14-1927/ H-1916/13.01.21 |  | 02-09-2021 | Hamsalekha Home, ShankarMutt Park, Milk booth, M.G.Nagar, 12th & 13th Main M.L.Puram Surrounding Area |  |  | 10:00 | 18:00 | 8:00
97 | NORTH | PEENYA | N7 | Nandini layout | NANDINI LAYOUT | F1 NANDINI LAYOUT | 11 kv Branch line DTC 03 NOS | OH TO LT AB CABLE CONVERSION WORK | CAPEX | 2020/PD/14-1927/ H-1891/13.11.20 |  | 02-09-2021 | VIJAYANANDA NAGARA &SURROUNDING AREA |  |  | 10:00 | 18:00 | 8:00
98 | WEST | RAJAJINAGAR | N8 | NAGARABHAVI | CHANDRALAYOUT | F-07 | 687,716,677 | Conversion of 11KV Overhead line into HT Ug Cable inFeeder CL F7 (O&M Nagarbhvai) N8 Sub Division,Rajaji nagar Division Bangalore West Circle, BMAZ (South), BESCOM under PHASE-I on Total turnkey under Rate Contract (RC.05) on Percentage basis quoting. | CAPEX | 2020/RN/14-1927/N-106353/12.01.2022 |  | 02-09-2021 | MALAGAL, RAMA KRISHNAPPA LYT | 2 | 500 | 10:30 | 17:30 | 7:00 | Works includes Srtinging of LT ab Cable one day and connecting servicing connections and load balancing one day
99 | NORTH | JALAHALLI | N9 | D BYALAKERE | Soldevanhalli MUSS | F-3 SHIVAKOTE | 11 KV Feeder DTC | 11 KV Maintenance | Maintenance Work |  |  | 02-09-2021 | SHIVALOTE, MAVALLIPURA, KONDASHETTIHALLI, |  |  | 10:00 | 12:00 | 2:00
100 | NORTH | JALAHALLI | N9 | D BYALAKERE | Soldevanhalli MUSS | F-3 SHIVAKOTE | 11 KV Feeder DTC | 11 KV Maintenance | Maintenance Work |  |  | 02-09-2021 | SHIVALOTE, MAVALLIPURA, KONDASHETTIHALLI, |  |  | 10:00 | 12:00 | 2:00
101 | NORTH | JALAHALLI | N9 | Hesraghatta | Soldevanhalli MUSS | F2 Hesaraghatta | 11 KV FeederXXX9 | Maintenance | Maintenance Work |  |  | 02-09-2021 | Hurulichikkanahalli,Kodige Thirumalapura,IIHR,Fisheries,State Animal Husbandary,Mathkoor,Koluvarayanahalli,Linganahalli,Madappanahalli,Seethakempanahalli,Kalenahalli |  |  | 10:00 | 13:00 | 3:00
102 | SOUTH | JAYANAGAR | S1 | jayanagar 4 T block | JAYADEVA | F04-JD | DTC S 23 | AB CABLE LAYING + CHARGING | CAPEX | 14.1927/J8806 |  | 02-09-2021 | 18th Main Jayanagar |  |  | 10:00 | 17:30 | 7:30
103 | SOUTH | JAYANAGAR | S1 | jayanagar | Jayanagar | F9-Jayanagar | DTC 90.19.93.54.302.127.101.149 | AB CABLE LAYING + CHARGING | CAPEX | 14.1927K-8356.28.6.21 |  | 02-09-2021 | Siddapura,2nd block, 18th cross,8th cross,6th cross, 10th Main 1st block, 3rd block, 18th Cross, 7th Cross, Someshwaranagar |  |  | 10:00 | 17:30 | 7:30
104 | SOUTH | HSR | S10 | BASAVANAPURA | GOLLAHALLI | F2 GOTTIGERE | 11 KV Feeder DTC 5 | Estimate for Arranging power supply to an extent of 195 kw in favour of Khader sha & Shariffa bi, GPA MR Homes no.75/1, kammanahalli | CAPEX & Other Works |  |  | 02-09-2021 | Nil |  |  | 11:00 | 14:00 | 3:00 | Change over given
105 | SOUTH | HSR | S12 | THALGHATTPURA | Anjanapura | F9 | 11 KV Feeder DTC 10 | E Gulam Jeelane Baig and R Shahanaz Begum No 482 2nd block JP nagara Bengaluru | Maintenance Work | M-13890/19.03.2021 |  | 02-09-2021 | BDA 9th phase, 2nd and 3rd block |  |  | 10:30 | 15:30 | 5:00 | Khodays F03
106 | SOUTH | JAYANAGAR | S14 | JP NAGAR O&M | SARAKKI | F23 | 11 KV Feeder | 3 GOS STRUCTURE & LT ABC | CAPEX | J-8832/15-12-2020 & K-8775/27-07-2021 |  | 02-09-2021 | JP NAGAR 5TH PHASE, K-R-LAYOUT, VENKATADRI LAYOUT , DOREANIPALYA- |  |  | 10:00 | 17:30 | 7:30
107 | SOUTH | JAYANAGAR | S15 | U2-KATHRIGUPPE | BSK_MUSS | F12-BSK 3RD STAGE | 11 KV Feeder 106, 354, 416, 569, 344 | conversion of 11KV structure work | CAPEX | J-8785/15.10.2020 |  | 02-09-2021 | Cauvery nagara, vivekananda nagara, Kathriguppe main road, kathriguppe east, BSK 3rd stage |  |  | 10:00 | 17:30 | 7:30
108 | SOUTH | KORAMANGALA | S17 | Basavanagara | BTP | Ayyappa Temple, F-13 | 11 KV Feeder | Line Maintenance Work | Maintenance Work |  |  | 02-09-2021 | Brindavana Layout,Gaffer Layout,Islampur,A.S.Paalya. |  |  | 13:00 | 15:00 | 2:00 | F-8 (ADA), HAL MUSS
109 | SOUTH | JAYANAGAR | S18 | U2 Chikkallasandra | Arehally | F04 | 11 KV Feeder | 3GOS Structure Work | CAPEX | 1572453 09.02.2021 |  | 02-09-2021 | SBM ROAD CK SANDRA |  |  | 10:00 | 17:00 | 7:00
110 | SOUTH | JAYANAGAR | S2 | U-2 SAMPANGI RAMANAGAR | BMTC | F10 | DTC DTC NO:222 | LT AB CABLE STRINGING | CAPEX | K-8773 DATE:28.6.2021 1884-88 DATE:09.07-2021 |  | 02-09-2021 | JC ROAD 1ST CROSS CSI COMPOUND |  |  | 10:00 | 17:00 | 7:00
111 | SOUTH | JAYANAGAR | S2 | U-3 SHANTHINAGAR | AUSTIN TOWN | F04 | DTC DTC NO:301 | LT AB CABLE STRINGING | CAPEX | K-8765 DATE:28.6.2021 1824-28 DATE:09.07-2021 |  | 02-09-2021 | WELLINGTON PARK |  |  | 10:00 | 17:00 | 7:00
112 | SOUTH | HSR | S20 | AGARA | HSR | F07 | 11 KV Feeder DTC 3 | CONVERSION OF O/H TO UG CABLE WORK-STRUCTURE WORK AND AB CABLE WORK | CAPEX | 14.192/L-13656 16.206/L-13756 DT:31.03.2020 |  | 02-09-2021 | 27TH MAIN , 1ST AND 2ND SECTOR, APWD AND NIFT COLLEGE SURROUNDINGS |  |  | 10:00 | 17:00 | 7:00
113 | SOUTH | HSR | S20 | HSR | HSR | F07 | 11 KV Feeder DTC 2 | CONVERSION OF O/H TO UG CABLE WORK-STRUCTURE WORK AND AB CABLE WORK | CAPEX | 14.192/L-13656 16.206/L-13756 DT:31.03.2020 |  | 02-09-2021 | JAKKASANDRA AND PART OF VENKAPURA SURROUNDING AREA |  |  | 10:00 | 17:00 | 7:00
114 | SOUTH | JAYANAGAR | S5 | ISRO layout | ISRO layout | F06-Ergo Spacer | 11 KV Feeder DT-450, DT-459, DT564, DT331 | 3GOS Structure Work | CAPEX | 14.1927/J-9018 |  | 02-09-2021 | Nanjappa Layout,J.C Industrial layout |  |  | 10:00 | 17:00 | 7:00
115 | SOUTH | JAYANAGAR | S6 | Konankunte Unit-4 | 66/11KV RBI | F2-GLASS FACTORY | 11 KV Feeder | 3 GOS STRUCTURE WORK | CAPEX | OH-UG/ Ph-11/ RC-06/14.1927/J-8809dt:29.10.2020 |  | 02-09-2021 | Chunchagatta VILLAGE, Supraja nagar, Ganapathi pura, OLD BANK COLONY, TEACHERS COLONY, KHODAYS BEER FACTORY, BEERESHWARA NAGAR, GANAPATHIPURA, JYOTHI L/O, KONANKUNTE INDUSTRIAL AREA, RAMA KRISHNAPPA L/O, Chunchagatta main road |  |  | 10:00 | 17:30 | 7:30
116 | SOUTH | JAYANAGAR | S9 | PADMANABHA NAGAR | Padmanabhanagar | F01-Banagiri Nagar | DTC TC-138 | LT AB Cable Laying+Charging | CAPEX | 14.1927/J-9008/17.12.2020 |  | 02-09-2021 | 1st Cross Road Banagiri Nagar |  |  | 10:00 | 17:00 | 7:00
117 | SOUTH | JAYANAGAR | S9 | PADMANABHA NAGAR | Padmanabhanagar | F05 9th main bata Showroom /F01-Banagiri Nagar | 11KV Feeder/DTC TC-250,31,152 ,126,181,266,372,446,397 | 3 GOS Structure/LT AB Cable | CAPEX | 14.1927/J-9008/17.12.2020 |  | 02-09-2021 | 24th cross,BDA Complex surrounding ,Bata Showroom limits |  |  | 10:00 | 17:00 | 7:00
118 | SOUTH | JAYANAGAR | S9 | PADMANABHA NAGAR | Padmanabhanagar | F09-Padmanabhanagar | DTC TC-86 | LT AB Cable Laying+Charging | CAPEX | 14.1927/J-9033/15.03.2021 & 14.1927/J-9012/17.12.2020 |  | 02-09-2021 | Padmanabhanagara bus stand ,Puttalingaiah Road ,Carmel School |  |  | 10:00 | 17:00 | 7:00
119 | SOUTH | JAYANAGAR | S9 | BTM O&M | Padmanabhanagar | F03-S9 Office | 11KV Feeder/DTC TC-132 , TC-360 ,TC-343 | 3 GOS Structure/LT AB Cable | CAPEX | 14.1927/J-9027/15.03.2021 & 14.1927/J-9009/17.12.2020 |  | 02-09-2021 | S9 Office, Ring Road, 27th Main,25th Main,28th Cross |  |  | 10:00 | 17:00 | 7:00
120 | SOUTH | JAYANAGAR | S9 | BSK 2nd Stage | Padmanabhanagar | F05 9th Main Bata Show Room | 11KV Feeder/DTC TC-24 | 3 GOS Structure/LT AB Cable | CAPEX | 14.1927/J-9029/15.03.2021 & 14.1927/J-11066/04.12.2020 |  | 02-09-2021 | 4th main,23rd cross K.R Road,Karisandra |  |  | 10:00 | 17:00 | 7:00
121 | SOUTH | JAYANAGAR | S9 | BSK 2nd Stage | Padmanabhanagar | F10-Yarab Nagar | DTC TC-102 | LT AB Cable | CAPEX | 14.1927/J-9030/15.03.2021 & 14.1927/J-9014/17.12.2020 |  | 02-09-2021 | Yarab Nagar Main Road, Masjid Road, |  |  | 10:00 | 17:00 | 7:00
122 | SOUTH | JAYANAGAR | S9 | BSK 2nd Stage | Padmanabhanagar | F13-Saroja Complex | 11KV Feeder/DTC TC NO-108,125,450,291,325,200,447 | 3 GOS Structure/LT AB Cable | CAPEX | 14.1927/J-9031/15.03.2021 & 14.1927/J-9013/17.12.2020 |  | 02-09-2021 | 17th Cross, 9th Main Post Office |  |  | 10:00 | 17:00 | 7:00
123 | KOLAR CIRCLE | KOLAR DIVISION | SP1 | GOWNAPALLLI | 66/11KV GOWNIPALLY MUSS | GF-9 hosudya | 11KV Feeder DTC 1 | Arranging power suppy to LT-2 installation of Sri.Vasudev S/O Chowdappa at Bachireddygaripally village in gownipally section Srinivaspura Subdivision | CAPEX & Other Works | C-38223/15-1-2021 |  | 02-09-2021 | chillarpally village |  |  | 0:00 | 0:00 | 0:00
124 | TUMKUR CIRCLE | TUMKUR DIVISION | TK1 | central section | Tumkur | Tumkur-1(TF-4) Tumkur3 TF5 | 11 KV feeder | conversion of overhead by UG cable | CAPEX | U-31623/25.9.2018 |  | 02-09-2021 | kotithopu road, belagumba road, N.R.colony, horpete road, FMc road, MG road N.r colony, Ashoka road k.R extn, BH road |  |  | 11:00 | 17:00 | 6:00 | full Feeder
125 | TUMKUR CIRCLE | TUMKUR DIVISION | TK2 | SARASWATHIPURAM | 66/11 KV Muss Tumkur | TF-1 Vijaya Nagara | 11 kv Branch line DTC 12 | Execution of the works of conversion of Overheads by UG cables for 11 kV Feeders, running new 11 kV UG cable for feeder load bifurcation, conversion of LT overhead line and service main by LT UG cables providing LT feeder piller boxes RMUs and other allied works and indicated in the tender documents in LOT-1 of Tumkur town of facilitating quality and reliable power supply on total turn key under percentage rate contract basis | CAPEX & Other Works | U-31642/20.11.18 |  | 02-09-2021 | Radhavendra ITI,Municipal Layout |  |  | 11:00 | 17:00 | 6:00 | Dr.Water RMU VL1 charging along with DTC"s Commissioning
126 | TUMKUR CIRCLE | TUMKUR DIVISION | TK2 | SARASWATHIPURAM | MELEKOTE | MF1, MF2,MF10, MF11, MF12, MF4,MF5,MF9,MF26 | 11 KV Feeder DTC 383 | Smart City Ring Road Pole Shifting Work | CAPEX & Other Works | Work Om No EE(ELE)/AEE/O/TA32019-2020/5670.72/20-08-2019 Work Om No EE(ELE)/AEE/O/TA32019-2020/4204-07/09-07-2019 Work Om No EE(ELE)/AEE/O/TA32019-2020/4200-03/09-07-2019 Work Om No EE(ELE)/AEE/O/TA32019-2020/4196.99/09-07-2019 Work Om No EE(ELE)/AEE/O/TA32019-2020/4196.99/09-07-2019 Work Om No EE(ELE)/AEE/O/TA32019-2020/4216.19/09-07-2031 |  | 02-09-2021 | Melekote, Gangasandra, Tuda layout, Danah Palace, UGD, Tippunagara, Nazarabadh, Veerasagara, Kuripalya, Goodshed, Shanthinagara, Upparahalli, Sadhashivanagara, Amarajyothi Nagara, Kumutaiah Badavane, Ramajoyes Nagara, Saraswathipuram 1ST and 2nd stage, Banashankari 1st and 2nd stage, Yadava Nagara, Maralooru, Maralooru Janatha Colony,Pragathi Badavane, Geddalahally, Gubbi Gate, Kuntammana Thota Dibburu,BH Palya, PH Colony, Vinoba Nagara, EdgaMohalla, Hegade Colony, Tilak Park, Jaipura, KHB Colony, bandimane Choutry |  |  | 7:12 | 17:30 | 10:18
127 | TUMKUR CIRCLE | TUMKUR DIVISION | TK4 | SIDDARTA NAGARA | Mallasandra66/11KV | F03-Mallasandra Town, F06-Gollahalli NJY | 13.08.2021 | For replacement of existing 11 KV overhead lines by 11 KV Covered condcutor on MF-03 feeder feeding from Melekote MUSS | Capex | W-1150 |  | 02-09-2021 | Mallasandra GP Limits |  |  | 10:00 | 18:00 | 8:00
128 | WEST | RR NAGAR | W1 | AVALAHALLI - 1 | BSK | F-3 | 11 KV Feeder DTC 203 | Releasing | Maintenance Work | E-56125/31.3.2020 |  | 02-09-2021 | 8th A cross 8thmain road girinagar |  |  | 10:00 | 18:00 | 8:00 | convertion of OVER HEAD to LT ABC the consumers pertains to perticular dtc is effected
129 | WEST | RR NAGAR | W1 | AVALAHALLI - 1 | BSK | F-3 | 11 KV Feeder DTC 123 | Releasing | Maintenance Work | E-56125/31.3.2020 |  | 02-09-2021 | 8th A cross 8thmain road girinagar |  |  | 10:00 | 18:00 | 8:00 | convertion of OVER HEAD to LT ABC the consumers pertains to perticular dtc is effected
130 | WEST | RR NAGAR | W1 | AVALAHALLI - 1 | BSK | F-3 | 11 KV Feeder DTC 71 | Releasing | Maintenance Work | E-56125/31.3.2020 |  | 02-09-2021 | 8th A cross 8thmain road girinagar |  |  | 10:00 | 18:00 | 8:00 | convertion of OVER HEAD to LT ABC the consumers pertains to perticular dtc is effected
131 | WEST | RR NAGAR | W1 | AVALAHALLI - 1 | BSK | F-3 | 11 KV Feeder DTC 126 | Releasing | Maintenance Work | E-56125/31.3.2020 |  | 02-09-2021 | 8th main road 2nd pahse girinagar |  |  | 10:00 | 18:00 | 8:00 | convertion of OVER HEAD to LT ABC the consumers pertains to perticular dtc is effected
132 | WEST | RR NAGAR | W1 | AVALAHALLI - 1 | BSK | F-3 | 11 KV Feeder DTC 95 | Releasing | Maintenance Work | E-56125/31.3.2020 |  | 02-09-2021 | 8th main road 2nd pahse girinagar |  |  | 10:00 | 18:00 | 8:00 | convertion of OVER HEAD to LT ABC the consumers pertains to perticular dtc is effected
133 | WEST | RR NAGAR | W1 | AVALAHALLI - 1 | BSK | F-3 | 11 KV Feeder DTC 78 | Releasing | Maintenance Work | E-56125/31.3.2020 |  | 02-09-2021 | 8th main road 2nd pahse girinagar |  |  | 10:00 | 18:00 | 8:00 | convertion of OVER HEAD to LT ABC the consumers pertains to perticular dtc is effected
134 | WEST | RR NAGAR | W1 | AVALAHALLI - 1 | BSK | F-3 | 11 KV Feeder DTC 162 | Releasing | Maintenance Work | E-56125/31.3.2020 |  | 02-09-2021 | chamundi nagar |  |  | 10:00 | 18:00 | 8:00 | convertion of OVER HEAD to LT ABC the consumers pertains to perticular dtc is effected
135 | WEST | RR NAGAR | W1 | AVALAHALLI - 1 | BSK | F-3 | 11 KV Feeder DTC 210 | Releasing | Maintenance Work | E-56125/31.3.2020 |  | 02-09-2021 | Avadanoi conventional Hall |  |  | 10:00 | 18:00 | 8:00 | convertion of OVER HEAD to LT ABC the consumers pertains to perticular dtc is effected
136 | WEST | RR NAGAR | W2 | SHANKAR PURAM | NATIONAL_COLLEGE_66 | F06-FPMK-CIRCLE | DTC DTC DTC NO:10 | Micro feeder Plan work | Maintenance Work |  |  | 02-09-2021 | JAIN TEMPLE ROAD & JAIN TEMPLE PARLLAL ROAD |  |  | 10:00 | 11:45 | 1:45
137 | WEST | RR NAGAR | W7 | U-20 O&M 20- RAJARAJESHWARI NAGAR | RR Nagar | F-1 SACHIDANAND NAGAR | DTC DTC 165 | Micro plan feeder | Maintenance Work |  |  | 02-09-2021 | Gayatri temple surrounding area |  |  | 10:00 | 13:00 | 3:00
138 | TUMKUR CIRCLE | TIPTUR DIVISION | CN1 | O&M-1 | CN HALLI_110/11 KV | F2 CN HALLI, F11 MUDDENAHALLI | 11 kv Branch line DTC 85 | Replacement of existing 11 Kv Over Head Line by 11 Kv Cover conductor at Varios Location on F2 C N Halli Feeder | Capex | C-57303/08.06.2021 |  | 02-09-2021 | CN HALLI TOWN, MUDDENAHALLI |  |  | 10:00 | 17:00 | 7:00
139 | WEST | RAJAJINAGAR | N8 | S G Kaval | Byadarahalli | F-08 | NA | Conversion from HT OH to HTUG Work | CAPEX | 2020/RN/14-1927/N-106361/12.01.2021 |  | 02-09-2021 | RHCS Layout, Annaporneshwari nagar, Health Layout, D Group Layout, Narasapura, Benachakal palya, Muddinapalya main road, Erana palya, Near reliance fresh gowramma Layout and sounding areas | 0 | 8450 | 10:30 | 17:30 | 7:00
140 | WEST | RAJAJINAGAR | N1 | 2nd BLOCK RAJAJI NAGAR | NRS | F1 | 2,19,40, | Estimate for conversion of LT Overhead line to LT AB Cable in F1 Feeder of NRS MUSS in O&M-2, N1 Sub-division | CAPEX | 2020/RN/14-1927/N-106242/24.09.2020 |  | 02-09-2021 | 1ST BLK | 3 | 1063 | 10:30 | 17:30 | 7:00
141 | TUMKUR CIRCLE | MADHUGIRI DIVISION | KR1 | O&M-1 | Koratagere 66/11kV | F05 Koratagere Town, F18 Urdagere Cross, F01, F03, F04, F09, F06, F07 | DTC 66 | For Providing Switch phase the Street light Control Switch in Koratagere Town limits in O&M-1 Section | CAPEX | R-34482/12.02.2021 |  | 02-09-2021 | Koratagere Town |  |  | 10:00 | 17:00 | 7:00
142 | TUMKUR CIRCLE | TIPTUR DIVISION | TU1 | o&m1 | Talkere | F01 Mangikuppe F02 Talkere F03 Ayarahalli F06 Honkere NJY | 11 KV Feeder | Link line from Donkihalli Bare to Donkihalli G hatti Gate to reduce the over load of F03 overload Feeder | Maintenance Work | B-21401 30.01.2021 |  | 02-09-2021 | Talkere, Donkihalli G Hatti, Donkihalli, D Kalkere, Ayarahalli, Doddaghoraghatta, Chikkaghorghatta, Siddanahatti, Aladevarahatti,Harikaranahalli. |  |  | 10:00 | 17:00 | 7:00
143 | TUMKUR CIRCLE | TIPTUR DIVISION | TU1 | o&m2 | Turuvekere Talkere | F05 Puttamadihalli F04 Anemale F03 Ayarahalli F06 Honkere NJY F17 Badarikashrama | 11 KV Feeder | Reconducting Of Existing F04 Anemale Feeder and Reconducting Of DTC's | Capex | B-37874 09.03.2021 |  | 02-09-2021 | Talkere, Donkihalli G Hatti, Donkihalli, D Kalkere, Ayarahalli, aralikere, sunklapura, dwaranahalli, anemale, mangikuppe |  |  | 10:00 | 17:00 | 7:00
144 | TUMKUR CIRCLE | TIPTUR DIVISION | TU1 | o&m2 | Turuvekere | F1 Mallagatta F3 Hemavathi F8 Anekere F13 Turuvekere F15 Gonitumkur F16 Court | 11 KV Feeder | Shifting Of Poles in Dabbeghatta Road due Road Widening | Maintenance Work |  |  | 02-09-2021 | Turuvekere town, Marasarakottige Mallaghatta, kodigehalli, T Hosahalli, Anekere, Kolghatta, Chikkaturuvekere, Guddenahalli, |  |  | 10:00 | 18:00 | 8:00
145 | DAVANAGERE CIRCLE | HIRIYUR DIVISION | HY1 | HARIYABBE | PD KOTE_66 | F05-HALAGALADDI NJY ,F02-PD-KOTE | 11 KV Feeder | Running 11 Kv Line from Pd ko T0 muss to hoskere limits | Maintenance Work |  |  | 02-09-2021 | maddihally,P.D.Kote,Kanajanahally,Benakanahally,hoskere |  |  | 10:00 | 17:00 | 7:00
146 | DAVANAGERE CIRCLE | HIRIYUR DIVISION | HY1 | HARIYABBE | PD KOTE_66 | F05-HALAGALADDI NJY ,F02-PD-KOTE | 11 KV Feeder | Running 11 Kv Line from Pd ko T0 muss to Benakanahally limits | Maintenance Work |  |  | 02-09-2021 | maddihally,P.D.Kote,Kanajanahally,Benakanahally,hoskere |  |  | 10:00 | 17:00 | 7:00
147 | WEST | RAJAJINAGAR | N6 | 1- KAMAKSHI PALYA | Vijayanagar | F7 | TC-21,20,13,22,28,26,29,33,34,37,38,39,172,173,184,220,231,253,281,283,294,300,301,304,662,664,756,804,863,839,886 | ESTIMATE FOR CONVERSION OF LT OVERHEAD LINE TO LT AB CABLE IN F -07 FEEDER OF VIJAYA NAGAR MUSS IN O&M-01 OF N6 SUB DIVISION | CAPEX | 4330-38/ 30.11.2020 |  | 02-09-2021 | MANIVILLA GARDEN , KAMAKSHIPALYA, VINAYAKA NAGARA, SHIVAFARM, SHIVA TEMPLE , ANDANAPPA LAYOUT, MARIYAPPA ROAD, KAMAKSHIPALYA |  | 6500 | 10:30 | 17:30 | 7:00 | Work will be taken up as schelduled from 1ST SEP 2021
148 | WEST | RAJAJINAGAR | N6 | 3 - SUNKADAKATTE | SRIGANDHA KAVALU | F-6 | TC-542,222,904, 295,744,352,375,353,N6HT-72, 869, 890, 929, N6HT-104, 134, 774, 302, N6HT-33, 133, 581, 581, 740,327, 328, 349,942,860, 135, 852, 228, 895, 831,946, 916, 735, 684, 131, 157, 302, N6HT33, 133,581, 740, 327,328,943,818,N6HT7, 938, 850,816, 342, 126,215, 125,343, 341, 893,54 | ESTIMATE FOR CONVERSION OF HT OVERHEAD LINE TO HT UG CABLE IN F -06 FEEDER OF SRIGANDHA KAVALU MUSS IN O&M-02 OF N6 SUB DIVISION | CAPEX | N-106352/ |  | 02-09-2021 | LAKSHMANA NAGARA, SANJEEVINI NAGARA, VIGNESHWARA NAGARA, HEGGANAHALLI, HEGGANAHALLI CROSS, SUNKADAKATTE, PIPELINE RAOAD SUNAKADAKATTE. |  | 4000 | 10:30 | 17:30 | 7:00 | Work will be taken up as schelduled from 1ST SEP 2021
149 | BRC | HOSAKOTE | DH1 | Vijayapura-1 | 66/11KV VIJAYAPURA | F01 LOCAL VIJAYAPURA,F05 DAIRY | 11 KV Feeder | LINE MAINTAINCE AND JUNGLE CUTTING | Maintenance Work |  |  | 02-09-2021 | VIJAYAPURA TOWN |  |  | 10:30 | 12:30 | 2:00
150 | BRC | HOSAKOTE | DH1 | Vijayapura-2 | 66/11KV VIJAYAPURA | F02BIJJAVARA,F11 MUDDAGURKI,F16 VENKATAGIRI KOTE,F03 NARAYANAPURA,F08 BEEDIGANAHALLI,F12 SAIBABA | 11 KV Feeder | LINE SHIFTING,TRANSFORMER, JUNGLE CUTTING , PROVIDING SPACERS,TC MAINTAINACE,STRAIGHTNING OF LOOSE SPAN, GOS WORK | Maintenance Work |  |  | 02-09-2021 | BIJJAVARA,MUDDAGURKI,VENKATAGIRIKOTE,NARAYANAPURA,BEEDIGANAHALLI |  |  | 10:30 | 12:30 | 2:00
151 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | KADABA | KADABA-110/11KV | F10-DASARAKALLAHALLI NJY ,F04 Honnashettyhally, F05 Bmallenahally, F7 Kadaba, F08 Byalahally | 11 KV Feeder DTC 74 | Bifercater load of F-10 Dasarakallahalli NJY Feeder to Reduce intereption to kadaba twonlimits in kadaba section nittur | Capex | Y-401 30.03.21 |  | 02-09-2021 | KADABA,K,RAMPURA,KOMMANAHALLI,BYADAGERE |  |  | 10:00 | 18:00 | 8:00 | DUE TO RAIN LC NOT AVAILED
152 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | KADABA | KGTEMPLE -110/11KV | F-12 Konnakere njy, F-2 suragenahally, f-5koppa, F-4 kunnala | 11 KV Feeder DTC 132 | For Replacing of Existing Detoriated 4 ACSR Conductor by Good Rabbit ACSR Conductor 11 KV HT Line From D Kunnala to Jeeganahalli Gollarahatti Village Limits of F4 Kunnala Feeder in Kadaba Section (DP- 06 No, 9 Mtr PSCC Pole 95 Nos Rabbit Wire-19.525 KM) | CAPEX | Y-24412/26.03.21 |  | 02-09-2021 | Koppa,kunnala,lingammanahally,konnemadanahally,konnakere,jeeganahally |  |  | 10:00 | 18:00 | 8:00 | DUE TO RAIN LC NOT AVAILED
153 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | KADABA | KGTEMPLE -110/11KV | F-12 Konnakere njy, F-2 suragenahally, f-5koppa, F-4 kunnala | 11 KV Feeder DTC 75 | For Providing Evacation of New 11 KV Link Line Konnakere to Konnanakere Village Limits to Biforcate Load From F5 B Mallenahalli Feeder From Kadaba Muss in Kadaba Section Nittur Sub Division (DP Set-10, 9Mt Pole-58 No, Rabbit Wire-7.605 KM) | Maintenance Work | Y-24371/26.03.21 |  | 02-09-2021 | Koppa,kunnala,lingammanahally,konnemadanahally,konnakere,jeeganahally |  |  | 10:00 | 18:00 | 8:00 | DUE TO RAIN LC NOT AVAILED
154 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | NITTUR | NITTUR220/110/11 KV | F16-SOPANAHALLI.F19-BOMMENAHALLI,F3-SAGAGARANAHALLI,F4-M.S.HALLI,F2-YALLAPURA,F5-HEMAVATHI,F6-THYAGATUR | 11 KV Feeder DTC 215 | For Providing Evacation of New 11 KV Link Line NITTUR MUSS to ADALAGERE PUMP HOUSE Village Limits to Biforcate Load From F3-SAGARANAHALLI FeederIN NITTUR Muss in NITTUR Section Nittur Sub Division (DP Set-10, 9Mt Pole-58 No, Rabbit Wire-7.605 KM) | Maintenance Work | Y-24373/26.3.21 |  | 02-09-2021 | SAGARANAHALLI,THYAGATUR,M.S.HALLI,YALLAPURA,BOMMENAHALLI,KUNDURANAHALLI. |  |  | 10:00 | 18:00 | 8:00
155 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | NITTUR | NITTUR220/110/11 KV | F15-NITTUR,F8-HESARAHALLI,F7-BENACHIGERE,F9-BELAVATHA | 11 KV Feeder DTC 183 | For replacement of existing 11 KV over head lines by 11 KV covered conductor from various locations in Nittur Section. | CAPEX | W-1243/18.3.2020 |  | 02-09-2021 | NITTUR,Mathighatta.HESARAHALLI |  |  | 10:00 | 18:00 | 8:00
156 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | KADABA | KADABA-110/11KV | F03-BELAVATHA, F013 thogarighatta, F11 Belavatha NJY | 11 KV Feeder DTC 84 | Kadaba Muss To Belavatha Village limits Biforcate Over loaded F-9 Belavatha Feeder | Capex | Y-402 31.03.21 |  | 02-09-2021 | ADAGONDANAHALLI , BELAVATHA,LAKSHMIPURA |  |  | 10:00 | 18:00 | 8:00 | DUE TO RAIN LC NOT AVAILED
157 | TUMKUR CIRCLE | TUMKUR DIVISION | YD1 | Yediyur | Yadiyur 66/11 | F-1 Siddalingeshwara Feeder | F-1 Siddalingeshwara Feeder DTC 10 | Estimate for Providing Continous power Supply 2KM Surrounding Yadiyuru Town Limits From F-1 Siddalingeshwara Feeder Feeding From Yadiyuru MUSS Pertaining to Yadiyuru Section Yadiyuru S/D. | CAPEX & Other Works | D-451/08.07.2021 |  | 02-09-2021 | Yadiyuru,Chakenahalli,Doddamadhure,Jaladhigere,Hemavathi,Beerganahalli |  |  | 10:00 | 17:00 | 7:00
158 | TUMKUR CIRCLE | TUMKUR DIVISION | YD1 | Yediyur | Yadiyur 66/11 | F-1 Siddalingeshwara Feeder | F-1 Siddalingeshwara Feeder DTC 12 | Estimate for Providing Continous power Supply 2KM Surrounding Yadiyuru Town Limits From F-1 Siddalingeshwara Feeder and Bifurcation of IP Sets Pertaining to Yadiyuru Section Yadiyuru S/D. | CAPEX & Other Works | D-452/08.07.2021 |  | 02-09-2021 | Yadiyuru,Chakenahalli,Doddamadhure,Jaladhigere,Hemavathi,Beerganahalli |  |  | 10:00 | 17:00 | 7:00
159 | DAVANAGERE CIRCLE | CHITRADURGA DIVISION | HD1 | O&M-1 | Hosadurga MUSS | F5 Kanthapura | 11 KV Feeder | GK Works | Maintenance Work |  |  | 02-09-2021 | Kathapura Areas |  |  | 12:00 | 16:00 | 4:00
160 | TUMKUR CIRCLE | MADHUGIRI DIVISION | PG1 | CK Pura | Pavagada 66/11KV | F06 Rajavanthi | DTC 9 | For HT reconductoring of 4 ACSR by Rabbit Conductor of F-06 Rajavanthi Feeder from Obenahalli to 63 KVA Tank Centre in C.K Pura Section | CAPEX | R-33312/18.02.2021 |  | 02-09-2021 | Rajavanthi, C.N.Halli, R.Hosakote, Kanivenahalli, Ivarlahalli |  |  | 10:00 | 17:00 | 7:00
161 | TUMKUR CIRCLE | MADHUGIRI DIVISION | PG1 | Y.N Hosakote | Y.N.Hosakote 66/11KV | F02 Y.N.Hosakote | DTC 4 | Awarding of Water supply works under rate contract PTK Basis Pavagada S/d Madhugiri Division at Y.N Hosakote Village in Y.N Hosakote section | CAPEX & Other Works | S-49042/07.07.2021 |  | 02-09-2021 | Y.N.Hosakote, J.Acchammanahalli |  |  | 10:00 | 17:00 | 7:00
162 | DAVANAGERE CIRCLE | CHITRADURGA DIVISION | HL1 | O&M - 1 | Holalkere66/11KV | F15-Punajuru, F14-malenahalli NJY, f10-Malladihalli,F11-Gundimadu | 11 KV Feeder | 11 KV Link line from Holalkere Railway station to Malenahalli limits | Maintenance Work |  |  | 02-09-2021 | Arehalli,punajur,Malenahalli, avalihatti,gundimadu,kunagali,Shivapura,Agrahara,Hulemalali,Jaipura |  |  | 10:00 | 18:00 | 8:00
163 | TUMKUR CIRCLE | MADHUGIRI DIVISION | PG1 | Venkatapura | Venkatapura 66/11KV | F03 Dommathamari | DTC 14 | For HT reconductoring of 4 ACSR by Rabbit Conductor of F-03 Dommathamari Feeder from Yalaganagutte to Gowdeti viollage Limits in Venkatapura Section | CAPEX | R-33311/18.02.2021 |  | 02-09-2021 | Dommathamari, Gowdeti, Yalaganagutte, Kanakapura |  |  | 10:00 | 17:00 | 7:00
164 | TUMKUR CIRCLE | MADHUGIRI DIVISION | PG1 | Y.N Hosakote | Y.N.Hosakote 66/11KV | F04 Jalodu | DTC 19 | For HT reconductoring of 4 ACSR by Rabbit Conductor of F-04 Jalod Feeeder from Markandaiah Land to Bhavanathappa Lawyer Land in Y.N Hosakote Section | CAPEX | R-33317/18.02.2021 |  | 02-09-2021 | Jalodu, Siddapura, Marammanahalli, G.T.Halli, Y.N.Halli |  |  | 10:00 | 17:00 | 7:00
165 | TUMKUR CIRCLE | MADHUGIRI DIVISION | PG1 | Nagalamadike | Nagalamadike 66/11KV | F07 Thirumani | DTC 31 | For HT reconductoring of 4 ACSR by Rabbit Conductor of F-07 Thirumani Feeder from Balasamudra to Venkatammanahalli Village in Nagalamadike Section | CAPEX | R-33320/18.02.2021 |  | 02-09-2021 | Thirumani, Vallur, Rayacherlu, R.Acchammanahalli |  |  | 10:00 | 17:00 | 7:00
166 | TUMKUR CIRCLE | TUMKUR DIVISION | YD1 | Yadavani | Yadavani 66/11 KV | NJY3 Kelara | NJY3 Kelara DTC 1 | Estimate for Shifting of HT Line from Existing place to nearby place 80mt Distance due to Existing Line Passing though Coconut Plant garden at Hosakere Village in favour of of Sri Ramakrishna S/O Venkataramaiah at Amruthur section, Yediyur Subdivision. | CAPEX | 2.09.2021 to 3.09.2021 |  | 02-09-2021 | Amruthuru,Sanaba,Hoskere,Jinnagara,Madihalli,chinnahalli |  |  | 10:00 | 17:00 | 7:00
167 | WEST | RAJAJINAGAR | N8 | Mallathahalli | Sir MV | F-01 | 342, 339, 205 | Conversion of 11KV Overhead line into HT Ug Cable inFeeder F-01 (O&M Mallathahalli) N8 Sub Division,Rajaji nagar Division Bangalore West Circle, BMAZ (South), BESCOM under PHASE-I on Total turnkey under Rate Contract (RC.05) on Percentage basis quoting. | CAPEX | 2020/RN/14-1927/N-106255/02.11.2020 |  | 02-09-2021 | Railway Layout and surrounding areas | 2 | 500 | 10:30 | 17:30 | 7:00 | Works includes Srtinging of LT ab Cable one day and connecting servicing connections and load balancing one day
168 | KOLAR CIRCLE | CHINTAMANI DIVISION | CM2 | KENCHARAHALLI | Yenigidale | F09 Yenigidale | 11 KV Feeder | Monsoon maintenance | Maintenance Work |  |  | 02-09-2021 | Yenigidale,Kenchepalli,Gundlahalli,Vangimallu,Balareddyhalli ,Minchalli, Chilakalanerpu,Hosudya,Beedalahalli, |  |  | 10:00 | 13:00 | 3:00
169 | KOLAR CIRCLE | CHINTAMANI DIVISION | CM2 | YEGWAKOTE | M.Gollahalli | F07 Yegavakote | 11 KV Feeder | New Service connection line Work | Capex | U 10111 12.07.2021 |  | 02-09-2021 | Kambalahalli,Yanumalapadi,Yagavakote,Diguvakota,Ragimakalahalli,Y. Kurupalli,Kadirappanayakanakote,Venkatarayanakote,Pasalanayakanahalli. |  |  | 11:00 | 12:00 | 1:00
170 | KOLAR CIRCLE | CHINTAMANI DIVISION | SG1 | O&M-2 | Sidlaghatta | F10-HANUMANTHAPUR | 11 kv Branch line DTC 64 | For Maintanace work | Maintenance Work |  |  | 02-09-2021 | Hanumanthapur,Varadanayakanahalli,Gudihalli,Abloodu,Shettihalli,Kottahalli,Mallahalli,Thathahalli,Idloodu. |  |  | 11:00 | 13:00 | 2:00
171 | KOLAR CIRCLE | CHINTAMANI DIVISION | SG2 | Dibburahalli | Ganjigunte | F4-Ganjikunte | 11 KV Feeder | Jungle/ Tree trimming work,DTC Maintenance , GOS alignment work,Load Balancing,Stringing of Loose Span, Fixing of Spacers of LT Line | Maintenance Work |  |  | 02-09-2021 | Ganjikunte,Lakkanahalli, Vemagal ,Madenahalli,Kyasakere |  |  | 10:00 | 14:00 | 4:00 | Line clear to be arranged during Load Shedding period & one NJY Feeder is interruption of 4:00 Hours
172 | KOLAR CIRCLE | CHINTAMANI DIVISION | SG2 | MELUR | Melur | F3- Kamadahalli | 11 KV Feeder | Jungle Cutting, GOS Manitance, TC Maintance, Jumps Replacing | Maintenance Work |  |  | 02-09-2021 | Kamadahalli, Appegowdanahalli. |  |  | 14:30 | 17:00 | 2:30 | Line clear to be arranged during Load Shedding period & one NJY Feeder is interruption of 2:30 Hours