## 04-09-2021
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Schedule Interruptions for the month of September 2021
Details of works to avail Line Clear for CAPEX, RC, Service connection, OH to UG conversion, Self execution maintenance works
Sl No | Circle | Division | Sub Dvn | OM Unit | Station Name | Feeder No /Name | IF LT Work DTC code capacity | Nomenclature of Works | CAPEX/ Maintenance | Work order No and Date | Sanctioned Date | Date of LC planned | Areas affected | No: of consumers affected |  | Duration of LC required |  |  | Remarks (changeover arranged details) | Work Belongs to Station / BESCOM | LC Taken or Not (Yes / No) | Issue | Remarks | Station/Feeder charged time |  |  | Confirmed by BESCOM / KPTCL | Remarks (If time extended)
[14 empty] | HT consumers | LT consumers | from | To | Total interruption period in | [5 empty] | From | To | Total interruption period in
1 | RAMANAGARA | CHANDAPURA DIVISION | AN1 | Indlawadi | Kubanahalli MUSS | F-03 Bagganadoddi |  | Tree triming , Transformet yard Cleaning and GOS maintaince | Maintenance Work |  |  | 04-09-2021 | Bagganadoddi, Thammanayakanahalli , Mysuramma doddi, Kadujakkanahalli |  |  | 12:15 | 13:45 | 1:30
2 | RAMANAGARA | CHANDAPURA DIVISION | AN1 | Anekal Rural | Samandoor MUSS | F-04 Gandhi Nagar |  | Tree triming , Transformet yard Cleaning and GOS maintaince | Maintenance Work |  |  | 04-09-2021 | Muttagatti, Gudnahalli, Geratiganabele, Sub Managa , Channaian Agrahar, Gandhi Nagar , S Madival , S Thimmasandra |  |  | 11:15 | 13:30 | 2:15
3 | RAMANAGARA | CHANDAPURA DIVISION | AT1 | Mayasandra | Attibele | F24 janadhara shubha & F5 mayasandra |  | Tree trimming & 11 KV/LT jump replacement. GOS maintaminance, LT lead relacement, Jungle cutting | Maintenance Work |  |  | 04-09-2021 | Janadhara Shubha phase 1 & 2, Ramalinga Reddy industrial estate, Shettihalli village |  |  | 0:00 | 48:00 | 48:00
4 | RAMANAGARA | RAMANAGARA DIVISION | BE1 | Dashavaara | 66/11Kv DASHAVARA MUSS | F02-kengal NJY |  | For preventive Maintenance | Maintenance Work |  |  | 04-09-2021 | Hanumantha pura, Kannamangala, Poulidoddi, Angrahalli & others |  |  | 10:30 | 17:00 | 6:30
5 | KOLAR CIRCLE | KGF DIVISION | BG1 | BUDIKOTE | BUDIKOTE | F4 BUDIKOTE | DTC | APS OF LT2 PERIYANNA M S/O MUNISWAMY BUDIKOTE VILLAGE BPET | CAPEX & Other Works |  |  | 04-09-2021 | Budikote town, markondaiha dam , hunkunda,kundenahalli, sanganhalli |  |  | 12:00 | 13:00 | 1:00
6 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | BP1 | PATHAPALAYA | SOMANATHAPURA | F10 PEDDURU | 11 KV Feeder | Venkatalakshmamma W/o Shivareddy,Kurapalli. | Maintenance Work | T-26261 /19.07.2021 |  | 04-09-2021 | Somanathapura,Kurapalli,MM Palli,Chinnaganapalli,Peddur.Jalipigaripalli Rachavaripalli,Gotlapalli,Moogareddypalli,Rajavandlapalli,Kothakotavandlapalli,Nallagutlapalli,Beerangavandlapalli,Bathalavaripalli,Venkatapura,Gunthurpalli,Pasapurallapalli. |  |  | 11:00 | 13:00 | 2:00
7 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | BP1 | O&M-1 | MITTEMARI | F4 GARUDADRI | 11 KV Feeder | M.B.Raghavendra S/o M.B.Venkatswamy,Mittemari. | Maintenance Work | T-26235 /13.07.2021 |  | 04-09-2021 | Mervapalli,Papinayakanapalli,Kothakote,Kodipalli,Pillagutta,Kanagamakalapalli,Dommharahatti,Giriyapalli,Malligurki,Appaswamythanda,Kempaihathnada,Mervapalli,Muthinapalli,Reddyvaripalli. |  |  | 15:00 | 17:00 | 2:00
8 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | BP1 | PATHAPALAYA | 66/11 KV Chakavelu MUSS | F3 Ugranamapalli | 11 KV Feeder DTC 56 |  | Maintenance Work |  |  | 04-09-2021 | Billur,Musliganapalli,Gaddampalli,babenayakanapalli,Yaraganapalli,Rachervu,Digavathanda,Ugranamapalli,Thurakeshpalli. |  |  | 11:00 | 13:00 | 2:00
9 | NORTH | MALLESHWARAM | C1 | Rajajinagar 2ndstage | NRS | F09 Nandhini | DTC228 229 | LT AB Cable | CAPEX |  |  | 04-09-2021 | Gayathirnagar |  |  | 10:00 | 17:00 | 7:00
10 | NORTH | MALLESHWARAM | C1 | Prakash nagar | NRS | F-11 PRAKASH NAGAR | DTC418 | Maintenance | Maintenance Work |  |  | 04-09-2021 | MARUTHI EXTENSION |  |  | 10:00 | 13:00 | 3:00
11 | NORTH | MALLESHWARAM | C1 | Prakash nagar | NANDINI | F-9 SUBRAMANYANAGAR | DTC422 | Maintenance | Maintenance Work |  |  | 04-09-2021 | 1ST, 2ND,3RD , 4TH MAIN B- BLOCK GAYATHRINAGAR |  |  | 10:00 | 14:00 | 4:00
12 | NORTH | MALLESHWARAM | C2 | Malleshwaram | IISC | F8 WATER SUPPLY | LT Line with DTC NoDTC25 | DTC MAINTENANCE AND TREE TRIMMING | Maintenance Work |  |  | 04-09-2021 | 15 TH CROSS 4 TH MAIN MALLESHWARAM |  |  | 10:00 | 14:00 | 4:00
13 | NORTH | JALAHALLI | C3 | ABBIGERE | ABBIGERE | AF03-LAKSHMIPURA | 11 KV Feeder DTC | Maintenance & Tree trimming WORKS | Maintenance Work |  |  | 04-09-2021 | lakshmipura, vaderahally |  |  | 10:00 | 14:00 | 4:00
14 | NORTH | JALAHALLI | C3 | Jalahally | Gokul | F7 - MES road | 11 KV Feeder DTC | For GOS Maintenance & Tree trimming | Maintenance Work |  |  | 04-09-2021 | Muthyalanagar |  |  | 12:00 | 13:00 | 1:00
15 | NORTH | HEBBAL | C5 | Kavalbyrasandra | Hebbala MUSS | F20-PATEL MUNIYAPPA LAYOUT | 11 KV FeederAll Dtcs | tree trimming and gos maintenance | Maintenance Work |  |  | 04-09-2021 | patel muniyappa L/O, Kanaka nagara.. |  |  | 11:00 | 13:00 | 2:00
16 | NORTH | MALLESHWARAM | C6 | Mathikere | MTK | F2 | 11 KV Feeder DTC TC 307, TC 316, TC 260, Gouri Apartment | Overhead to UG Works | CAPEX |  |  | 04-09-2021 | RK garden limits BeL Road |  |  | 10:30 | 18:00 | 7:30
17 | NORTH | HEBBAL | C7 | Yelahanka old town | PUTTENAHALLI | F12 | 11 kv Branch line DTC TC 307, TC 383 | Conversion of 11KV OH to UG Line for F12 ( Puttenahalli Muss) MARUTHI NAGAR BLR Feeder in Yelahanka Old Town O&M 19A of C7 Sub Division, Hebbal Division | CAPEX |  |  | 04-09-2021 | Maruthi Nagar water Tank Area |  |  | 10:00 | 17:00 | 7:00
18 | NORTH | HEBBAL | C7 | Yelahanka old town | PUTTENAHALLI | F13 | 11 kv Branch line DTC TC 331, NEW TC, EX HT, TC 289, HT 735, TC 687,688, HT 707, Ram Lake view HT | Conversion of 11KV OH to UG Line for F13 ( Puttenahalli Muss) Venkatala BLR Feeder in Yelahanka Old Town O&M 19A of C7 Sub Division, Hebbal Division | CAPEX |  |  | 04-09-2021 | Palanahalli 4th cross, Warriors Towers, Dwaraka Nagar |  |  | 10:00 | 17:00 | 7:00
19 | NORTH | HEBBAL | C7 | Yelahanka new town | KHB | F3 | 11 kv Branch line DTC Ajantha Appartment Branch line | Estimate for Conversion of Existing11 KV HT OverHead Line into HT UG cable pertaining to F-3 Feeder KHB MUSS, Feeding to different locations of C-7 Sub-division ,under Phase-II on total Turnkey Basis Under RC-10. | CAPEX |  |  | 04-09-2021 | Ajantha Appartment Road |  |  | 10:00 | 17:00 | 7:00
20 | NORTH | HEBBAL | C7 | Yelahanka new town | KHB | F12 | 11 kv Branch line DTC Saneeshwaratemple Road/Smashana TC | Conversion of 11KV OH to UG Line for F12 ( KHB Muss) BLR- Feeder in Yelahanka New Town O&M 19 of C7 Sub Division, Hebbal Division | CAPEX |  |  | 04-09-2021 | Saneeshwaratemple Road/Smashana TC |  |  | 10:00 | 17:00 | 7:00
21 | NORTH | HEBBAL | C7 | Yelahanka old town | ATTUR | F10 | 11 KV Feeder DTC Govt Hospital Area | Conversion of 11KV OH to UG Line for F10 ( Yelakhanka Muss) IAF BLR- Feeder in Yelahanka Old Town O&M 19A of C7 Sub Division, Hebbal Division | CAPEX |  |  | 04-09-2021 | Govt Hospital Area |  |  | 10:00 | 17:00 | 7:00
22 | NORTH | HEBBAL | C8 | JAKKUR | shoba | F10 | 11 kv Branch line DTC 385.384,382 | CONVERTION OH/UG | CAPEX |  |  | 04-09-2021 | HEGDENAGARA |  |  | 10:00 | 17:00 | 7:00
23 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | CB1 | O&M-4 | Nallimaradahalli | F13 S Gollahalli | full line | Link line work | Maintenance Work |  |  | 04-09-2021 | S Gollahalli Panchath Limits,Kethenahalli,Reddygollavarahalli,Sadenahalli,Rayappanahalli, |  |  | 10:00 | 14:00 | 4:00
24 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | CB1 | O&M-4 | Nallimaradahalli | F4 Kethenahalli | full line | Link line work | Maintenance Work |  |  | 04-09-2021 | S Gollahalli Panchath Limits,Kethenahalli,Reddygollavarahalli,Sadenahalli,Rayappanahalli, |  |  | 10:00 | 14:00 | 4:00
25 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | CB1 | O&M-4 | Nallimaradahalli | F3 Ramadevaragudi | full line | Link line work | Maintenance Work |  |  | 04-09-2021 | S Gollahalli Panchath Limits,Kethenahalli,Reddygollavarahalli,Sadenahalli,Rayappanahalli, |  |  | 10:00 | 14:00 | 4:00
26 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | CB2 | MANDIKAL | Mandikal MUSS | F4-Addagal | full line | Estimat for APS to Irrigation pump set installation in the name of Mariyamma W/o Madappa , Sy no:180 at Nallakadirenahalli Village in Mandikal section RSD CBPUR | CAPEX & Other Works | OM No:-1338-39 dtd:-05-07-2021 |  | 04-09-2021 | All villages of F4-Adagal |  |  | 11:00 | 15:00 | 4:00
27 | DAVANAGERE CIRCLE | CHITRADURGA DIVISION | CD2 | Bharamasagara | BHARAMASAGARA_66 | F11Bharamasagara | 11 KV Feeder | Maintenance work | Maintenance Work |  |  | 04-09-2021 | Bharamasagara |  |  | 13:00 | 15:00 | 2:00
28 | DAVANAGERE CIRCLE | CHITRADURGA DIVISION | CD2 | Bharamasagara | BHARAMASAGARA_66 | F13Kogunde NJY | 11 KV Feeder | Maintenance work | Maintenance Work |  |  | 04-09-2021 | Kodihalli,Bevinahalli,Chowlihalli,Nandihalli,Bahadurghatta,Bahadurghatta Hosahatti,Dyapanahalli,Kariyammanahalli,Kogunde,Panjainahatti,Yammanaghatta, |  |  | 13:00 | 15:00 | 2:00
29 | RAMANAGARA | CHANDAPURA DIVISION | CH1 | Surya City | Kumbaranahalli | F05 Rajapura |  | Tree trimming, Maintenance of GOS, loose span restrining, Bent pole straightening | Maintenance Work |  |  | 04-09-2021 | Rajapura Village |  |  | 10:00 | 12:00 | 2:00
30 | RAMANAGARA | CHANDAPURA DIVISION | CH1 | Bommasandra | Bommasandra | F1 -RESIL CHEMICAL |  | Tree trimming, Maintenance of GOS, loose span restrining, Bent pole straightening | Maintenance Work |  |  | 04-09-2021 | Apotex, Bommasandra Indl area 4th Phase , MTR Road |  |  | 10:00 | 12:00 | 2:00
31 | RAMANAGARA | CHANDAPURA DIVISION | CH1 | Bommasandra | Bommasandra | F3 Orlicon |  | Tree trimming, Maintenance of GOS, loose span restrining, Bent pole straightening | Maintenance Work |  |  | 04-09-2021 | Apotex, Bommasandra Indl area 4th Phase , MTR Road |  |  | 10:00 | 12:00 | 2:00
32 | RAMANAGARA | CHANDAPURA DIVISION | CH1 | Bommasandra | Bommasandra | F7- MAINE MATERIALS ROAD |  | Tree trimming, Maintenance of GOS, loose span restrining, Bent pole straightening | Maintenance Work |  |  | 04-09-2021 | Bommasandra Indl area 4th Phase |  |  | 10:00 | 12:00 | 2:00
33 | RAMANAGARA | CHANDAPURA DIVISION | CH1 | Bommasandra | Bommasandra | F8 BBS Alloys |  | Tree trimming, Maintenance of GOS, loose span restrining, Bent pole straightening | Maintenance Work |  |  | 04-09-2021 | Bommasandra Indl area 4th Phase |  |  | 10:00 | 12:00 | 2:00
34 | RAMANAGARA | CHANDAPURA DIVISION | CH1 | Bommasandra | Bommasandra | F12 |  | Tree trimming, Maintenance of GOS, loose span restrining, Bent pole straightening | Maintenance Work |  |  | 04-09-2021 | Apotex, Bommasandra Indl area 4th Phase , MTR Road |  |  | 10:00 | 12:00 | 2:00
35 | KOLAR CIRCLE | CHINTAMANI DIVISION | CM2 | IRAGAMPALLI | iragampalli | F12 K Raguttahalli | 11 KV Feeder | Cover conductor replacement works | Capex | U-4922/10.08.2021 |  | 04-09-2021 | Anakalu,Jagathanahalli,Gudisalahalli,B. Bathalahalli,Kotagal,Byrasandra,Moogalamari,Upparahalli,Bandakota,Thippenahalli,Shettihalli,Chowdanahalli |  |  | 10:00 | 17:00 | 7:00
36 | KOLAR CIRCLE | CHINTAMANI DIVISION | CM2 | IRAGAMPALLI | iragampalli | F16 Mindigal | 11 KV Feeder | Cover conductor replacement works | Capex |  |  | 04-09-2021 | Nernahalli,Nallarallahalli,Kuramaralahalli,Mindigal,Bodanamari,Sujjanahalli, |  |  | 10:00 | 17:00 | 7:00
37 | RAMANAGARA | RAMANAGARA DIVISION | CP2 | B V Halli | B V HALLI | F-3 BYRASHETTIHALLI |  | MAINTENANCE | Maintenance Work |  |  | 04-09-2021 | BYRASHETTIHALLI |  |  | 12:00 | 14:00 | 2:00
38 | BRC | NELAMANGALA DIVISION | DB2 | Tubagere | 66/11KV Tubagere | TF-11 GUNJUR & TF-3 S S Ghati | 11 KV Feeder DTC 8 | Maintatnce works | Maintenance Work |  |  | 04-09-2021 | SS Ghati,Nellugudige ,Geddalapalya Pal Pal Dinne,Laghumenahalli Makali . Gunjur,KJ Halli, MJ Halli |  |  | 10:00 | 14:00 | 4:00
39 | BRC | HOSAKOTE | DH1 | Budigere | Budigere | F-6 BUDIGERE IP | 11KV Feeder | Maintance work with Jungle trimming | Maintenance Work |  |  | 04-09-2021 | nallu. Jonahalli .reddihalli kaggalahalli nagenahalli |  |  | 9:00 | 12:00 | 3:00
40 | BRC | HOSAKOTE | DH1 | Avathi | 66/11KV DEVANAHALLI | F27 SAIBABA | 11 KV Feeder | JUNGLE CUTTING ,GOS WORK AND LINE MAINTAINCE | Maintenance Work |  |  | 04-09-2021 | THAILGERE,AVATHI BULLAHALLI AVATHI |  |  | 10:00 | 12:00 | 2:00
41 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | DV1 | O&M - 3 | DAVANAGERE_66 | F04-BT | 11 KV Feeder | Self execution work | Maintenance Work | - |  | 04-09-2021 | Old Town Area |  |  | 10:00 | 17:00 | 7:00
42 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | DV1 | O&M - 3 | DAVANAGERE_66 | F11-LF1 | 11 KV Feeder | Self execution work | Maintenance Work | - |  | 04-09-2021 | Old Town Area |  |  | 10:00 | 17:00 | 7:00
43 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | DV1 | O&M - 3 | DAVANAGERE_66 | F10-CGH | 11 KV Feeder | Self execution work | Maintenance Work | - |  | 04-09-2021 | PJ Extension |  |  | 10:00 | 17:00 | 7:00
44 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | DV2 | O&M - 1 | AVARAGERE_66 | F13-ANEKONDA F14 MAHAVEERA | 11 KV Feeder | Feeder Maintenance | Maintenance Work | - |  | 04-09-2021 | RMC LINK ROAD,BT LAYOUT,GUJARI LINE,BAMBOOBAZAR,MATTIKAL ,BDO OFFICE ,IMAMA NAGARA, AMARAPPANA TOATA, ANEKONDA,LBS NAGARA |  |  | 10:00 | 16:00 | 6:00
45 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | DV2 | O&M - 2 | DAVANAGERE | 04-BT | 11 KV Feeder | PREVENTIVE MAINTAINANCE | Maintenance Work | - |  | 04-09-2021 | Mandakki batti, karl marx nagar siddarameshwar nagar indira nagar koli channappa |  |  | 10:00 | 16:00 | 6:00
46 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | DV2 | O&M - 3 | YARAGUNTA | F15-COMMERCIAL | 11 KV Feeder | PREVENTIVE MAINTAINANCE/DSCL | Maintenance Work | - |  | 04-09-2021 | DODDA PETE,VIJAYALAXMI ROAD,CHOWKIPETE,BASAVARAJ PETE,HAGEDIBBA CIRCLE, AMBEDKAR CIRCLE |  |  | 10:00 | 16:00 | 6:00
47 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | DV2 | O&M - 4 | YARAGUNTE | VIJAYANAGARA | 11 KV Feeder | DSCL /DEPARTMENT | Maintenance Work | - |  | 04-09-2021 | DEVARAJ URSU BADAVANE, VIJAYA NAGARA , RAJIVGHANDI BADAVNE, |  |  | 10:00 | 16:00 | 6:00
48 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | DV2 | O&M - 2 | DAVANAGERE | F11-LF1 | 11 KV Feeder | DSCL | Maintenance Work | - |  | 04-09-2021 | KR Market Road, MG Road, Vijayalaxmi Road, Chamarajpete Road. |  |  | 10:00 | 16:00 | 6:00
49 | EAST | SHIVAJINAGAR | E1 | FT | C_STATION_66 | F07-KEMP-ROAD | 112020102079 112020102002 112020102269 | Regular maintanance | Maintenance Work |  |  | 04-09-2021 | Nidhi Apt ,Promenande Road |  |  | 10:30 | 15:00 | 4:30 | Regular maintanance of Line TC
50 | EAST | INDIRANAGAR | E10 | BGH | ITI | F5 ITI | 11 kv Branch line Hindutools TC,Govt School TC, Guruvareddy TC | LT AB Cable Laying+ Dismantling | CAPEX | 405/19/OH to UG/IND/14-192/F-3134 |  | 04-09-2021 | A Narayanapura |  |  | 10:00 | 16:00 | 6:00 | Full Feeder LC
51 | EAST | INDIRANAGAR | E11 | RM NAGAR | ITI | F10 HOYSALA NAGAR | 11 kv Branch Line & LT Line With DTC SAI GREEN APPT. to NAKSHTRA APPT3RD MAIN ENTRANCE HOYSALA NAGAR EX RMU-7 V/L-1 to OYO HOTEL OYO HOTEL to GOWRI APPT.GOWRI APPT. to JS SPLENDER APPT.JS SPLENDER APPT. to NETHRAVATHI APPT.NETHRAVATHI APPT. to NEAR CHETNA COSMOS APPTNEAR CHETNA COSMOS APPT to Akshaya Education FoundationAkshaya Education Foundation to Sri Morakambi MarketingPRABHU SWAMY TC | 1.95 Sqmm Cable Charging & GOS. 2.240 Sqmm&AB Cable Charging | CAPEX |  |  | 04-09-2021 | 2ND MAIN HOYSALA |  |  | 10:00 | 16:00 | 6:00
52 | EAST | INDIRANAGAR | E6 | JBN | HAL | F19 HAL | 11 kv Branch line TC 620 | LT UG Cable commissioning Dismantling | CAPEX | 405/31/INR/OH to UG/14-192/H-1302 |  | 04-09-2021 | Subhash nagar , TC palya , Bhatrahalli, halehalli , garden city college sorounding areas |  |  | 10:00 | 16:00 | 6:00
53 | EAST | INDIRANAGAR | E6 | DMLR | AMARJYOTHI | F09 AMJ | 11 kv Branch line DTC 342,DTC 344,DTC 341 | Dismatnling | CAPEX | 405/20/OH to UG/IND/14-192/G-1019 |  | 04-09-2021 | Prof. U R Rao road, 3rd Cross , Swami Vivekananda road, Domulur Village |  |  | 10:00 | 16:00 | 6:00
54 | EAST | SHIVAJINAGAR | E9 | GOVINDAPURA | LR BANDE | F10-VHBCS LAYOUT | 7 | DTC MAINTENANCE | Maintenance Work |  |  | 04-09-2021 | VHBCS LAYOUT |  |  | 10:00 | 12:30 | 2:30 | -
55 | EAST | SHIVAJINAGAR | E9 | Kothanur | Geddalahalli_66 | F6 Kothanur | 1 | PROVIDING ADDITIONAL TRANSFORMER 100KVA FOR OVERLOADED DTC: BAIRATHI BANDE 465A | Maintenance Work |  |  | 04-09-2021 | Byrathi Bande |  |  | 11:00 | 15:00 | 4:00 | -
56 | EAST | SHIVAJINAGAR | E9 | Kothanur | Geddalahalli | F-06 | TC - 492 | OH to UG Conversion | CAPEX | 1627942 & 01.04.2021 |  | 04-09-2021 | LAWYER LAYOUT |  |  | 0:00 | 120:00 | 120:00 | -
57 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | GB1 | HOSUR | Ramapaura 66/11 | F07-KOTALDINNE | 11 KV Feeder DTC 80 | GOS Maintainance,Jungle cutting& LOOSE SPAN Restringing | Maintenance Work |  |  | 04-09-2021 | kotaladinne , hosuru, sonaganahalli, kachamachanahalli, baktarahalli |  |  | 14:00 | 16:00 | 2:00
58 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | GB1 | HOSUR | Ramapaura 66/11 | F8 ANUDI | 11 kv Branch line DTC 62 | GOS Maintainance,Jungle cutting& LOOSE SPAN Restringing | Maintenance Work |  |  | 04-09-2021 | Anudi, Ramapura , kurudi, kurubarapalya , ranaganahalli , hampasandra,Kudurebelya jalahalli, upprahalli, kundihalli , bisalahalli , |  |  | 14:00 | 16:00 | 2:00
59 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | GB1 | O&M-1 , O&M-2 | Gowribidanuru 220/66/11 | F10-LOCAL | 11 KV Feeder DTC 204 | GOS Maintainance,Jungle cutting& LOOSE SPAN Restringing | Maintenance Work |  |  | 04-09-2021 | Bangalore circle , manasa circle , BH road , Hirebidanuru, MCH Hospital, madanahalli, abhilasaha layout, ajad nagar,court road neharuji colony |  |  | 14:00 | 16:00 | 2:00
60 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | GB1 | O&M-1 , O&M-2 | Gowribidanuru 220/66/11 | F10-LOCAL | 11 KV Feeder DTC 204 | service connection WORK | Maintenance Work |  |  | 04-09-2021 | Bangalore circle , manasa circle , BH road , Hirebidanuru, MCH Hospital, madanahalli, abhilasaha layout, ajad nagar,court road neharuji colony |  |  | 14:00 | 16:00 | 2:00 | service connection
61 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | GD1 | GUDIBANDE | Gudibande_66 | F06-Polampalli | 11 KV Feeder DTC 73 | GOS Maintainance,Jungle cutting | Maintenance Work |  |  | 04-09-2021 | Polampalli,Naduvanahalli,Jangalahalli,Bommaganahalli,Bommanahalli,Appareddyhalli,Melinaappireddyhalli,Medamakalahalli,Keliginaappireddyhalli |  |  | 9:00 | 12:00 | 3:00
62 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | GD1 | D PALYA | D.Palya_66 | F05-Bychapura | 11 kv Branch line DTC 48 | GOS Maintainance,Jungle cutting | Maintenance Work |  |  | 04-09-2021 | Bychapura,Huduguru,D.Palya,Devaganahalli,Bacchareddyhalli |  |  | 11:00 | 14:00 | 3:00
63 | RAMANAGARA | KANAKAPURA DIVISION | HA1 | MARALAVADI | MARALAVADI | F06 GANDHIFORM |  | JUNGLE CLEARNCE | Maintenance Work |  |  | 04-09-2021 | KIADB 2ND PHASE |  |  | 11:00 | 16:00 | 5:00
64 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | JL1 | Pallagatte | Pallagatte_66 | F08-Thuppadahalli | 11 KV Feeder | Maintenance work | Maintenance Work | - |  | 04-09-2021 | Kenchammanagattihalli, Diddagi, hucchangipura, ujjapavaderahalli, siddayyanakote, basavankote and uddaboranahalli |  |  | 10:00 | 18:00 | 8:00
65 | RAMANAGARA | CHANDAPURA DIVISION | JN1 | Jigani | 66/11kv Jigani bommasandra link road | F5 Bansal |  | GOS Maintanance works and tree trimming works | Maintenance Work |  |  | 04-09-2021 | Jigani industrial area |  |  | 10:00 | 14:00 | 4:00
66 | RAMANAGARA | CHANDAPURA DIVISION | JN1 | Bannerughatta | 66/11kv Bannerughatta | F5 AMC |  | GOS Maintanance works and tree trimming works | Maintenance Work |  |  | 04-09-2021 | Mantappa, Lakshmipura, Hullikasanahalli, sakalavara, Hullahalli, Chinnaiahnapalya, C K Palya, Kalkere, Gollahalli, Sampangiramanagara. |  |  | 10:00 | 14:00 | 4:00
67 | WEST | KENGERI | K1 | Ramohalli | Bandemutt Station | F10- Kommaghataa | DTC DT-11 | Tree trimming,DTC maintenance | Maintenance Work |  |  | 04-09-2021 | Kommaghatta Lake TC |  |  | 10:30 | 12:30 | 2:00
68 | WEST | KENGERI | K2 | Andrahalli | NG Halli | F-6 -HT | Full Feeder TC-71,NFTC,150,149 | Estimate for conversion of 11KV OH Line to HT UG Cable of F6 feeder from NG Halli muss in Andrahalli O&M-2, K2 Sub divin, Kengeri Divin, Bangalore. | CAPEX | I-15418 I-15618 I-15718 ,DT:25-02-2021 |  | 04-09-2021 | Industrial Tower Limited, Chakra Nagar,Near Nice Road |  |  | 10:00 | 17:00 | 7:00
69 | WEST | KENGERI | K2 | DB Kallu | Widia | F-9-HT | Spur Line Siddi binyak Layout 2 tc ,Maryapa Layout 2 tc,&LR- | Estimate for conversion of 11KV OH Line to HT UG Cable of F09 feeder from Widia muss in Doddabidarakallu O&M-3, K2 Sub divin, Kengeri Divin, Bangalore | CAPEX | I-15410 I-15610 I-15710 ,DT:22-02-2021 |  | 04-09-2021 | Siddi binyak Layout |  |  | 10:00 | 17:00 | 7:00
70 | WEST | KENGERI | K2 | Andrahalli | NG Halli | F-7-LT | Spur Line TC-102,TC-120,NFTC | Estimate for conversion of LT OH to LT AB Cable of F07 feeder from NG Halli muss in Andrahalli O&M-2, K2 Sub divin, Kengeri Divin, Bangalore-91 | CAPEX | I-15407 I-15707 I-15607 Dt:13-01-2021 |  | 04-09-2021 | T.G. PALYA GOV.SCHOOL |  |  | 10:00 | 17:00 | 7:00
71 | WEST | KENGERI | K2 | Herohalli | Byadarahalli | F-3 -LT | Spur Line TC-01,291,52 | Estimate for conversion of LT OH to LT AB Cable of F3 feeder from Byadarahalli muss in Herohalli O&M-1, K2 Sub divin, Kengeri Divin, Bangalore-91 | CAPEX | I-15404 I-15704 I-15604 ,DT:13-01-2021 |  | 04-09-2021 | Hosahalli Road |  |  | 10:00 | 17:00 | 7:00
72 | KOLAR CIRCLE | KGF DIVISION | KG1 | ROBERTSONPET-2 | Andersonpet | MF-10,f-9 | 11 KV Feeder | Est for APS to lgt. Inst. Of 18 HP of sri. K.J. Sandeep s/o jayaram at muddegowganahalli in R Pet-2 kgf s/d | CAPEX & Other Works |  |  | 04-09-2021 | Kotilingashwara,peddhampalli,gattakamadenu,peddhpalli,kothur |  |  | 11:00 | 11:45 | 0:45
73 | TUMKUR CIRCLE | MADHUGIRI DIVISION | KH1 | O&M-1 | Kodigenahalli | F03 Kodigenahally | DTC 23 | For replacement of existing 11 KV overhead lines by 11 KV Covered condcutor from Police station 100 KVA TC to 25 KVA TC in O&M-1 | CAPEX | S-5562 |  | 04-09-2021 | Kodigenahalli |  |  | 10:00 | 17:00 | 7:00
74 | KOLAR CIRCLE | KOLAR DIVISION | KL2 | Vemgal (Medial village) | Vemagal | F13 Kurubarahalli NJY | 11KV Feeder DTC 134 | For A/L/P/S of Sri Munishami Gowda S/o Anjanappa at Chandrashekarapura V in Vemagal Section RSD Kolar. | CAPEX & Other Works | C-37302 dt:12.02.2021 |  | 04-09-2021 | Vemagal,Purahalli,Hullankallu,Holerahalli,Dinnuru,Seethi,Seethi hosuru,Chanjimale,Mallandahalli,Kurugal,Kurugal Gate,Harjenahalli,Perjenahalli,Chandrashekarapura,Singehalli.Veerapura |  |  | 11:00 | 13:00 | 2:00
75 | KOLAR CIRCLE | KOLAR DIVISION | KL2 | Vemgal (Medial village) | Vemagal | F13 Kurubarahalli NJY | 11KV Feeder DTC 134 | For A/L/P/S of Sri S.M.Lakshminarayana S/o Muniyappa at Singehalli V in Vemagal Section RSD Kolar. | CAPEX & Other Works | C-37300 dt:10.02.2021 |  | 04-09-2021 | Vemagal,Purahalli,Hullankallu,Holerahalli,Dinnuru,Seethi,Seethi hosuru,Chanjimale,Mallandahalli,Kurugal,Kurugal Gate,Harjenahalli,Perjenahalli,Chandrashekarapura,Singehalli.Veerapura |  |  | 11:00 | 13:00 | 2:00
76 | KOLAR CIRCLE | KOLAR DIVISION | KL2 | Vemgal (Medial village) | Vemagal | F13 Kurubarahalli NJY | 11KV Feeder DTC 134 | For A/L/P/S of Sri Chandrappa S/o P.M.Venkatappa at Perjenahalli V in Vemagal Section RSD Kolar. | CAPEX & Other Works | C-37315 dt:02.03.2021 |  | 04-09-2021 | Vemagal,Purahalli,Hullankallu,Holerahalli,Dinnuru,Seethi,Seethi hosuru,Chanjimale,Mallandahalli,Kurugal,Kurugal Gate,Harjenahalli,Perjenahalli,Chandrashekarapura,Singehalli.Veerapura |  |  | 11:00 | 13:00 | 2:00
77 | KOLAR CIRCLE | KOLAR DIVISION | KL2 | Vemgal (Medial village) | Vemagal | F12 Rajakallahalli | 11KV Feeder DTC 39 | For A/L/P/S of Smt Jalajakshi W/o V.E.Ramesh at Chennapanahalli V in Vemagal Section RSD Kolar. | CAPEX & Other Works | C-37335 dt:19.03.2021 |  | 04-09-2021 | Channapanahalli,Shettihalli,Girijinapete,Thokalagatta,Rajakallahalli,S.Agrahara |  |  | 11:00 | 13:00 | 2:00
78 | TUMKUR CIRCLE | TUMKUR DIVISION | KYT | Honnudike | 66/11kV MUSS Honnudike | HNF-01 Thavarekere HNF-03 Honnudike HNF-08 Honnudike HNF-12 Maskal HNF-04 Sasalu HNF-14 Jolumaranahalli | 11 KV Feeder | For replacement of existing 11 KV overhead lines by 11 KV Covered condcutor in Honnudike Section | Maintenance Work |  |  | 04-09-2021 | Honnudike, Maskal Grama Panchayath Limits |  |  | 10:00 | 18:00 | 8:00
79 | KOLAR CIRCLE | KGF DIVISION | MB1 | O&M2 | Mudiyanur | F6,F7,F8 | 11 KV Feeder DTC 45 | Est for APS to 15HP Poultry farm power installation in favour of M.Srinivas S/o Munivenkatappa at Kunthandahalli in O&M-II Sec. | CAPEX & Other Works |  |  | 04-09-2021 | POMBARAHALLI Kunthanadahalli |  |  | 13:00 | 17:00 | 4:00
80 | KOLAR CIRCLE | KGF DIVISION | MB1 | NANGLI | NAGALI | NF2 | 11 KV Feeder DTC 150 | 11 KV LINES R&M | Maintenance Work |  |  | 04-09-2021 | MUSTOR MUDIGERE |  |  | 11:00 | 12:00 | 1:00
81 | KOLAR CIRCLE | KGF DIVISION | MB1 | O&M2 | H GOLLAHALLI | F2.F3,F4,F9 | 11 KV Feeder DTC 150 | JUNGLE CUTTING DTC MAINTAINANCE | Maintenance Work |  |  | 04-09-2021 | H GOLLAHALLI LINGAPUARA AREA |  |  | 10:00 | 14:00 | 4:00
82 | KOLAR CIRCLE | KGF DIVISION | MB1 | O&M2 | H.Gollahalli | F2,F6,F7,F8 | 11 kv Branch line DTC 54 | Est for evacuation of new link to GF4 Vommasandra feeder in O&M-II Sec. | Maintenance Work |  |  | 04-09-2021 | Vommasandra ,KOLADEVI, Kalikere,H gollahali, Sangasandra, Mathagatta |  |  | 10:30 | 16:30 | 6:00
83 | NORTH | PEENYA | N5 | PEENYA | WELCASTSTEEL_66 | F02-AYYAPPA-RMU | 11 KV Feeder DTC OH TO UG/ABC | OH TO UG CONVERSION OF 11KV LINE | CAPEX | H-1896 |  | 04-09-2021 | SIDHARTHNAGAR AND SURROUNDING AREA |  |  | 10:00 | 18:00 | 8:00 | PARTIAL FEEDER INTERUPTED ALL OTHER DTC/HT WILL BE CHRGED WITH CHANGE OVER FEEDER
84 | NORTH | PEENYA | N5 | T.DASRAHALLI | MEILAYOUT_66 | F06-TUMKUR MAIN ROAD | DTC NO-122STRINGING of LT ABC | STRINGING of LT ABC | CAPEX |  |  | 04-09-2021 | Dasarahalli metro back side ,Govt school road, 1st main road |  |  | 10:00 | 18:00 | 8:00
85 | NORTH | PEENYA | N5 | T.DASRAHALLI | WELCASTSTEEL_66 | F09 -Ramesh Road | DTC NO-5,91,405 STRINGING of LT ABC | STRINGING of LT ABC | CAPEX |  |  | 04-09-2021 | Officers model colony, prashanthnagara,MTS colony near mutthurayaswamy temple road |  |  | 10:00 | 18:00 | 8:00
86 | NORTH | PEENYA | N5 | SHETTYHALLI | MEILAYOUT_66 | F3,CHIKKASANDRA | FULL FEEDER DTC | OH to UG PENDING WORK converrison work DTC wise | CAPEX | H-1860 & DT-19.10.2020 |  | 04-09-2021 | BONEVILL AREA CHIKKASANDRA AYR LAYOUT SAPTHAGIRI COLLEGE |  |  | 10:00 | 17:30 | 7:30
87 | NORTH | PEENYA | N5 | SHETTYHALLI | MEILAYOUT_66 | F2,JANAPRIYA HEIGHTS | DTC Tc 266 Tc 07 | OH to UG WORK converrison work DTC wise | CAPEX |  |  | 04-09-2021 | ,Shetihalli ,Mallasandra,Marigold appartment |  |  | 10:00 | 17:30 | 7:30
88 | NORTH | PEENYA | N5 | T.DASRAHALLI | WELCASTSTEEL_66 | F02-AYYAPPA-RMU | 11KV spur line DTC OH to UG cable work | OH to UG cable work | CAPEX |  |  | 04-09-2021 | Kalasthrinagara, Officers model colony ,urdu school road surroundings |  |  | 10:00 | 18:00 | 8:00
89 | NORTH | PEENYA | N7 | Nandini layout | NANDINI LAYOUT | F2 NANDINI LAYOUT | 11 kv Branch line DTC 03 NOS | OH TO LT AB CABLECONVERSION WORK | CAPEX | 2020/PD/14-1927/ H-1892/13.11.20 |  | 04-09-2021 | SOMESHWARA NAGARA & SURROUNDING AREA |  |  | 10:00 | 18:00 | 8:00
90 | WEST | RAJAJINAGAR | N8 | NAGARABHAVI | CHANDRALAYOUT | F-07 | 433,771,745 | Conversion of 11KV Overhead line into HT Ug Cable inFeeder CL F7 (O&M Nagarbhvai) N8 Sub Division,Rajaji nagar Division Bangalore West Circle, BMAZ (South), BESCOM under PHASE-I on Total turnkey under Rate Contract (RC.05) on Percentage basis quoting. | CAPEX | 2020/RN/14-1927/N-106353/12.01.2022 |  | 04-09-2021 | MALAGAL, RAMA KRISHNAPPA LYT, GANGAMMA GARDEN | 2 | 380 | 10:30 | 17:30 | 7:00 | Works includes Srtinging of LT ab Cable one day and connecting servicing connections and load balancing one day
91 | NORTH | JALAHALLI | N9 | Hesraghatta | Soldevanhalli MUSS | F4- Hesaraghatta Express & F-8 Sasuveghatta | 11 KV Feeder DTC | Maintenance | Maintenance Work |  |  | 04-09-2021 | Hurulichikkanahalli,Tarabanahalli,Kodige Thirumalapura,T B Cross,Hesaraghatta,Dasenahalli,Guddadahalli,CPDO,CFSPTI,KMF,DANISH |  |  | 10:00 | 13:00 | 3:00
92 | RAMANAGARA | RAMANAGARA DIVISION | RM2 | Shanaboganahalli | Kootagallu_66KV | F1 Kootagallu |  | Tree trimming and maintenace | Maintenance Work |  |  | 04-09-2021 | Jaipura ,DK Pura |  |  | 10:00 | 12:00 | 2:00
93 | SOUTH | JAYANAGAR | S1 | jayanagar | Jayanagar | F14 -Jayanagar | DTC 16.92.49.60.59.135.20 | AB CABLE LAYING + CHARGING | CAPEX | 14.1927K-9356 |  | 04-09-2021 | 22nd Cross, 3rd block anebande Road, 3rd block, 15th Cross Road, 3rd block, 7th main 2nd block. |  |  | 10:00 | 17:30 | 7:30
94 | SOUTH | HSR | S13 | C.K.Nagara | Naganathapura | F19 | 11 KV Feeder DTC 5 | Sri. Mohammed Ali, #6 & 7, Sy.no.15, Silicon town, Doddanagamangala(V), Begur(H), Bengaluru in C.K.nagara O&M unit, S13 Subdivision | Maintenance Work | M-13654/ 23.12.2020 |  | 04-09-2021 | DODDANAGAMANGALA VILLAGE |  |  | 10:30 | 16:30 | 6:00 | YES
95 | SOUTH | HSR | S13 | C.K.Nagara | Naganathapura | F19 | 11 KV Feeder DTC 5 | Sri. Miyadad mahamood, #40, K.no.4587/15/40,41, Silicon town, Doddanagamangala(V), Begur(H), Bengaluru in C.K.nagara O&M unit, S13 Subdivision | Maintenance Work | M-13652/ 23.12.2020 |  | 04-09-2021 | DODDANAGAMANGALA VILLAGE |  |  | 10:30 | 16:30 | 6:00 | YES
96 | SOUTH | HSR | S13 | C.K.Nagara | Naganathapura | F19 | 11 KV Feeder DTC 3 | Sri. Venkatesh Kukka, No.09, Doddanagamangala (V), Bangalore | Maintenance Work | 05.03.2020 |  | 04-09-2021 | SILICON TOWN DODDANAGAMANGALA |  |  | 10:30 | 14:30 | 4:00 | YES
97 | SOUTH | HSR | S13 | C.K.Nagara | Naganathapura | F19 | 11 KV Feeder DTC 5 | Sri. Sankathala Thirupalu, #79, K.no.3848/15/79, Doddanagamangala(V), Begur(H), Bengaluru. | Maintenance Work |  |  | 04-09-2021 | SILICON TOWN DODDANAGAMANGALA |  |  | 10:30 | 13:30 | 3:00 | YES
98 | SOUTH | JAYANAGAR | S14 | BTM O&M | ST.JOHN | F1 | 11 KV Feeder | LT ABC WORK | CAPEX | K-8774/27-07-2021 |  | 04-09-2021 | BTM 1st stage, 27th main, 17th main, 23rd main, 25th main, AICOBOO Nagar |  |  | 10:00 | 17:30 | 7:30
99 | SOUTH | JAYANAGAR | S15 | U-1 ITTAMADU | AREHALLI_MUSS | F1-NANDINI ENCLAVE | 11 KV Feeder 322, 195, 236, 05, 06, 07,09,10, 170, 303,349 | conversion of 11KV structure work | CAPEX | J-8824/15.12.2020 |  | 04-09-2021 | Mahalakshmi temple, Nandini enclave, Dena Bank colony, Kamakya layout |  |  | 10:30 | 17:30 | 7:00
100 | SOUTH | KORAMANGALA | S17 | Basavanagara | BTP | MOTOROLA,F-2 TEXAS,F-3 RETAILBLOCK,F-4 | 11 KV Feeder | Maintenance Work | Maintenance Work |  |  | 04-09-2021 | Motorola,Texas & Retailblock |  |  | 10:00 | 17:00 | 7:00 | F-15 (Dynasty) HAL MUSS & for F-4 Changeover is DG
101 | SOUTH | JAYANAGAR | S18 | U2 Chikkallasandra | Subramanyapura | F05 | 11 KV Feeder | 3GOS Structure Work | CAPEX | 1637718 30.01.2021 |  | 04-09-2021 | Nagappa L/O |  |  | 10:00 | 17:00 | 7:00
102 | SOUTH | JAYANAGAR | S2 | U-2 SAMPANGI RAMANAGAR | BMTC | F02 | DTC DTC NO:221 | LT AB CABLE STRINGING | CAPEX | K-8762 DATE:28.6.2021 1874-78 DATE:09.07-2021 |  | 04-09-2021 | CSI COMPOUND |  |  | 10:00 | 17:00 | 7:00
103 | SOUTH | JAYANAGAR | S2 | U-3 SHANTHINAGAR | BMTC | F10 | DTC DTC NO:394 | LT AB CABLE STRINGING | CAPEX | K-8768 DATE:28.6.2021 1839-43 DATE:09.07-2021 |  | 04-09-2021 | PURE PHARMA LALBHAG ROAD |  |  | 10:00 | 17:00 | 7:00
104 | SOUTH | HSR | S20 | AGARA | HSR | F09 | 11 KV Feeder DTC 2 | CONVERSION OF O/H TO UG CABLE WORK-STRUCTURE WORK AND AB CABLE WORK | CAPEX | 14.192/L-13662 16.206/L-13762 DT:31.03.2020 |  | 04-09-2021 | 28TH MAIN TO 31ST MAIN OF 1ST NAD 2ND SECTOR |  |  | 10:00 | 17:00 | 7:00
105 | SOUTH | JAYANAGAR | S5 | ISRO layout | ISRO layout | F-08 Vikram Nagar | 11 KV Feeder DT-45, DT-391, DT-47 | 3GOS Structure Work | CAPEX | 14.1927/J-9038 |  | 04-09-2021 | Bikisipura,Mango Garden, Prathima Industrial Layout,kashi Nagar Lake, Isro Layout |  |  | 10:00 | 17:00 | 7:00
106 | SOUTH | JAYANAGAR | S6 | Konankunte Unit-4 | 66/11KV RBI | F5-RBI L/O-2 | 11 KV Feeder | RABBIT RELEASING | CAPEX | OH-UG/ Ph-11/ RC-06/14.1927/J-8831 dt15.12.2022 |  | 04-09-2021 | RBI layout, YADAV FARM |  |  | 10:00 | 17:30 | 7:30
107 | SOUTH | KORAMANGALA | S7 | PANATHUR | 66/11KV MUSS CESSNA | F02 CESSNA | DTC 30 | Maintanace work for MICRO PLAN FEEDER WORK ( Preventive maintance work,providing GOS, top up transil oil, overhauling of GOS,providing LT spacers, provinding Grounding , DTC wiring etc- | Maintenance Work |  |  | 04-09-2021 | cessna road,gear school road & surroundings |  |  | 11:00 | 14:00 | 3:00 | F5 KBH
108 | SOUTH | HSR | S8 | Hongasandra | Naganathapura | F8 | 11 KV Feeder | Preventive Maintenance of the feeder , Tree trimming , Jump renovation | Maintenance Work |  |  | 04-09-2021 | Manipal County Road and sourroundings |  |  | 10:30 | 14:00 | 3:30 | Naganathpura F13 Feeder
109 | SOUTH | JAYANAGAR | S9 | PADMANABHA NAGAR | Padmanabhanagar | F01-Banagiri Nagar | DTC TC-135 | LT AB Cable Laying+Charging | CAPEX | 14.1927/J-9008/17.12.2020 |  | 04-09-2021 | BWSSB office Banagirinagara ,Ganesh temple ,Appolo school surrounding |  |  | 10:00 | 17:00 | 7:00
110 | SOUTH | JAYANAGAR | S9 | PADMANABHA NAGAR | Padmanabhanagar | F09-Padmanabhanagar | DTC TC-111 | LT AB Cable Laying+Charging | CAPEX | 14.1927/J-9033/15.03.2021 & 14.1927/J-9012/17.12.2020 |  | 04-09-2021 | Ganesh temple Puttalingalingaiah Road Padmanabhanagara |  |  | 10:00 | 17:00 | 7:00
111 | SOUTH | JAYANAGAR | S9 | BSK 2nd Stage | Padmanabhanagar | F03-S9 Office | 11KV Feeder/DTC TC-46 | 3 GOS Structure/LT AB Cable | CAPEX | 14.1927/J-9027/15.03.2021 & 14.1927/J-9009/17.12.2020 |  | 04-09-2021 | 26th main road,25th main road,24th cross and 22nd A Cross road |  |  | 10:00 | 17:00 | 7:00
112 | SOUTH | JAYANAGAR | S9 | BSK 2nd Stage | Padmanabhanagar | F10-Yarab Nagar | DTC TC-11 | LT AB Cable | CAPEX | 14.1927/J-9030/15.03.2021 & 14.1927/J-9014/17.12.2020 |  | 04-09-2021 | 9th Main BSK 2ND Stage ,Yarabnagara |  |  | 10:00 | 17:00 | 7:00
113 | SOUTH | JAYANAGAR | S9 | BSK 2nd Stage | Padmanabhanagar | F13-Saroja Complex | 11KV Feeder/DTC TC NO-029,028,280,167,207,223,245 | 3 GOS Structure/LT AB Cable | CAPEX | 14.1927/J-9031/15.03.2021 & 14.1927/J-9013/17.12.2020 |  | 04-09-2021 | MM Industries,14th Cross ,Shatrinagara main road ,K.R.Road |  |  | 10:00 | 17:00 | 7:00
114 | KOLAR CIRCLE | CHINTAMANI DIVISION | SG1 | O&M-2 | Y.HUNASENAHALLI | F08-GOLLAHALLI | 11 kv Branch line DTC 74 | For Maintanace work | Maintenance Work |  |  | 04-09-2021 | Doddadasenahalli,Chikkadasenahalli,Gollahalli,Kundalagurki,Donnahalli,Siddapur,Devaramallur,Kuthandhalli,Dogaranayakanahalli, |  |  | 11:00 | 13:00 | 2:00
115 | KOLAR CIRCLE | CHINTAMANI DIVISION | SG2 | MELUR | Melur | F3- Kamadahalli | 11 KV Feeder | Jungle Cutting, GOS Manitance, TC Maintance, Jumps Replacing | Maintenance Work |  |  | 04-09-2021 | Kamadahalli, Appegowdanahalli. |  |  | 14:30 | 17:00 | 2:30 | Line clear to be arranged during Load Shedding period & one NJY Feeder is interruption of 2:30 Hours
116 | TUMKUR CIRCLE | TUMKUR DIVISION | TK1 | central section | Tumkur | Tumkur-1(TF-4) | 11 KV feeder | conversion of overhead by UG cable | CAPEX | U-31623/25.9.2018 |  | 04-09-2021 | barline road, MG raod Bh road, FMC road KR extn |  |  | 11:00 | 17:00 | 6:00 | Partial feeder
117 | TUMKUR CIRCLE | TUMKUR DIVISION | TK2 | SARASWATHIPURAM | MELEKOTE | MF1, MF2,MF10, MF11, MF12, MF4,MF5,MF9,MF28 | 11 KV Feeder DTC 383 | Smart City Ring Road Pole Shifting Work | CAPEX & Other Works | Work Om No EE(ELE)/AEE/O/TA32019-2020/5670.72/20-08-2019 Work Om No EE(ELE)/AEE/O/TA32019-2020/4204-07/09-07-2019 Work Om No EE(ELE)/AEE/O/TA32019-2020/4200-03/09-07-2019 Work Om No EE(ELE)/AEE/O/TA32019-2020/4196.99/09-07-2019 Work Om No EE(ELE)/AEE/O/TA32019-2020/4196.99/09-07-2019 Work Om No EE(ELE)/AEE/O/TA32019-2020/4216.19/09-07-2033 |  | 04-09-2021 | Melekote, Gangasandra, Tuda layout, Danah Palace, UGD, Tippunagara, Nazarabadh, Veerasagara, Kuripalya, Goodshed, Shanthinagara, Upparahalli, Sadhashivanagara, Amarajyothi Nagara, Kumutaiah Badavane, Ramajoyes Nagara, Saraswathipuram 1ST and 2nd stage, Banashankari 1st and 2nd stage, Yadava Nagara, Maralooru, Maralooru Janatha Colony,Pragathi Badavane, Geddalahally, Gubbi Gate, Kuntammana Thota Dibburu,BH Palya, PH Colony, Vinoba Nagara, EdgaMohalla, Hegade Colony, Tilak Park, Jaipura, KHB Colony, bandimane Choutry |  |  | 7:12 | 17:30 | 10:18
118 | WEST | RR NAGAR | W1 | AVALAHALLI - 1 | BSK | F-13 | 11 KV Feeder DTC 75 | Convertion | CAPEX | E-56127/31.03.2020 |  | 04-09-2021 | 50 feet road gerinagar eranna gubndde avalhalli hosekereahalli main road , part muneshwara block SLV hotel area mithrukuta hotel backside |  |  | 10:00 | 18:00 | 8:00 | convertion of OVER HEAD to LT ABC the consumers pertains to perticular dtc is effected
119 | WEST | RR NAGAR | W1 | AVALAHALLI - 1 | BSK | F-13 | 11 KV Feeder DTC HT156 | Convertion | CAPEX | E-56127/31.03.2020 |  | 04-09-2021 | 50 feet road gerinagar eranna gubndde avalhalli hosekereahalli main road , part muneshwara block SLV hotel area mithrukuta hotel backside |  |  | 10:00 | 18:00 | 8:00 | convertion of OVER HEAD to LT ABC the consumers pertains to perticular dtc is effected
120 | WEST | RR NAGAR | W1 | AVALAHALLI - 1 | BSK | F-13 | 11 KV Feeder DTC 77 | Convertion | CAPEX | E-56127/31.03.2020 |  | 04-09-2021 | 50 feet road gerinagar eranna gubndde avalhalli hosekereahalli main road , part muneshwara block SLV hotel area mithrukuta hotel backside |  |  | 10:00 | 18:00 | 8:00 | convertion of OVER HEAD to LT ABC the consumers pertains to perticular dtc is effected
121 | WEST | RR NAGAR | W1 | AVALAHALLI - 1 | BSK | F-13 | 11 KV Feeder DTC 129 | Convertion | CAPEX | E-56127/31.03.2020 |  | 04-09-2021 | 50 feet road gerinagar eranna gubndde avalhalli hosekereahalli main road , part muneshwara block SLV hotel area mithrukuta hotel backside |  |  | 10:00 | 18:00 | 8:00 | convertion of OVER HEAD to LT ABC the consumers pertains to perticular dtc is effected
122 | WEST | RR NAGAR | W6 | BYATARAYANAPURA | Remco | F-4 | 11 KV Feeder DTC 13 | Releasing | Maintenance Work | F-55362/ 12-11-2020 |  | 04-09-2021 | Bapuji nagr 11 & 12 th cross |  |  | 10:00 | 18:00 | 8:00
123 | WEST | RR NAGAR | W6 | BYATARAYANAPURA | Remco | F-4 | 11 KV Feeder DTC 22 | Releasing | Maintenance Work | F-55362/ 12-11-2020 |  | 04-09-2021 | Bapuji nagr 11 & 12 th cross |  |  | 10:00 | 18:00 | 8:00
124 | WEST | RR NAGAR | W6 | BYATARAYANAPURA | Remco | F-4 | 11 KV Feeder DTC add | Releasing | Maintenance Work | F-55362/ 12-11-2020 |  | 04-09-2021 | Bapuji nagr 11 & 12 th cross |  |  | 10:00 | 18:00 | 8:00
125 | WEST | RR NAGAR | W6 | BYATARAYANAPURA | Remco | F-4 | 11 KV Feeder DTC MS | Releasing | Maintenance Work | F-55362/ 12-11-2020 |  | 04-09-2021 | Bapuji nagr 11 & 12 th cross |  |  | 10:00 | 18:00 | 8:00
126 | WEST | RR NAGAR | W6 | BYATARAYANAPURA | VRASHBAVATHI | F2 | 11 KV Feeder | MAINTAINANCE | Maintenance Work | F-55356 /2-11-2020 |  | 04-09-2021 | PANTHRPALYA |  |  | 10:00 | 18:00 | 8:00
127 | WEST | RR NAGAR | W7 | CHANNASANDRA | BSK | F15 BANGARAPPA NAGAR | DTC DTC 83 | Micro plan feeder | Maintenance Work |  |  | 04-09-2021 | Dsouza Nagara |  |  | 10:00 | 13:00 | 3:00
128 | WEST | RR NAGAR | W7 | U-20 O&M 20- RAJARAJESHWARI NAGAR | RR Nagar | F-1 SACHIDANAND NAGAR | DTC DTC 351 | Micro plan feeder | Maintenance Work |  |  | 04-09-2021 | Police station, HDFC bank |  |  | 10:00 | 13:00 | 3:00
129 | WEST | RAJAJINAGAR | N8 | S G Kaval | Byadarahalli | F-08 | NA | Conversion from HT OH to HTUG Work | CAPEX | 2020/RN/14-1927/N-106361/12.01.2021 |  | 04-09-2021 | RHCS Layout, Annaporneshwari nagar, Health Layout, D Group Layout, Narasapura, Benachakal palya, Muddinapalya main road, Erana palya, Near reliance fresh gowramma Layout and sounding areas | 0 | 8450 | 10:30 | 17:30 | 7:00
130 | WEST | RAJAJINAGAR | N1 | 2nd BLOCK RAJAJI NAGAR | NRS | F1 | 2,19,40, | Estimate for conversion of LT Overhead line to LT AB Cable in F1 Feeder of NRS MUSS in O&M-2, N1 Sub-division | CAPEX | 2020/RN/14-1927/N-106242/24.09.2020 |  | 04-09-2021 | 1ST BLK | 3 | 1063 | 10:30 | 17:30 | 7:00
131 | TUMKUR CIRCLE | MADHUGIRI DIVISION | KR1 | O&M-1 | Koratagere 66/11kV | F05 Koratagere Town, F18 Urdagere Cross, F01, F03, F04, F09, F06, F07 | DTC 66 | For Providing Switch phase the Street light Control Switch in Koratagere Town limits in O&M-1 Section | CAPEX | R-34482/12.02.2021 |  | 04-09-2021 | Koratagere Town |  |  | 10:00 | 17:00 | 7:00
132 | TUMKUR CIRCLE | TIPTUR DIVISION | TU1 | o&m1 | Talkere | F01 Mangikuppe F02 Talkere F03 Ayarahalli F06 Honkere NJY | 11 KV Feeder | Link line from Donkihalli Bare to Donkihalli G hatti Gate to reduce the over load of F03 overload Feeder | Maintenance Work | B-21401 30.01.2021 |  | 04-09-2021 | Talkere, Donkihalli G Hatti, Donkihalli, D Kalkere, Ayarahalli, Doddaghoraghatta, Chikkaghorghatta, Siddanahatti, Aladevarahatti,Harikaranahalli. |  |  | 10:00 | 17:00 | 7:00
133 | TUMKUR CIRCLE | TIPTUR DIVISION | TU1 | o&m2 | Turuvekere Talkere | F05 Puttamadihalli F04 Anemale F03 Ayarahalli F06 Honkere NJY F17 Badarikashrama | 11 KV Feeder | Reconducting Of Existing F04 Anemale Feeder and Reconducting Of DTC's | Capex | B-37874 09.03.2021 |  | 04-09-2021 | Talkere, Donkihalli G Hatti, Donkihalli, D Kalkere, Ayarahalli, aralikere, sunklapura, dwaranahalli, anemale, mangikuppe |  |  | 10:00 | 17:00 | 7:00
134 | TUMKUR CIRCLE | TIPTUR DIVISION | TU1 | o&m2 | Turuvekere | F1 Mallagatta F3 Hemavathi F8 Anekere F13 Turuvekere F15 Gonitumkur F16 Court | 11 KV Feeder | Shifting Of Poles in Dabbeghatta Road due Road Widening | Maintenance Work |  |  | 04-09-2021 | Turuvekere town, Marasarakottige Mallaghatta, kodigehalli, T Hosahalli, Anekere, Kolghatta, Chikkaturuvekere, Guddenahalli, |  |  | 10:00 | 18:00 | 8:00
135 | DAVANAGERE CIRCLE | HIRIYUR DIVISION | HY1 | HARIYABBE | PD KOTE_66 | F05-HALAGALADDI NJY ,F02-PD-KOTE | 11 KV Feeder | Running 11 Kv Line from Pd ko T0 muss to hoskere limits | Maintenance Work |  |  | 04-09-2021 | maddihally,P.D.Kote,Kanajanahally,Benakanahally,hoskere |  |  | 10:00 | 17:00 | 7:00
136 | DAVANAGERE CIRCLE | HIRIYUR DIVISION | HY1 | HARIYABBE | PD KOTE_66 | F05-HALAGALADDI NJY ,F02-PD-KOTE | 11 KV Feeder | Running 11 Kv Line from Pd ko T0 muss to Benakanahally limits | Maintenance Work |  |  | 04-09-2021 | maddihally,P.D.Kote,Kanajanahally,Benakanahally,hoskere |  |  | 10:00 | 17:00 | 7:00
137 | WEST | RAJAJINAGAR | N6 | 1- KAMAKSHI PALYA | Vijayanagar | F7 | TC-21,20,13,22,28,26,29,33,34,37,38,39,172,173,184,220,231,253,281,283,294,300,301,304,662,664,756,804,863,839,886 | ESTIMATE FOR CONVERSION OF LT OVERHEAD LINE TO LT AB CABLE IN F -07 FEEDER OF VIJAYA NAGAR MUSS IN O&M-01 OF N6 SUB DIVISION | CAPEX | 4330-38/ 30.11.2020 |  | 04-09-2021 | MANIVILLA GARDEN , KAMAKSHIPALYA, VINAYAKA NAGARA, SHIVAFARM, SHIVA TEMPLE , ANDANAPPA LAYOUT, MARIYAPPA ROAD, KAMAKSHIPALYA |  | 6500 | 10:30 | 17:30 | 7:00 | Work will be taken up as schelduled from 1ST SEP 2021
138 | WEST | RAJAJINAGAR | N6 | 3 - SUNKADAKATTE | SRIGANDHA KAVALU | F-6 | TC-542,222,904, 295,744,352,375,353,N6HT-72, 869, 890, 929, N6HT-104, 134, 774, 302, N6HT-33, 133, 581, 581, 740,327, 328, 349,942,860, 135, 852, 228, 895, 831,946, 916, 735, 684, 131, 157, 302, N6HT33, 133,581, 740, 327,328,943,818,N6HT7, 938, 850,816, 342, 126,215, 125,343, 341, 893,54 | ESTIMATE FOR CONVERSION OF HT OVERHEAD LINE TO HT UG CABLE IN F -06 FEEDER OF SRIGANDHA KAVALU MUSS IN O&M-02 OF N6 SUB DIVISION | CAPEX | N-106352/ |  | 04-09-2021 | LAKSHMANA NAGARA, SANJEEVINI NAGARA, VIGNESHWARA NAGARA, HEGGANAHALLI, HEGGANAHALLI CROSS, SUNKADAKATTE, PIPELINE RAOAD SUNAKADAKATTE. |  | 4000 | 10:30 | 17:30 | 7:00 | Work will be taken up as schelduled from 1ST SEP 2021
139 | WEST | RAJAJINAGAR | N8 | S G Kaval | S G Kaval | F-10 | NA | Conversion from HT OH to HTUG Work | CAPEX | 2020/RN/14-1927/N-106330/02.11.2020 |  | 04-09-2021 | RHCS Layout, Annaporneshwari nagar, Health Layout, D Group Layout and sounding areas | 0 | 7860 | 10:30 | 17:30 | 7:00
140 | BRC | HOSAKOTE | DH1 | Vijayapura-1 | 66/11KV VIJAYAPURA | F01 LOCAL VIJAYAPURA,F05 DAIRY | 11 KV Feeder | LINE MAINTAINCE AND JUNGLE CUTTING | Maintenance Work |  |  | 04-09-2021 | VIJAYAPURA TOWN |  |  | 10:30 | 12:30 | 2:00
141 | BRC | HOSAKOTE | DH1 | Vijayapura-2 | 66/11KV VIJAYAPURA | F02BIJJAVARA,F11 MUDDAGURKI,F16 VENKATAGIRI KOTE,F03 NARAYANAPURA,F08 BEEDIGANAHALLI,F12 SAIBABA | 11 KV Feeder | LINE SHIFTING,TRANSFORMER, JUNGLE CUTTING , PROVIDING SPACERS,TC MAINTAINACE,STRAIGHTNING OF LOOSE SPAN, GOS WORK | Maintenance Work |  |  | 04-09-2021 | BIJJAVARA,MUDDAGURKI,VENKATAGIRIKOTE,NARAYANAPURA,BEEDIGANAHALLI |  |  | 10:30 | 12:30 | 2:00
142 | TUMKUR CIRCLE | TIPTUR DIVISION | CN1 | O&M-1 | CN HALLI_110/11 KV | F3 TALUK OFFICE F13 HONNEBAGI | 11 kv Branch line DTC 39 | Replacement of existing 11 Kv Over Head Line by 11 Kv Cover conductor at Varios Location on F3 Taluk Office Feeder | Capex | C-57302/08.06.2021 |  | 04-09-2021 | VIDYANAGAR, JOGIHALLI, TALUK OFFICE, HONNEBAGI |  |  | 10:00 | 17:00 | 7:00
143 | TUMKUR CIRCLE | MADHUGIRI DIVISION | KR1 | Theetha | Koratagere 66/11kV | F12- Doddasaggere | DTC 76 | For maintenance of GOS, replacement of 11 Kv line jumps & DTC's of F12 Doddasaggere NJY feeder | Maintenance Work |  |  | 04-09-2021 | Doddasaggere panchayat limit |  |  | 10:00 | 17:00 | 7:00 | LC given only in Load Shedding time of Agri feeders
144 | TUMKUR CIRCLE | MADHUGIRI DIVISION | KR1 | Theetha | Kolala 66/11kV | F17 Ekalavya | DTC 60 | For maintenance of GOS, replacement of 11 Kv line jumps & DTC's of F17-Ekalavya NJY feeder | Maintenance Work |  |  | 04-09-2021 | Theetha panchayat limit |  |  | 10:00 | 17:00 | 7:00 | LC given only in Load Shedding time of Agri feeders
145 | WEST | RAJAJINAGAR | N2 | MARENAHALLI | VIJAYNAGARA | F8 | 1)DTC164-N2 SUBDIVISION OFFICE 2)DTC51-GOVINDARAJ NAGAR 3)DTC522-GOVINDARAJ NAGAR GOVT SCHOOL 4)DTC184-BCES HBCS. | Estimate for conversion of LT Overhead line in to AB Cable pertaining to F8 Feeder , Vijaynagara MUSS in O&M-5,N2 Sub-division. | CAPEX | 2020/RN/14.1927/P-106373/17-03-2021 |  | 04-09-2021 | N2 SUBDIVISION OFFICE, GOVINDARAJ NAGAR,GOVINDARAJ NAGAR GOVT SCHOOL, ,BCES HBCS. | 0 | 4295 | 10:30 | 17:30 | 7:00
146 | WEST | RAJAJINAGAR | N2 | MARENAHALLI | Chandralayout | F1 | 1)DTC140-WIDIA LAYOUT,KOLIMANE ROAD 2)DTC14-ATTIGUPPE PETROL BUNK MAIN ROAD 3)DTC31-ATTIGUPPE INCOME TAX LAYOUT 4)DTC254-WIDIA LAYOUT 5)DTC117-WIDIA LAYOUT 6)DTC52-WIDIA LAYOUT 7)DTC336-BHEL GUEST HOUSE 8)DTC85- BASAVESHWARA LAYOUT 9)DTC243-NEAR BUNT SANGHA, SUBBANNA GARDEN 10)DTC13- BHEL TOWNSHIP, SUBBANNA GARDEN 11)DTC34-BHEL TOWNSHIP, SUBBANNA GARDEN 12)DTC317- BASAVESHWARA LAYOUT 13)DTC198- SUBBANNA GARDEN . | Estimate for conversion of LT Overhead line in to AB Cable pertaining to F1 Feeder , CHANDRALAYOUT MUSS in O&M-5,N2 Sub-division. | CAPEX | 2021/RN/14.1927/P-113459-15-04-2021 |  | 04-09-2021 | WIDIA LAYOUT,KOLIMANE ROAD,ATTIGUPPE PETROL BUNK MAIN ROAD,ATTIGUPPE INCOME TAX LAYOUT,WIDIA LAYOUT,BHEL GUEST HOUSE, BASAVESHWARA LAYOUT,NEAR BUNT SANGHA, SUBBANNA GARDEN,BHEL TOWNSHIP, SUBBANNA GARDEN, BASAVESHWARA LAYOUT,SUBBANNA GARDEN . | 9 | 5695 | 10:30 | 17:30 | 7:00
147 | WEST | RAJAJINAGAR | N2 | MARENAHALLI | Remco | F9 | 1)DTC76-GANGONDANA HALLY 2)DTC218-CHANDRALAYOUT 3DTC368-HBCS LAYOUT 2,BCC LAYOUT 4)DTC554-GANGONDANAHALLI MAIN ROAD PARK SERVICE ROAD 5)DTC118-BINNY LAYOUT 6)DTC126-GOODWILL APPT 7)DTC86-GOODWILL APPT 8)DTC38-BINNY LAYOUT 9)DTC120-BINNY LAYOUT 10)DTC206-ATTIGUPPE NEAR GOVT COLLAGE 11)DTC116-INDIRA COLONY 12)DTC160-MICO LAYOUT II 13)DTC66-MICO LAYOUT 14)DTC159-CHANDRA LAYOUT,NEAR 15)DTC37-BCC LAYOUT 16)DTC77-GANGONDANA HALLY17)DTC74-GANGONDANA HALLY 18)DTC75-GANGONDANA HALLY 19)DTC148-MICO LAYOUT 20)DTC82-BCC LAYOUT 21)DTC205-ATTIGUPPE NEAR GOVT COLLAGE 22)DTC275-BCC LAYOUT WATER TANK BACK SIDE23)DTC76-GANGONDANA HALLY. | Estimate for conversion of LT Overhead line in to AB Cable pertaining to F9 Feeder , Remco MUSS in O&M-5,N2 Sub-division. | CAPEX | 2020/RN/14.1927/N-19-11-2020 |  | 04-09-2021 | GANGONDANA HALLY -CHANDRALAYOUT HBCS LAYOUT 2,BCC LAYOUT GANGONDANAHALLI MAIN ROAD PARK SERVICE ROAD 5)DTC118-BINNY LAYOUT GOODWILL APPT ,-GOODWILL APPT BINNY LAYOUT ,BINNY LAYOUT ,ATTIGUPPE NEAR GOVT COLLAGE ,INDIRA COLONY, MICO LAYOUT II ,MICO LAYOUT CHANDRA LAYOUT,NEAR,BCC LAYOUT GANGONDANA HALLY ,GANGONDANA HALLY -GANGONDANA HALLY ,MICO LAYOUT -BCC LAYOUT ,ATTIGUPPE NEAR GOVT COLLAGE -BCC LAYOUT WATER TANK BACK SIDE,GANGONDANA HALLY. | 10 | 5511 | 10:30 | 17:30 | 7:00
148 | WEST | RAJAJINAGAR | N2 | MARENAHALLI | NRS | F18 | 1)DTC67-SARASWATHI IRON 2)DTC308-CENTRAL EXCISE LAYOUT 3)DTC307-HARIRAM ALIAS LAYOUT 4)DTC309-HARIRAM ALIAS LAYOUT 5)DTC127-11TH MAIN , M C LAYOUT 6)DTC60-C.E.S LAYOUT 7)DTC16- BAPUJI LAYOUT 8)DTC70- SARASWATHI NAGAR 9)DTC124- BINNY LAYOUT 10)DTC310- 4TH CRS,CENTRAL EXCISE 11)DTC305-MC LAYOUT INDUSTRIAL AREA 12)DTC122-BINNY LAYOUT 13)DTC23-LIBRARY 2 14)DTC154-M.C. LAYOUT 15)DTC17-VINAYAKA LAYOUT 16)DTC27-BAPUJI LAYOUT 17)DTC559-NEAR SARASWATHINAGARA APPARTMENT 18)DTC01-VEERESH THEATER 19)DTC209-HARIRAM ALIDAS LAYOUT 20)DTC150-3RD CROSS, CENTRAL EXISE LAYOUT 21)DTC09- CENTRAL EXCISE LAYOUT 22)DTC47-C.S.LAYOUT 23)DTC02-8TH CROSS , M C LAYOUT 24)DTC42- M C LAYOUT 25)DTC22-LIBRARY 1, M C LAYOUT 26)DTC144- BAYANNA INDL ESTATE AD HALLY , MC LAYOUT 27)DTC151-SHANIMAHATHMA TEMPLE, MC LAYOUT 28)DTC55-13TH CROSS M.C.LAYOUT 29)DTC225-MC LAYOUT 2ND CROSS 30)DTC188-MC LAY OUT NEAR CUTEES HOSPITAL 31)DTC270-BAPUJI LAYOUT 32)DTC366-GKW LAYOUT 33)DTC36-SECRETARIATE LAYOUT 34)DTC112-MARENA HALLI | Estimate for conversion of LT Overhead line in to AB Cable pertaining to F18 Feeder , NRS MUSS in O&M-5,N2 Sub-division. | CAPEX | 2021/RN/14.1927/P-113460/15-04-2021 |  | 04-09-2021 | SARASWATHI IRON CENTRAL EXCISE LAYOUT ,HARIRAM ALIAS LAYOUT ,HARIRAM ALIAS LAYOUT ,11TH MAIN , M C LAYOUT ,C.E.S LAYOUT BAPUJI LAYOUT SARASWATHI NAGAR BINNY LAYOUT,4TH CRS,CENTRAL EXCISEMC LAYOUT INDUSTRIAL AREA BINNY LAYOUT LIBRARY 2 ,M.C. LAYOUT VINAYAKA LAYOUTBAPUJI LAYOUT NEAR SARASWATHINAGARA APPARTMENT VEERESH THEATER 19)DTC209-HARIRAM ALIDAS LAYOUT 3RD CROSS, CENTRAL EXISE LAYOUT,CENTRAL EXCISE LAYOUT,C.S.LAYOUT,8TH CROSS , M C LAYOUT M C LAYOUT LIBRARY 1, M C LAYOUT BAYANNA INDL ESTATE AD HALLY , MC LAYOUT,SHANIMAHATHMA TEMPLE, MC LAYOUT 13TH CROSS M.C.LAYOUTMC LAYOUT 2ND CROSS MC LAY OUT NEAR CUTEES HOSPITAL BAPUJI LAYOUT -GKW LAYOUT -SECRETARIATE LAYOUT,MARENA HALLI . | 17 | 7069 | 11:30 | 17:30 | 6:00 | Work will be taken up as schelduled from 3rd SEP 2021
149 | WEST | RAJAJINAGAR | N2 | MARENAHALLI | Chandralayout | F2 | 1)DTC265-VYALIKAVAL HBCS LAYOUT 2)DTC268- VYALIKAVAL HBCS LAYOUT 3)DTC267- VYALIKAVAL HBCS LAYOUT 4)DTC40-GKW LAYOUT 5)DTC197-GKW LAYOUT 6TH MAIN 6)DTC468-PRIYADARSHINI LAYOUT 7)DTC54-PRIYADARSHINI LAYOUT 8)DTC437-PRIYADARSHINI LAYOUT 9)DTC192- SUBBANA GARDEN 10)DTC266- VYALIKAVAL HBCS, NEAR 11)DTC62-VINAYAKA LAYOUT 12)DTC84-ADJASCENT TO WIIDIA LAYOUT 13)DTC155- NEAR VINAYAKA LAYOUT 14)DTC190-VINAYAKA LAYOUT 15)DTC316-VINAYAKA LAYOUT 1ST MAIN 16)DTC83- SUBBANNA GARDEN17)DTC328- SUBBANNA GARDEN 18)DTC147-SHIVANANDNAGARA 19)DTC156- VINAYAKA LAYOUT 3RD MAIN 20)DTC315-VINAYAKA LAYOUT 1ST MAIN 21)DTC59-MOODALAPALYA 22)DTC46- CHANDRA LAYOUT 23)DTC90- CHANDRA LAYOUT 24)DTC18-GKW LAYOUT 25)DTC115-GKW LAYOUT 26)DTC87-PF LAYOUT 27)DTC88-PF LAYOUT 28)DTC49-VINAYAKA LAYOUT 29)DTC314-VINAYAKA LAYOUT 3RD MAIN 30)DTC245-VYALIKAVAL LAYOUT 31)DTC265-VYALIKAVAL HBCS 32)DTC89-KPA BLOCK CHANDRALAYOUT. | Estimate for conversion of LT Overhead line in to AB Cable pertaining to F2 Feeder , Chandralayout MUSS in O&M-5,N2 Sub-division. | CAPEX | 2021/RN/14.1927/P-113457/15-04-2021 |  | 04-09-2021 | VYALIKAVAL HBCS LAYOUT,GKW LAYOUT,GKW LAYOUT 6TH MAIN, PRIYADARSHINI LAYOUT,SUBBANA GARDEN, VYALIKAVAL HBCS, NEARVINAYAKA LAYOUT, ADJASCENT TO WIIDIA LAYOUT,NEAR VINAYAKA LAYOUT, 1ST MAIN SUBBANNA GARDEN, SHIVANANDNAGARA, ,VINAYAKA LAYOUT 3RD MAIN,VINAYAKA LAYOUT 1ST MAIN,MOODALAPALYA, CHANDRA LAYOUT,GKW LAYOUT,PF LAYOUT,VINAYAKA LAYOUT,VINAYAKA LAYOUT 3RD MAIN,VYALIKAVAL LAYOUT VYALIKAVAL HBCS KPA BLOCK, CHANDRALAYOUT. | 6 | 10122 | 10:30 | 17:30 | 7:00
150 | WEST | RAJAJINAGAR | N2 | MARENAHALLI | Chandralayout | F6 | 1)DTC269-NANJARASAPPA LAYOUT 2)DTC327- NEAR SKYLINE BBMP PARK 3)DTC222- BAPUJI HBCS LAYOUT 4)DTC200-CANARA BANK COLONY 5)DTC330 MARUTHINAGARA 6)DTC320-CHANDRA LAYOUT 7)DTC250- BAPUJI LAYOUT 8)DTC71-CHICKPETE LAYOUT 9)DTC221-BAPUJI LAYOUT10)DTC19-CANARA BANK COLONY 11)DTC162-SKYLINE APARTMENT MAIN ROAD12)DTC111-CANARA BANK COLONY13)DTC503-ANUBHAVA NAGARA 14)DTC137-MARUTHI NAGARA15_DTC332-NAGARABHAVI MAIN ROAD 16)DTC43-MARUTHINAGARA17)DTC323- MARUTHINAGARA 3RD MAIN 18)DTC64-CANARA BANK COLONY 19)DTC269-MC LAYOUT JAYALAKSHMI INDUSTRIAL. | Estimate for conversion of LT Overhead line in to AB Cable pertaining to F6 Feeder , Chandralayout MUSS in O&M-5,N2 Sub-division. | CAPEX | 2021/RN/14.1927/P-113458/15-04-2022 |  | 04-09-2021 | NANJARASAPPA LAYOUT NEAR SKYLINE BBMP PARK BAPUJI HBCS LAYOUT CANARA BANK COLONY,MARUTHINAGARA CHANDRA LAYOUT BAPUJI LAYOUT CHICKPETE LAYOUT BAPUJI LAYOUT CANARA BANK COLONY SKYLINE APARTMENT MAIN ROAD ,CANARA BANK COLONY ,ANUBHAVA NAGARA,MARUTHI NAGARA15,NAGARABHAVI MAIN ROAD,MARUTHINAGARA,MARUTHINAGARA 3RD MAIN,CANARA BANK COLONY MC LAYOUT JAYALAKSHMI INDUSTRIAL. | 2 | 5840 | 10:30 | 17:30 | 7:00
151 | WEST | RAJAJINAGAR | N2 | MARENAHALLI | Chandralayout | F8 | 1)DTC213-CHANDRALAYOUT NEAR SIDDAGANGA SCHOOL BACK SIDE 2)DTC460-Siddaganga School Back side 3)DTC226- INCOME TAX LAYOUT 4)DTC227-INCOME TAX LAYOUT 5)DTC228-INCOME TAX LAYOUT 6)DTC229-INCOME TAX LAYOUT 7)DTC233- VIDYAGIRI LAYOUT 8)DTC157- CHANDRA LAYOUT, BUS 9)DTC119-MARUTHI NAGARA 10)DTC260-CHANDRA LAYOUT 80FEET ROAD 11)DTC458-CHANDRA LAYOUT SIDDAGANGA SCHOOL BACKSIDE 12)DTC450- CHANDRA LAYOUT 80FEET ROAD MARUTHINAGARA 13)DTC438-CHANDRA LAYOUT BMTC DEPOT 14)DTC93- CHANDRA LAYOUT 15)DTC94-CHANDRA LAYOUT MILK BOOTH 16)DTC20-CHANDRA LAYOUT 17)DTC73-CHANDRA LAYOUT 18)DTC72- BASAVESHWARA LAYOUT 19)DTC321- KPA CHANDRA LAYOUT 20)DTC215- MARUTHI NAGARA 80 FEET ROAD 21)DTC263-MARUTHI NAGARA 80 FEET ROAD 22)DTC203- CHANDRALAYOUT 23)DTC244-JYOTHINAGARA 24)DTC168-BCES HBCS 25)DTC169- BCES HBCS 26)DTC232- INCOME TAX LAYOUT 27)DTC233- INCOME TAX LAYOUT 28)DTC261-CHANDRALAYOUT 29)DTC179-BCES HBCS 30)DTC178-BCES HBCS 31)DTC92-N-BHAVI,1 STG,BHND 32)DTC149-SBI, CHANDRALAYOUT 33)DTC240-8TH CROSS, M C LAYOUT 34)DTC50-CHANDRA LAYOUT 35)DTC45- NAGARABHAVI 36)DTC252- CHANDRALAYOUT 12TH CROSS 37)DTC253-CHANDRALAYOUT 11TH CROSS 38)DTC166-BCES HBCS 39)DTC262-CHANDRALAYOUT 12TH CROSS 40)DTC167-BCES HBCS 41)DTC61-CHANDRA LAYOUT SLUM 42)DTC132-CHANDRALAYOUT 43)DTC177- BCES HBCS 44)DTC173- BCES HBCS 45)DTC171- BCES HBCS 46)DTC170- BCES HBCS 47)DTC230-INCOME TAX LAYOUT 48)DTC219-CHANDRALAYOUT 49)DTC181-BCES HBCS 50)DTC182-BCES HBCS 51)DTC459-Siddaganga School Back side. | Estimate for conversion of LT Overhead line in to AB Cable pertaining to F8 Feeder , CHANDRALAYOUT MUSS in O&M-5,N2 Sub-division. | CAPEX | 2021/RN/14.1927/ |  | 04-09-2021 | CHANDRALAYOUT NEAR SIDDAGANGA SCHOOL BACK SIDE ,Siddaganga School Back side , INCOME TAX LAYOUT ,VIDYAGIRI LAYOUT , CHANDRA LAYOUT, BUS ,MARUTHI NAGARA ,CHANDRA LAYOUT 80FEET ROAD ,CHANDRA LAYOUT BMTC DEPOT ,CHANDRA LAYOUT MILK BOOTH , BASAVESHWARA LAYOUT , KPA CHANDRA LAYOUT , MARUTHI NAGARA 80 FEET ROAD ,JYOTHINAGARA ,N-BHAVI,1 STG,BHND ,SBI, CHANDRALAYOUT,8TH CROSS, M C LAYOUT ,NAGARABHAVI ,CHANDRALAYOUT 12TH CROSS ,CHANDRALAYOUT 11TH CROSS ,BCES HBCS ,CHANDRALAYOUT 12TH CROSS ,CHANDRA LAYOUT SLUM. | 0 | 10542 | 10:30 | 17:30 | 7:00
152 | WEST | RAJAJINAGAR | N10 | PATTEGAR PALYA | Vijayanagar | F15 | 6ADTC-595,437,317,238,252,237,30,318,268,417,702,471,02,784,31,735,644,760,280,19,21,25,553,270,772 | ESTIMATE FOR CONVERSION OF LT OVERHEAD LINE TO LT AB CABLE IN F -15 FEEDER OF VIJAYA NAGAR MUSS IN O&M-6A PATTEGARAPALYA OF N10 SUB DIVISION | CAPEX | 113467/15.04.2021 |  | 04-09-2021 | PETECHANNAPPA INDUSTRAIL AREA | 0 | 685 | 11:30 | 17:30 | 6:00 | Work will be taken up as schelduled Saturday & Sunday only
153 | TUMKUR CIRCLE | TUMKUR DIVISION | TK3 | BELLAVI | 66/11kV MUSS HEGGERE, BELLAVI, MALLASANDRA | F5-BUGUDANAHALLI, F4-MUDIGERE, F7-KANNENAHALLI,F7-DODDANARAVANGA, F13-GOWDIHALLI | 11 KV Feeder DTC 56 | LINE SHIFTING WORK UNDER SELF EXECUTION | Maintenance Work | WEC-A-1728/05.08.2021 |  | 04-09-2021 | BUGUDANAHALLI GOWDIHALLI MUDIGERE KANNENAHALLI AGALAKUNTE |  |  | 10:00 | 17:00 | 7:00
154 | WEST | RAJAJINAGAR | N10 | PATTEGAR PALYA | Vijayanagar | F10 | 6ADTC-32,33,326,732,552,36,35,525,296,710,411,41,368,587,500,409,34,749,37,779,216,39,580 | ESTIMATE FOR CONVERSION OF LT OVERHEAD LINE TO LT AB CABLE IN F -10 FEEDER OF VIJAYA NAGAR MUSS IN O&M-6A PATTEGARAPALYA OF N10 SUB DIVISION | CAPEX | 106346/19.11.2020 |  | 04-09-2021 | KAMAKSHIPALYA INDUSTRIAL ESTATE,KCG ESTATE | 0 | 485 | 11:30 | 17:30 | 6:00 | Work will be taken up as schelduled Saturday & Sunday only
155 | WEST | RAJAJINAGAR | N10 | PATTEGAR PALYA | Vijayanagar | F15 | PETECHANNAPPA INDUSTRIAL AREA FEEDER OH TO UG STRUCTURE WORK | ESTIMATE FOR CONVERSION OF HT OVERHEAD LINE TO UG CABLE IN F -15 FEEDER OF VIJAYA NAGAR MUSS IN O&M-6A PATTEGARAPALYA OF N10 SUB DIVISION | CAPEX | N-106357/12.02.2021 |  | 04-09-2021 | PETECHANNAPPA INDUSTRAIL AREA | 5 | 685 | 11:30 | 17:30 | 6:00 | Work will be taken up as schelduled Saturday & Sunday only
156 | WEST | RAJAJINAGAR | N10 | PATTEGAR PALYA | Vijayanagar | F10 | KAMAKSHI PALYA INDUSTRIAL AREA FEEDER OH TO UG STRUCTURE WORK | ESTIMATE FOR CONVERSION OF HT OVERHEAD LINE TO UG CABLE IN F -10 FEEDER OF VIJAYA NAGAR MUSS IN O&M-6A PATTEGARAPALYA OF N10 SUB DIVISION | CAPEX | 2019/RN/14-1927/M-97837/31.03.2020 |  | 04-09-2021 | KAMAKSHIPALYA INDUSTRIAL ESTATE,KCG ESTATE | 4 | 485 | 11:30 | 17:30 | 6:00 | Work will be taken up as schelduled Saturday & Sunday only
157 | TUMKUR CIRCLE | MADHUGIRI DIVISION | KR1 | Thovinakere | Thovinakere 66/11kV | F06 Thovinakere town | DTC 27 | for Jungle cutting GOS & DTC maintenace | Maintenance Work |  |  | 04-09-2021 | Thovinakere Town |  |  | 11:00 | 15:00 | 4:00 | LC given only in Load Shedding time of Agri feeders
158 | TUMKUR CIRCLE | TUMKUR DIVISION | KU1 | O&M-1 | Anchepalya 66/11 | F13 NJY Hosahally | F13 NJY Hosahally DTC 1 | Est for reconductoring 4 ACSR wire by rabbit conductor with providing intermediate poles of existing 25 KVA DTC at Hosahally Colony in O&M-1 Sec, Kunigal S/D | CAPEX | C-11795 /30.03.2021 |  | 04-09-2021 | Hosahally village limits |  |  | 10:00 | 13:00 | 3:00
159 | TUMKUR CIRCLE | TUMKUR DIVISION | KU1 | O&M-1 | Kunigal 66/11 | F4 Rayappamarga | F4 Rayappamarga DTC 1 | Est for reconductoring 4 ACSR wire by rabbit conductor with providing intermediate poles of existing 100 KVA DTC at Mahaveeranagara village in O&M-1 Sec, Kunigal S/D | CAPEX | C-551 / 20.03.2021 |  | 04-09-2021 | Mahaveeranagara village limits |  |  | 10:00 | 13:00 | 3:00
160 | TUMKUR CIRCLE | TUMKUR DIVISION | YD1 | Yediyur | Jiddigere | F4 Jiddigere | F4 Jiddigere DTC 90 | Estimate for providing 11KV Link line for reduce the over load of F-4 Jiddigere Feeder ( Jiddigere 66/11KV MUSS) , Jiddiger 66/11 KV MUSS to Yallapura village in Yediyur section, Yediyur Subdivision. | CAPEX | C-201 / 29.08.2020 |  | 04-09-2021 | Chottanahallygate,Yallapura gate devara kannasandra,Channthimmanapalya |  |  | 10:00 | 17:00 | 7:00
161 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | KADABA | KADABA-110/11KV | F10-DASARAKALLAHALLI NJY ,F04 Honnashettyhally, F05 Bmallenahally, F7 Kadaba, F08 Byalahally | 11 KV Feeder DTC 74 | Bifercater load of F-10 Dasarakallahalli NJY Feeder to Reduce intereption to kadaba twonlimits in kadaba section nittur | Capex | Y-401 30.03.21 |  | 04-09-2021 | KADABA,K,RAMPURA,KOMMANAHALLI,BYADAGERE |  |  | 10:00 | 18:00 | 8:00 | DUE TO RAIN LC NOT AVAILED
162 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | KADABA | KGTEMPLE -110/11KV | F-12 Konnakere njy, F-2 suragenahally, f-5koppa, F-4 kunnala | 11 KV Feeder DTC 132 | For Replacing of Existing Detoriated 4 ACSR Conductor by Good Rabbit ACSR Conductor 11 KV HT Line From D Kunnala to Jeeganahalli Gollarahatti Village Limits of F4 Kunnala Feeder in Kadaba Section (DP- 06 No, 9 Mtr PSCC Pole 95 Nos Rabbit Wire-19.525 KM) | CAPEX | Y-24412/26.03.21 |  | 04-09-2021 | Koppa,kunnala,lingammanahally,konnemadanahally,konnakere,jeeganahally |  |  | 10:00 | 18:00 | 8:00 | DUE TO RAIN LC NOT AVAILED
163 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | KADABA | KGTEMPLE -110/11KV | F-12 Konnakere njy, F-2 suragenahally, f-5koppa, F-4 kunnala | 11 KV Feeder DTC 75 | For Providing Evacation of New 11 KV Link Line Konnakere to Konnanakere Village Limits to Biforcate Load From F5 B Mallenahalli Feeder From Kadaba Muss in Kadaba Section Nittur Sub Division (DP Set-10, 9Mt Pole-58 No, Rabbit Wire-7.605 KM) | Maintenance Work | Y-24371/26.03.21 |  | 04-09-2021 | Koppa,kunnala,lingammanahally,konnemadanahally,konnakere,jeeganahally |  |  | 10:00 | 18:00 | 8:00 | DUE TO RAIN LC NOT AVAILED
164 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | NITTUR | NITTUR220/110/11 KV | F16-SOPANAHALLI.F19-BOMMENAHALLI,F3-SAGAGARANAHALLI,F4-M.S.HALLI,F2-YALLAPURA,F5-HEMAVATHI,F6-THYAGATUR | 11 KV Feeder DTC 215 | For Providing Evacation of New 11 KV Link Line NITTUR MUSS to ADALAGERE PUMP HOUSE Village Limits to Biforcate Load From F3-SAGARANAHALLI FeederIN NITTUR Muss in NITTUR Section Nittur Sub Division (DP Set-10, 9Mt Pole-58 No, Rabbit Wire-7.605 KM) | Maintenance Work | Y-24373/26.3.21 |  | 04-09-2021 | SAGARANAHALLI,THYAGATUR,M.S.HALLI,YALLAPURA,BOMMENAHALLI,KUNDURANAHALLI. |  |  | 10:00 | 18:00 | 8:00
165 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | NITTUR | NITTUR220/110/11 KV | F15-NITTUR,F8-HESARAHALLI,F7-BENACHIGERE,F9-BELAVATHA | 11 KV Feeder DTC 183 | For replacement of existing 11 KV over head lines by 11 KV covered conductor from various locations in Nittur Section. | CAPEX | W-1243/18.3.2020 |  | 04-09-2021 | NITTUR,Mathighatta.HESARAHALLI |  |  | 10:00 | 18:00 | 8:00
166 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | KADABA | KADABA-110/11KV | F03-BELAVATHA, F013 thogarighatta, F11 Belavatha NJY | 11 KV Feeder DTC 84 | Kadaba Muss To Belavatha Village limits Biforcate Over loaded F-9 Belavatha Feeder | Capex | Y-402 31.03.21 |  | 04-09-2021 | ADAGONDANAHALLI , BELAVATHA,LAKSHMIPURA |  |  | 10:00 | 18:00 | 8:00 | DUE TO RAIN LC NOT AVAILED
167 | TUMKUR CIRCLE | TUMKUR DIVISION | YD1 | Yediyur | Yadiyur 66/11 | F-1 Siddalingeshwara Feeder | F-1 Siddalingeshwara Feeder DTC 10 | Estimate for Providing Continous power Supply 2KM Surrounding Yadiyuru Town Limits From F-1 Siddalingeshwara Feeder Feeding From Yadiyuru MUSS Pertaining to Yadiyuru Section Yadiyuru S/D. | CAPEX & Other Works | D-451/08.07.2021 |  | 04-09-2021 | Yadiyuru,Chakenahalli,Doddamadhure,Jaladhigere,Hemavathi,Beerganahalli |  |  | 10:00 | 17:00 | 7:00
168 | TUMKUR CIRCLE | TUMKUR DIVISION | YD1 | Yediyur | Yadiyur 66/11 | F-1 Siddalingeshwara Feeder | F-1 Siddalingeshwara Feeder DTC 12 | Estimate for Providing Continous power Supply 2KM Surrounding Yadiyuru Town Limits From F-1 Siddalingeshwara Feeder and Bifurcation of IP Sets Pertaining to Yadiyuru Section Yadiyuru S/D. | CAPEX & Other Works | D-452/08.07.2021 |  | 04-09-2021 | Yadiyuru,Chakenahalli,Doddamadhure,Jaladhigere,Hemavathi,Beerganahalli |  |  | 10:00 | 17:00 | 7:00
169 | DAVANAGERE CIRCLE | CHITRADURGA DIVISION | HL1 | O&M - 1 | Holalkere66/11KV | F15-Punajuru, F14-malenahalli NJY, f10-Malladihalli,F11-Gundimadu | 11 KV Feeder | 11 KV Link line from Holalkere Railway station to Malenahalli limits | Maintenance Work |  |  | 04-09-2021 | Arehalli,punajur,Malenahalli, avalihatti,gundimadu,kunagali,Shivapura,Agrahara,Hulemalali,Jaipura |  |  | 10:00 | 18:00 | 8:00
170 | TUMKUR CIRCLE | MADHUGIRI DIVISION | PG1 | Venkatapura | Venkatapura 66/11KV | F03 Dommathamari | DTC 14 | For HT reconductoring of 4 ACSR by Rabbit Conductor of F-03 Dommathamari Feeder from Yalaganagutte to Gowdeti viollage Limits in Venkatapura Section | CAPEX | R-33311/18.02.2021 |  | 04-09-2021 | Dommathamari, Gowdeti, Yalaganagutte, Kanakapura |  |  | 10:00 | 17:00 | 7:00
171 | TUMKUR CIRCLE | MADHUGIRI DIVISION | PG1 | Y.N Hosakote | Y.N.Hosakote 66/11KV | F04 Jalodu | DTC 19 | For HT reconductoring of 4 ACSR by Rabbit Conductor of F-04 Jalod Feeeder from Markandaiah Land to Bhavanathappa Lawyer Land in Y.N Hosakote Section | CAPEX | R-33317/18.02.2021 |  | 04-09-2021 | Jalodu, Siddapura, Marammanahalli, G.T.Halli, Y.N.Halli |  |  | 10:00 | 17:00 | 7:00
172 | TUMKUR CIRCLE | MADHUGIRI DIVISION | PG1 | Nagalamadike | Nagalamadike 66/11KV | F07 Thirumani | DTC 31 | For HT reconductoring of 4 ACSR by Rabbit Conductor of F-07 Thirumani Feeder from Balasamudra to Venkatammanahalli Village in Nagalamadike Section | CAPEX | R-33320/18.02.2021 |  | 04-09-2021 | Thirumani, Vallur, Rayacherlu, R.Acchammanahalli |  |  | 10:00 | 17:00 | 7:00
173 | WEST | RAJAJINAGAR | N8 | Mallathahalli | Sir MV | F-01 | 342, 339, 205 | Conversion of 11KV Overhead line into HT Ug Cable inFeeder F-01 (O&M Mallathahalli) N8 Sub Division,Rajaji nagar Division Bangalore West Circle, BMAZ (South), BESCOM under PHASE-I on Total turnkey under Rate Contract (RC.05) on Percentage basis quoting. | CAPEX | 2020/RN/14-1927/N-106255/02.11.2020 |  | 04-09-2021 | Railway Layout and surrounding areas | 2 | 500 | 10:30 | 17:30 | 7:00 | Works includes Srtinging of LT ab Cable one day and connecting servicing connections and load balancing one day
174 | DAVANAGERE CIRCLE | CHITRADURGA DIVISION | HD1 | O&M-1 | Hosadurga MUSS | F12 Rangavanahalli | 11 KV Feeder | GK Works | Maintenance Work |  |  | 04-09-2021 | Rangavanahalli Areas |  |  | 13:00 | 17:00 | 4:00
175 | TUMKUR CIRCLE | MADHUGIRI DIVISION | PG1 | Y.N Hosakote | Y.N.Hosakote 66/11KV | F10 Neelammanahalli | DTC 14 | For HT reconductoring of 4 ACSR by Rabbit Conductor of F-10 Neelammanahalli Feeeder from Neelammanahallio Gate to Neelammanahalli Village in Y.N Hosakote Section | CAPEX | R-33318/18.02.2021 |  | 04-09-2021 | Neelammanahalli, Buddareddyhalli, Meenakuntanahalli, Bommaganahalli |  |  | 10:00 | 17:00 | 7:00
176 | WEST | RAJAJINAGAR | N8 | Mallathahalli | Sir MV | F-09 | 761 | Conversion of 11KV Overhead line into HT Ug Cable inFeeder F-09 (O&M Mallathahalli) N8 Sub Division,Rajaji nagar Division Bangalore West Circle, BMAZ (South), BESCOM under PHASE-I on Total turnkey under Rate Contract (RC.05) on Percentage basis quoting. | CAPEX | 2020/RN/14-1927/N-106363/12.01.2021 |  | 04-09-2021 | Ullal Main road and surrounding areas | 0 | 250 | 10:30 | 17:30 | 7:00 | Works includes Srtinging of LT ab Cable one day and connecting servicing connections and load balancing one day
177 | WEST | RAJAJINAGAR | N8 | Mallathahalli | Sir MV | F-09 | 330, 331 | Conversion of 11KV Overhead line into HT Ug Cable inFeeder F-09 (O&M Mallathahalli) N8 Sub Division,Rajaji nagar Division Bangalore West Circle, BMAZ (South), BESCOM under PHASE-I on Total turnkey under Rate Contract (RC.05) on Percentage basis quoting. | CAPEX | 2020/RN/14-1927/N-106363/12.01.2021 |  | 04-09-2021 | ITI Layout and surrounding areas | 2 | 380 | 10:30 | 17:30 | 7:00 | Works includes Srtinging of LT ab Cable one day and connecting servicing connections and load balancing one day
178 | TUMKUR CIRCLE | MADHUGIRI DIVISION | PG1 | CK Pura | Mangalawada 66/11KV | F06 Killarlahalli | DTC 6 | For HT reconductoring of 4 ACSR by Rabbit Conductor of F-06 Kilarlahalli Feeder from Kilarlahalli village to Doudabetta Thanda in C.K Pura Section | CAPEX | R-33313/18.02.2021 |  | 04-09-2021 | Killarlahalli, Davadabetta, Gundarlahalli, Channasagaradahatti |  |  | 10:00 | 17:00 | 7:00
179 | TUMKUR CIRCLE | MADHUGIRI DIVISION | PG1 | Mangalawada | Lingadahalli 66/11KV | F10 Nidagallu NJY | DTC 18 | For LT reconductoring of 2/4 ACSR by Rabbit Conductor at Vadanakal Village tc Opposite temple village limts 63 KVA DTC in Mangalawada Section | CAPEX | R-33851/18.02.2021 |  | 04-09-2021 | Vadanakallu |  |  | 10:00 | 17:00 | 7:00
180 | BRC | HOSAKOTE | DH1 | O&M 1 | 66/11KV DEVANAHALLI | F02 BEERSANDRA ,F19 KUNDANA | 11 KV Feeder | EXECUTING THE GANGA KALYANA WORKS | Maintenance Work |  |  | 04-09-2021 | BEERSANDRA,VISHWANATHAPURA,DINNE SOLURU |  |  | 10:00 | 12:00 | 2:00