## 06-09-2021
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Schedule Interruptions for the month of September 2021
Details of works to avail Line Clear for CAPEX, RC, Service connection, OH to UG conversion, Self execution maintenance works
Sl No | Circle | Division | Sub Dvn | OM Unit | Station Name | Feeder No /Name | IF LT Work DTC code capacity | Nomenclature of Works | CAPEX/ Maintenance | Work order No and Date | Sanctioned Date | Date of LC planned | Areas affected | No: of consumers affected |  | Duration of LC required |  |  | Remarks (changeover arranged details) | Work Belongs to Station / BESCOM | LC Taken or Not (Yes / No) | Issue | Remarks | Station/Feeder charged time |  |  | Confirmed by BESCOM / KPTCL | Remarks (If time extended)
[14 empty] | HT consumers | LT consumers | from | To | Total interruption period in | [5 empty] | From | To | Total interruption period in
1 | RAMANAGARA | CHANDAPURA DIVISION | AN1 | Anekal Rural | AKLMUSS | F-18 Chikkahosahalli |  | Tree triming , Transformet yard Cleaning DTC & pole erection , restringing of snapped condcutor, removing tree branches fallen on the line | Maintenance Work |  |  | 06-09-2021 | Sidhi Hosakote, Honnakalasapura, Kempavadarahalli , Doddahagade, Soppahalli, Yallamanapalya |  |  | 11:45 | 13:25 | 1:40
2 | RAMANAGARA | CHANDAPURA DIVISION | AN1 | Anekal Urban | AKLMUSS | F-08 Chilling centre |  | Tree triming , Transformet yard Cleaning DTC & pole erection , restringing of snapped condcutor, removing tree branches fallen on the line | Maintenance Work |  |  | 06-09-2021 | Venteswar Takies , Haldenahalli , Vidhath School , Ram kutter |  |  | 10:35 | 13:25 | 2:50
3 | RAMANAGARA | CHANDAPURA DIVISION | AN1 | Anekal Rural | AKLMUSS | F-19 Kaveri Telecom |  | Tree triming , Transformet yard Cleaning DTC & pole erection , restringing of snapped condcutor, removing tree branches fallen on the line | Maintenance Work |  |  | 06-09-2021 | Suragajakkanahalli, CK layout , Prashanth Layout Strides |  |  | 9:35 | 12:35 | 3:00
4 | RAMANAGARA | CHANDAPURA DIVISION | AN1 | Anekal Rural | AKLMUSS | F-20 Vanakanahalli NJY |  | Tree triming , Transformet yard Cleaning DTC & pole erection , restringing of snapped condcutor, removing tree branches fallen on the line | Maintenance Work |  |  | 06-09-2021 | Bodarahalli , Venkateswarapura, Sunavar, Lakshimipura , Mutturu, Basavanapura, Telagarahalli, Homplaghatta , Singsandran , Vanakanahalli, Menasiganahalli, Kempudommasandra, Bilinirukunte, |  |  | 11:45 | 13:10 | 1:25
5 | RAMANAGARA | CHANDAPURA DIVISION | AT1 | Attibele | Attibele | F19-JAYABHARATHI SCHOOL |  | Tree trimming & 11 KV jump replacement. | Maintenance Work |  |  | 06-09-2021 | Attibele Town towards Anekal Road |  |  | 0:00 | 48:00 | 48:00
6 | RAMANAGARA | CHANDAPURA DIVISION | AT1 | Dommasandra | Dommasandra | F01-V.KALLAHALLI,F06-SOMPURAGATE & F09-CHAMBENAHALLI |  | Tree trimming & 11 KV/LT jump replacement. GOS maintaminance, LT lead relacement, Jungle cutting | Maintenance Work |  |  | 06-09-2021 | Chambenahalli, V kallahalli, ittangoor,Dasarahalli,Sompura,K N S Layout,Yamare,Chanebenahalli Road, Trinity Complex,Sompura gate,Kadahagrahara,Hosahalli Road S2 home's. |  |  | 0:00 | 24:00 | 24:00
7 | RAMANAGARA | CHANDAPURA DIVISION | AT1 | Mayasandra | Attibele | F14 Balluru & F01 Inchaguru |  | Tree trimming & 11 KV/LT jump replacement. GOS maintaminance, LT lead relacement, Jungle cutting | Maintenance Work |  |  | 06-09-2021 | ,Manchanahalli, Balluru, Arehalli, dasanapura, Bhakthipura, TVS road |  |  | 0:00 | 48:00 | 48:00
8 | KOLAR CIRCLE | KGF DIVISION | BG1 | KAMSAMUDRA | kamasamudra | F-11 NJY THALLURU | 11 KV Feeder | JUNGLE CUTTING | Maintenance Work |  |  | 06-09-2021 | Doddaponadlahalli, bodapatti, kolamauru limits and back |  |  | 11:00 | 13:00 | 2:00
9 | KOLAR CIRCLE | KGF DIVISION | BG1 | O&M3 | Bangarpet | F2 sulikunte | 11 KV Feeder | DTC WIRING | Maintenance Work |  |  | 06-09-2021 | SULIKUNTE,HANCHALA, BYADABELE, KANIMBELE |  |  | 11:00 | 13:00 | 2:00
10 | KOLAR CIRCLE | KGF DIVISION | BG1 | KARAHALLI | KGF | F5 JAYAMANGALA | 11 KV Feeder | DTC WIRING | Maintenance Work |  |  | 06-09-2021 | KARAPANAHALLI,MADHAMUTTANAHALLI LIMITS |  |  | 11:00 | 12:00 | 1:00
11 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | BP1 | O&M-2 | THIMMAMPALLI | F5 NAGARLU | 11 KV Feeder | Lakshminarasimhaswamy Temple C/o Narasimhappa, Guttapalya. | Maintenance Work | T-26260/ 19.07.2021 |  | 06-09-2021 | Thimmampalli G Maddepalli,Vsanthapura,Gorthapalli,D Kothapalli,Sajjupalli,Sriramapura,Jeeganavandlapalli Sakavandlapalli,Guttapalya. |  |  | 15:00 | 17:00 | 2:00
12 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | BP1 | O&M-1 | BAGEPALLI | F14 PUTTAPARTHI | 11 KV Feeder DTC 15 | Shakila Banu W/o Shafeer Ahamed,Yetagaddapalli | Maintenance Work | T-26342/10.08.2021 |  | 06-09-2021 | Gantamvaripalli,Hosahudya,Narepalli,TB Cross,Abakavaripalli.Adiganapalli. |  |  | 13:00 | 15:00 | 2:00
13 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | BP1 | O&M-2 | 66/11 KV Bagepalli MUSS | F15 NALLAPPAREDDYPALLI | 11 kv Branch line DTC 44 |  | Maintenance Work |  |  | 06-09-2021 | Rayadurgampalli.Pothepalli,Nallappareddypalli,Jillajirla,Chennarayanapalli,Guluru,Narasapura,Motakapalli,Nanjireddypalli,Ivaralapalli,Parvathipura thanda,Malakachervupalli,Kuradinnapalli,Koyyaguttathanda,Lakshman thanda,Papannakuntathanda,Chinnakayalapalli. |  |  | 11:00 | 13:00 | 2:00
14 | NORTH | MALLESHWARAM | C1 | Rajajinagar 2ndstage | NRS | F09 Nandhini | DTC231 232 | LT AB Cable | CAPEX |  |  | 06-09-2021 | Gayathirnagar |  |  | 10:00 | 17:00 | 7:00
15 | NORTH | MALLESHWARAM | C1 | Okalipuram | A | F3'OKALIPURA | DTC111010103 342 | Maintenance | Maintenance Work |  |  | 06-09-2021 | MUDDAPPA GARDEN 1ST CROSS TO 6TH CROSS |  |  | 9:30 | 13:30 | 4:00
16 | NORTH | MALLESHWARAM | C1 | Prakash nagar | NRS | F-26 SAI MANDIRA | DTC481 | Maintenance | Maintenance Work |  |  | 06-09-2021 | srirampura |  |  | 10:00 | 12:00 | 2:00
17 | NORTH | MALLESHWARAM | C1 | Prakash nagar | NRS | F4-DEVAIAH PARK | DTC434433 | Maintenance | Maintenance Work |  |  | 06-09-2021 | 1ST STAGE OKALPURAM |  |  | 10:00 | 13:00 | 3:00
18 | NORTH | MALLESHWARAM | C2 | PALACE GUTTAHALLI | BRIGADE | F4 | LT Line with DTC NoDTC NO-40 | MAINTANANCE AND TREE TRIMMING | Maintenance Work |  |  | 06-09-2021 | RAGAVENDRA TC (S P EXTENSION) |  |  | 10:00 | 17:00 | 7:00
19 | NORTH | MALLESHWARAM | C2 | Malleshwaram | IISC | F5 GANESHA | LT Line with DTC NoDTC49 | DTC MAINTENANCE | Maintenance Work |  |  | 06-09-2021 | KRISHNA APARTMENT 18TH CROSS |  |  | 10:00 | 14:00 | 4:00
20 | NORTH | JALAHALLI | C3 | ABBIGERE | ABBIGERE | F05-SINGAPURA | 11 KV Feeder DTC | Maintenance & Tree trimming WORKS | Maintenance Work |  |  | 06-09-2021 | singapura, abbigere industrial area |  |  | 10:00 | 14:00 | 4:00
21 | NORTH | HEBBAL | C4 | Hebbal | SAHAKARNAGAR | F6-kempapura | 11 KV Feeder DTC 8 | FEEDER MAINTAINENCE | Maintenance Work |  |  | 06-09-2021 | DASRAHALLI MAIN ROAD, BHUVANESHWARI NAGRA, VENKATEGOWDA L/O, COFFE BOARD L/O PARK |  |  | 11:30 | 15:00 | 3:30
22 | NORTH | HEBBAL | C4 | Ganganagar | HEBBALA | F3-SULTHANPALYA | 11 KV Feeder DTC 22 | FEEDER MAINTAINENCE | Maintenance Work |  |  | 06-09-2021 | CHAMUNDINAGR, ANANDNAGAR, RT NAGAR |  |  | 11:00 | 15:00 | 4:00
23 | NORTH | HEBBAL | C4 | Sanjaynagar | RMV | F2 | 11 KV Feeder DTC 2 | SELF EXECUTION WORK | Maintenance Work |  |  | 06-09-2021 | DOLLARS COLONY |  |  | 11:30 | 15:00 | 3:30
24 | NORTH | HEBBAL | C5 | Kavalbyrasandra | LR Bande | F06-FD-J-HALLI | 11 KV FeederAll Dtcs | tree trimming and gos maintenance | Maintenance Work |  |  | 06-09-2021 | M M L/o. Nagamma L/O, K B Sandra |  |  | 11:00 | 13:00 | 2:00
25 | NORTH | MALLESHWARAM | C6 | Yeshwanthapura | MTK | F5 | 11 KV Feeder DTC TC 48, TC 82, TC 99, TC 40, TC 10, TC 96, RR Residency | Overhead to UG Works | CAPEX |  |  | 06-09-2021 | BK Nagar 2nd Main road |  |  | 10:30 | 18:00 | 7:30
26 | NORTH | HEBBAL | C7 | new town | Attur | F09 | 11 kv Branch line DTC 308, 307, 346 & 391. | Convertion of Existing OH to UG cable of F9 feeder of Yelahanka MUSS. | CAPEX |  |  | 06-09-2021 | 14th Main Judicial Layout |  |  | 10:00 | 17:00 | 7:00
27 | NORTH | HEBBAL | C7 | Yelahanka old town | KHB | F11 | 11 kv Branch lineTC 657, TC 470, DTC 528 | Conversion of 11KV OH to UG Line for F11 ( KHB Muss) Feeder in Yelahanka Old Town O&M 19A of C7 Sub Division, Hebbal Division | CAPEX |  |  | 06-09-2021 | MSV Vivek Marvel Apt |  |  | 10:00 | 17:00 | 7:00
28 | NORTH | HEBBAL | C7 | Yelahanka old town | PUTTENAHALLI | F13 | 11 KV Feeder DTC TC 65, TC 66, EX HT, Ford HT, HT 19, TC 704, TC 68 | Conversion of 11KV OH to UG Line for F13 ( Puttenahalli Muss) Venkatala BLR Feeder in Yelahanka Old Town O&M 19A of C7 Sub Division, Hebbal Division | CAPEX |  |  | 06-09-2021 | NH From Kogilu circle to Bagalur circle |  |  | 10:00 | 17:00 | 7:00
29 | NORTH | HEBBAL | C7 | Yelahanka new town | KHB | F5 | 11 KV Feeder DTC Saratha Nagar , And Ambedkar Colony | Estimate for Conversion of Existing11 KV HT OverHead Line into HT UG cable pertaining to F-5 Feeder KHB MUSS, Feeding to different locations of C-7 Sub-division ,under Phase-II on total Turnkey Basis Under RC-10. | CAPEX |  |  | 06-09-2021 | Saratha Nagar , And Ambedkar Colony |  |  | 10:00 | 17:00 | 7:00
30 | NORTH | HEBBAL | C7 | Yelahanka old town | ATTUR | F10 | 11 KV Feeder DTC Mini VidhanSoudha Road | Conversion of 11KV OH to UG Line for F10 ( Yelakhanka Muss) IAF BLR- Feeder in Yelahanka Old Town O&M 19A of C7 Sub Division, Hebbal Division | CAPEX |  |  | 06-09-2021 | MiniSoudha Road |  |  | 10:00 | 17:00 | 7:00
31 | NORTH | HEBBAL | C8 | Sahakar nagar | SKN | F1 | 11 kv Branch lineAll Dtcs | OH to UG | CAPEX |  |  | 06-09-2021 | SAHAKARANAGAR A BLOCK |  |  | 9:00 | 17:00 | 8:00
32 | NORTH | HEBBAL | C8 | Sahakar nagar | SKN | F5 | 11 kv Branch lineAll Dtcs | OH to UG | CAPEX |  |  | 06-09-2021 | G K V K LAYOUT, YASHODANAGAR |  |  | 9:00 | 17:00 | 8:00
33 | NORTH | HEBBAL | C8 | Sahakar nagar | SKN | F7 | 11 kv Branch lineAll Dtcs | OH to UG | CAPEX |  |  | 06-09-2021 | AMRUTHAHALLI, JAKKUR, TELECOM LAYOUT |  |  | 9:00 | 17:00 | 8:00
34 | NORTH | HEBBAL | C8 | Sahakar nagar | SKN | F12 | 11 kv Branch lineAll Dtcs | OH to UG | CAPEX |  |  | 06-09-2021 | SAHAKARANAGAR C BLOCK |  |  | 9:00 | 17:00 | 8:00
35 | NORTH | HEBBAL | C8 | Sahakar nagar | SKN | F20 | 11 kv Branch lineAll Dtcs | OH to UG | CAPEX |  |  | 06-09-2021 | THIRUMENAHALLI VILLAGE, KOGILU |  |  | 9:00 | 17:00 | 8:00
36 | NORTH | HEBBAL | C8 | JAKKUR | SKN | F14 | 11 kv Branch line DTC 718719720721 | CONVERTION OH/UG | CAPEX |  |  | 06-09-2021 | SAMPIGEHALLI |  |  | 10:00 | 17:00 | 7:00
37 | NORTH | HEBBAL | C8 | JAKKUR | SKN | F22 | 11 kv Branch line DTC 243244245 | CONVERTION OH/UG | CAPEX |  |  | 06-09-2021 | MCECHS LAYOUT |  |  | 10:00 | 17:00 | 7:00
38 | NORTH | HEBBAL | C8 | JAKKUR | SKN | F21 | 11 kv Branch line DTC 475418106805 | CONVERTION OH/UG | CAPEX |  |  | 06-09-2021 | KOGILU LAYOUT |  |  | 10:00 | 17:00 | 7:00
39 | NORTH | HEBBAL | C8 | JAKKUR | shoba | F10 | 11 kv Branch line DTC 690, 691, 692 | CONVERTION OH/UG | CAPEX |  |  | 06-09-2021 | HEGDENAGARA |  |  | 10:00 | 17:00 | 7:00
40 | NORTH | HEBBAL | C8 | JAKKUR | shoba | F11 | 11 kv Branch line DTC 100, 99, 846 | CONVERTION OH/UG | CAPEX |  |  | 06-09-2021 | THIRUMENAHALLI |  |  | 10:00 | 17:00 | 7:00
41 | NORTH | JALAHALLI | C9 | VIDYARANYAPURA | YELAHANKA | F2 | 11 KV Feeder DTC full feeder |  | Maintenance Work |  |  | 06-09-2021 | VIDYARANYAPURA |  |  | 11:00 | 14:00 | 3:00
42 | NORTH | JALAHALLI | C9 | VIRUPAKSHAPURA | SAHAKARNAGAR | F09 | 11 KV Feeder DTC |  | Maintenance Work |  |  | 06-09-2021 | CANARA BANK L/O,DHANLAKSHMI L/O,THINDLU MAIN ROAD ,SIR MV L/O |  |  | 11:00 | 15:00 | 4:00
43 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | CB1 | O&M-4 | Nallimaradahalli | F13 S Gollahalli | full line | Link line work | Maintenance Work |  |  | 06-09-2021 | S Gollahalli Panchath Limits,Kethenahalli,Reddygollavarahalli,Sadenahalli,Rayappanahalli, |  |  | 10:00 | 14:00 | 4:00
44 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | CB1 | O&M-4 | Nallimaradahalli | F4 Kethenahalli | full line | Link line work | Maintenance Work |  |  | 06-09-2021 | S Gollahalli Panchath Limits,Kethenahalli,Reddygollavarahalli,Sadenahalli,Rayappanahalli, |  |  | 10:00 | 14:00 | 4:00
45 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | CB1 | O&M-4 | Nallimaradahalli | F3 Ramadevaragudi | full line | Link line work | Maintenance Work |  |  | 06-09-2021 | S Gollahalli Panchath Limits,Kethenahalli,Reddygollavarahalli,Sadenahalli,Rayappanahalli, |  |  | 10:00 | 14:00 | 4:00
46 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | CB2 | MANDIKAL | Peresandra MUSS | F10-Mandikal Express | full line | Estimat for APS to Irrigation pump set installation in the name of Dhanalakshmamma W/o Papanna, Sy No 332 at Manipura Village in Mandikal section RSD CBPUR | CAPEX & Other Works | OM No:-6256-58 dtd:-25-10-2019 |  | 06-09-2021 | All villages of F10-Mandikal Exp |  |  | 11:00 | 15:00 | 4:00
47 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | CB2 | MANDIKAL | Peresandra MUSS | F10-Mandikal Express | full line | Estimat for APS to Irrigation pump set installation in the name of Narayanappa S/o Gangappa, Sy No:95 at Gundlamandial Village in Mandikal section RSD CBPUR | CAPEX & Other Works | OM No:-1709-11 dtd:-19-07-2021 |  | 06-09-2021 | All villages of F10-Mandikal Exp |  |  | 11:00 | 15:00 | 4:00
48 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | CB2 | PERESANDRA | Somenahalli MUSS | F6-Thumukunte | full line | Re-alinghment of HT line of F-6 Thumakunte feeder at Lakshmisagara Lake. | CAPEX & Other Works | S-13786 dtd:21-12-2020 |  | 06-09-2021 | All villages |  |  | 11:00 | 16:00 | 5:00
49 | DAVANAGERE CIRCLE | CHITRADURGA DIVISION | CD2 | Bharamasagara | BIDARKERE_66 | F05Yalogodu | 11 KV Feeder | Maintenance work | Maintenance Work |  |  | 06-09-2021 | Pamarahalli,Hullehalu,Hullehalu Gollarahatti,Yelagodu,Yelagodu Myasarahatti,Basthihalli,Isamudra,Kodirangavanahalli,Nallikatte,Ajjapanahalli,Azadnagara,Gollarahalli,Isamudra hosahatti,Nallikatte Gollarahatti,Nallikatte Hosagrama,Sultanipura,Aralakatte,Isamudra Gollarahatti,Kakbalu,Kalgere,Chowlihalli Gollarahatti, |  |  | 14:00 | 16:00 | 2:00
50 | DAVANAGERE CIRCLE | CHITRADURGA DIVISION | CD2 | Hiregutanur | PANDARAHALLI_66 | F08NJY Sollapura | 11 KV Feeder | Maintenance work | Maintenance Work |  |  | 06-09-2021 | Erajjanahatti, Janukonda, Karihatti, Nayakara Sollapura, Sollapura,Singapura |  |  | 13:00 | 15:00 | 2:00
51 | RAMANAGARA | CHANDAPURA DIVISION | CH1 | Hebbagodi | Hulimangala | F1 Margondanahalli |  | Tree trimming, Maintenance of GOS, loose span restrining, Bent pole straightening | Maintenance Work |  |  | 06-09-2021 | Margondanahalli Village , Shikaripalya Village |  |  | 10:00 | 12:00 | 2:00
52 | RAMANAGARA | CHANDAPURA DIVISION | CH1 | Bommasandra | Yarandahalli | F21 R K Town ship |  | Tree trimming, Maintenance of GOS, loose span restrining, Bent pole straightening | Maintenance Work |  |  | 06-09-2021 | Yarandhalli Village , R K Township |  |  | 10:00 | 12:00 | 2:00
53 | DAVANAGERE CIRCLE | HIRIYUR DIVISION | CK1 | O&M-1 | CHALLAKERE | F8 BALLERY ROAD | 11 KV Feeder | SHIFTING OF 11KV LINE | Maintenance Work |  |  | 06-09-2021 | BALLERY ROAD, CHITHRAIAHNAHATTY, JAFFER SHARIF LAYOUT, GORLAKATTE, AND VALMIKI NAGARA AND SOROUNDING AREAS. |  |  | 10:00 | 17:30 | 7:30
54 | DAVANAGERE CIRCLE | HIRIYUR DIVISION | CK1 | O&M-1 | CHALLAKERE | F6 NANNIVALA AND F11 VEERADIMMANAHALLY NJY | 11 KV Feeder | LINK LINE WORK | Maintenance Work |  |  | 06-09-2021 | UNDER NANNIVALA PANCHAYATAH VILLAGES,VEERADIMMANAHALLI, BORAPPANAHATTY, MARADIHATTY, AND SOROUNDING VILLAGES. |  |  | 10:00 | 17:30 | 7:30
55 | RAMANAGARA | RAMANAGARA DIVISION | CP1 | O&M -I | 66/11 KVMUSS , Channapatna | F7 SS MILL |  | For preventive maintainance of HT and LT lines & DTCs | Maintenance Work |  |  | 06-09-2021 | R.K Badavane, Manjunatha badavane, Mangalavarapete, Chikkamaluru, maruthi badavane, kote |  |  | 10:00 | 15:00 | 5:00
56 | RAMANAGARA | RAMANAGARA DIVISION | CP2 | Kodamballi | AKKUR | F-10 AMBADAHALLI |  | MAINTENANCE | Maintenance Work |  |  | 06-09-2021 | AMBADAHALLI, MADAPURA |  |  | 11:30 | 13:40 | 2:10
57 | BRC | HOSAKOTE | DH1 | Budigere | Budigere | F-8 GANGAVARA | 11KV Feeder | Maintance work with Jungle trimming | Maintenance Work |  |  | 06-09-2021 | nallu. Jonahalli .reddihalli kaggalahalli nagenahalli |  |  | 9:00 | 12:00 | 3:00
58 | BRC | HOSAKOTE | DH1 | O&M 1 | 66/11KV DEVANAHALLI | F06 CHAPPARADAKALLU | 11 KV Feeder | MAINTAINCE WORK | Maintenance Work |  |  | 06-09-2021 | CHAPARADAKALLU,DODDACHEEMANAHALLI,LINGADHEERAGOLLAHALLI |  |  | 11:00 | 13:30 | 2:30
59 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | DV2 | O&M - 4 | YARAGUNTE | SJM | 11 KV Feeder | DSCL DAVANGERE | Maintenance Work | - |  | 06-09-2021 | SJM NAGARA, SMK NAGARA, BABU JAGAJIVANA NAGARA BASHA NAGARA MANDAKKI BATTI,AND OTHERS AREA. |  |  | 10:00 | 16:00 | 6:00
60 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | DV3 | Elebethur | Yaragunta_66 | F14-Yaragunta | 11 KV Feeder | Maintenance of Microplan feeder-Load Balancing of DTCs | Maintenance Work | - |  | 06-09-2021 | Yaragunta, Ahokanagara, Karur |  |  | 10:00 | 17:00 | 7:00
61 | EAST | INDIRANAGAR | E10 | BGH | NGEF | F17 NGEF | 11 kv Branch line Madonna School TC, Salem Track TC, Shiva Temple TC | Dismantling | CAPEX | 405/19/OH to UG/IND/14-192/F-3134 |  | 06-09-2021 | Uday Nagar |  |  | 10:00 | 16:00 | 6:00 | Full Feeder LC
62 | EAST | INDIRANAGAR | E11 | Akshay Nagar | ITI | F1 IPDS | 11 kv Branch Line 1.New 5 way RMU 03 Near Lake VL-03 to F1 SP CM SSVR APPT 100 KVA. 2.F1 SP CM SSVR APPT 100 KVA to F1 SP FDTC - 240 POLICE MUNIRAJA 250 KVA. 3.F1 SP FDTC - 240 POLICE MUNIRAJA 250 KVA to F1 SP FDTC BUNFACTORY 250 KVA. 4.F1 IPDS SP CM BUSHRESTA L/O - SDTC - 419 to F1 IPDS FDTC - 442 - PRASTIHANA L/O 250KVA. 5.F1 IPDS FDTC - 442 - PRASTIHANA L/O 250KVA. 6. F1 IPDS VINAYAKA GREEN PARK FDTC 341-A - 250KVA | 1.GOS & 95 Sqmm Charging. 2. 240 sqmm Cable Charging | CAPEX | 405/20/OH TO UG/IND/14-192/F-3135/31.03.2020 |  | 06-09-2021 | Varnasi Road, PRASTIHANA L/O, Sunny L/O |  |  | 10:00 | 16:00 | 6:00
63 | EAST | INDIRANAGAR | E11 | Bhattarhalli | ITI | F7 KIADB | 11 kv Branch Line & LT Line With DTC 1. RMU-15 V/L-01 to F7 FDTC OPP RELIANCE FRESH 2.F7 FDTC OPP RELIANCE FRESH to F7 SDTC ALYSEEN 3.F7 SDTC ALYSEEN to F7 SDTC SAI VIHAR APPT 4.F7 SDTC SAI VIHAR APPT to F7 SDTC SASTHA SADANAM | GOS&95 Sqmm Cable Charging | CAPEX |  |  | 06-09-2021 | Subhash nagar , TC palya , Bhatrahalli, halehalli , garden city college sorounding areas |  |  | 10:00 | 16:00 | 6:00
64 | EAST | WHITE FIELD | E12 | MAHADEVAPURA | ITI | F09-MAHADEVAPURA. | 11 KV Feeder | Conversion from LT TO ht WITH 250KVA HT Power Supply bearing R.R No: 4ECP7116 in favour of M/s. Indian Oil Corporation Ltd, Mahadevapura, Bengaluru-560048 Under Self Execution. | CAPEX & Other Works | E12/C-357/1593274 Dated: 26/03/2021 |  | 06-09-2021 | B. Narayanapura, Mahadevapura |  |  | 11:00 | 14:00 | 3:00
65 | EAST | SHIVAJINAGAR | E5 | Lingarajapura | BANASWADI | F09 | 8 | HT UG cable raising and structure work uinder OH to UG conversion project | CAPEX | G-45751 |  | 06-09-2021 | Nanjundappa Road, Ramaiah Layout |  |  | 10:00 | 17:00 | 7:00 | -
66 | EAST | INDIRANAGAR | E6 | INR | Leela S/S | F09 LEELA | 11 kv Branch line 17th Cross TC, 18th Cross TC & JP Building TC | HT UG Cable commissioning | CAPEX | 405/19/OH to UG/IND/14-192/F-3133 |  | 06-09-2021 | ESHWARA LAYOUT |  |  | 10:00 | 16:00 | 6:00
67 | EAST | INDIRANAGAR | E6 | JBN | HAL S/S | F6 HAL | 11 kv Branch line TC 763 | LT UG Cable commissioning Dismantling | CAPEX | 405/20/OH to UG/IND/14-192/G-1022 |  | 06-09-2021 | DTC 763 JBN BUS STAND |  |  | 10:00 | 16:00 | 6:00
68 | EAST | SHIVAJINAGAR | E8 | RS Palya | Banasawadi | F-17 | feeder | Maitanance Work | Maintenance Work |  |  | 06-09-2021 | RS Palya, Subbaiah Palya, Kammanahalli Main Road, ITC Main Road, Jayalakshmi School Road |  |  | 11:00 | 15:00 | 4:00 | -
69 | EAST | SHIVAJINAGAR | E9 | Nagawara2 | YELLARBANDE_66 | F03-DASARAHALLI | 40 | MAINTENANCE | Maintenance Work |  |  | 06-09-2021 | Coffee Board Layout, Mariyannapalya, Dynasty Layout, Dasarahalli main road, Kaveri layout |  |  | 11:00 | 15:00 | 4:00 | -
70 | EAST | SHIVAJINAGAR | E9 | Kothanur | Geddalahalli | F-07 | TC - 815 | OH to UG Conversion | CAPEX | 1627944 & 01.04.2021 |  | 06-09-2021 | AVALAHALLI MAIN ROAD |  |  | 0:00 | 120:00 | 120:00 | -
71 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | GB1 | VIDHURASHPATHA | Vidhurashwatha 66/11 | F11 JAGAREDDYHALLI | 11 kv Branch line DTC 33 | GOS Maintainance,Jungle cutting& LOOSE SPAN Restringing | Maintenance Work |  |  | 06-09-2021 | Jagareddyhalli , melya, ramachanadrapura , gowdasandra, huchchodanahalli, chittavalahalli, dinnenahalli, hunasenahalli, |  |  | 14:00 | 16:00 | 2:00
72 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | GB1 | HOSUR | Gowribidanuru 220/66/11 | F14 MUDUGERE | 11 kv Branch line DTC 87 | GOS Maintainance,Jungle cutting& LOOSE SPAN Restringing | Maintenance Work |  |  | 06-09-2021 | kadalaveni, mudugere, KT Halli, Kenkarte, Kachamachanahalli , channenahalli, dimmagattanahalli |  |  | 14:00 | 16:00 | 2:00
73 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | GD1 | VATADA HOSAHALLI | Vatadahosahalli_66 | F02-D.Palya | 11 kv Branch line DTC 30 | GOS Maintainance,Jungle cutting | Maintenance Work |  |  | 06-09-2021 | Hulikunte,Narasapura,Suryanayakanahalli,Ontimanehalli,Bodabandanahalli. |  |  | 9:00 | 12:00 | 3:00
74 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | JL1 | O&M - 2 and Bilichodu | Jagaluru_66 | F11-Devikere | 11 KV Feeder | Maintenance work | Maintenance Work | - |  | 06-09-2021 | Rastemachikere, Malammanahalli, Bullenahalli, Baggenahalli, Maharajanahatti, Shettigondanahalli, Devikere, Hire arakere, chikka arakere, Sagalagatte, Medaginakere, Koratigere, Somenahalli, Gokulahatti, Guttidurga, Halavadandi, Kasturipura and Vyasagondanahalli |  |  | 10:00 | 18:00 | 8:00
75 | RAMANAGARA | CHANDAPURA DIVISION | JN1 | Jigani | 66/11KV Hulimangala | F7 Agri |  | GOS Maintanance works and tree trimming works | Maintenance Work |  |  | 06-09-2021 | IP Sets of Hulimangala |  |  | 10:00 | 14:00 | 4:00
76 | RAMANAGARA | CHANDAPURA DIVISION | JN1 | Bannerughatta | 66/11KV Gollahalli | F3 Mantapa |  | GOS Maintanance works and tree trimming works | Maintenance Work |  |  | 06-09-2021 | Mantappa, Lakshmipura, Hullikasanahalli, sakalavara, Hullahalli, Chinnaiahnapalya, C K Palya, Kalkere, Gollahalli, Sampangiramanagara. |  |  | 10:00 | 14:00 | 4:00
77 | WEST | KENGERI | K1 | Kumbalagudu | KUMBALAGODU_66 | F07-DEVIKIRAN | DTC DT-08,461,22 | TREE TRIMMING | Maintenance Work |  |  | 06-09-2021 | DEVIKIRAN FACTORY, VISHWAS FACTORY |  |  | 10:00 | 12:00 | 2:00
78 | WEST | KENGERI | K1 | Kengeri | RR Nagara | F3 | Spur Line | Estimate for Conversion of HT Overhead to HT UG Cable for F3 Feeder BWSSB Feeder emanating from RR Nagara MUSS in O&M U-22 kengeri of K1 Sub Dvn, Kengeri Dvn. Under (RC 14) Total turnkey basis | CAPEX | I-15017 I-15217 I-15317 |  | 06-09-2021 | Balaji Layout Vijayshree Layout Mukambika Layout BHEL Layout |  |  | 9:00 | 17:00 | 8:00
79 | WEST | KENGERI | K1 | Ramohalli | Bandemutt Station | F5 - Hunasemaradapalya | DTC DT-309 | Tree trimming,DTC maintenance | Maintenance Work |  |  | 06-09-2021 | Archakara L/o |  |  | 10:30 | 12:30 | 2:00
80 | WEST | KENGERI | K2 | Andrahalli | NG Halli | F-7-LT | Spur Line TC-57,NFTC Mamata,87 | Estimate for conversion of LT OH to LT AB Cable of F07 feeder from NG Halli muss in Andrahalli O&M-2, K2 Sub divin, Kengeri Divin, Bangalore-91 | CAPEX | I-15407 I-15707 I-15607 Dt:13-01-2021 |  | 06-09-2021 | T.G. PALYA GOV.SCHOOL |  |  | 10:00 | 17:00 | 7:00
81 | WEST | KENGERI | K2 | Herohalli | Byadarahalli | F-3 -LT | Spur Line TC-217,272 | Estimate for conversion of LT OH to LT AB Cable of F3 feeder from Byadarahalli muss in Herohalli O&M-1, K2 Sub divin, Kengeri Divin, Bangalore-91 | CAPEX | I-15404 I-15704 I-15604 ,DT:13-01-2021 |  | 06-09-2021 | Hosahalli Road |  |  | 10:00 | 17:00 | 7:00
82 | WEST | KENGERI | K2 | Andrahalli | NG Halli | F-6 -HT | Spur Line TC-148,147,85 | Estimate for conversion of 11KV OH Line to HT UG Cable of F6 feeder from NG Halli muss in Andrahalli O&M-2, K2 Sub divin, Kengeri Divin, Bangalore. | CAPEX | I-15418 I-15618 I-15718 ,DT:25-02-2021 |  | 06-09-2021 | Floormill andhrahalli,Krishnappa building VM nagara |  |  | 10:00 | 17:00 | 7:00
83 | WEST | KENGERI | K4 | KST | B MUTT | F3 | Full Feeder | Estimate for Conversion of HT Overhead to HT UG Cable forF3 Feeder KHB Feeder BANDEMUTTA MUSS in O&M U21K4 Sub Dvn, Kengeri Dvn.RC 14 | CAPEX | I-15033 I-15233 I-15333 Dt:22.02.2021 |  | 06-09-2021 | KHB Diamond |  |  | 9:00 | 17:00 | 8:00
84 | WEST | KENGERI | K4 | RR Layout | SIR MV | F2 | Spur Line | Estimate prepared for convertion of OH to HT UG Cable for F2Feeder Maruthinagara of Sir M V MUSS in O&M-24 RRLayoutof K-4 Subdivison Nagadevanhalli Bangalore-56 | CAPEX | I-15031 I-15231 I-15331 Dt:25.02.2021 |  | 06-09-2021 | Ullal Nagar, Maruti nagar |  |  | 9:00 | 17:00 | 8:00
85 | WEST | KENGERI | K4 | Anjananagara | SIR MV | F11 | DTC | Estimate For Conversion of LT Overhead line in to LT ABCable in LT lines of F-11 Feeder(BDA 5th Block) feeding FromSir M.V MUSS in O&M-1, Anjananagara Unit of K-4 SubDIvision, Kengeri Division (under Total Turnkey RC-14) | CAPEX | I-15016 I-15216 I-15316 Dt:12.02.2021 |  | 06-09-2021 | Mallathali Layout, East West College Road, Dwarkabasa Road, KLE College Road |  |  | 9:00 | 17:00 | 8:00
86 | TUMKUR CIRCLE | MADHUGIRI DIVISION | KH1 | O&M-1 | Kodigenahalli | F03 Kodigenahally | DTC 23 | For replacement of existing 11 KV overhead lines by 11 KV Covered condcutor from Cremation cut point to 25 KVA water supply TC of F03 Feeder in O&M-1 | CAPEX | S-5563 |  | 06-09-2021 | Kodigenahalli |  |  | 10:00 | 17:00 | 7:00
87 | TUMKUR CIRCLE | TUMKUR DIVISION | KYT | Honnudike | 66/11kV MUSS Honnudike | HNF-09 CNNL | 11 KV Feeder | Jungle cutting Maintenance work from HNF-09 CNNL feeder | Maintenance Work |  |  | 06-09-2021 | Water Supply Dedicated Feeder |  |  | 10:00 | 18:00 | 8:00
88 | KOLAR CIRCLE | KGF DIVISION | MB1 | AVANI | AVANI | F2,F3, | 11 KV Feeder DTC 45 | For Shifting of HT/LT Line passing due to NH234 road widening from Machanahalli cross to Chapurahalli kere limits on request of Somanna s/o Yamanna Vijalapura. | Maintenance Work |  |  | 06-09-2021 | KR Circle,Devarayasamudra. |  |  | 13:00 | 17:00 | 4:00
89 | KOLAR CIRCLE | KGF DIVISION | MB1 | NANGLI & M N HALLY | NAGALI | NF16 | 11 KV Feeder DTC 62 | 11 KV LINES R&M | Maintenance Work |  |  | 06-09-2021 | THATHIKAL VADDAHALLI |  |  | 11:00 | 12:00 | 1:00
90 | KOLAR CIRCLE | KGF DIVISION | MB1 | AVANI | Mulbagal | F6,F8,F9 | 11 KV Feeder DTC 89 | 11 KV LINES R&M | Maintenance Work |  |  | 06-09-2021 | YALAGONDAHALLI ,CHIYANDAHALLI,avani,Diguragadahalli, |  |  | 10:30 | 12:00 | 1:30
91 | KOLAR CIRCLE | KGF DIVISION | MB1 | THAYLUR | Thaylur | F1,F2,F7,F8,F5 | 11 KV Feeder DTC 90 | 11 KV LINES R&M | Maintenance Work |  |  | 06-09-2021 | MITHAKAPALLI,DOOLAPALLI |  |  | 11:00 | 12:00 | 1:00
92 | KOLAR CIRCLE | KGF DIVISION | MB1 | O&M2 | Mulbagal | F1,F2,F6, | 11 KV Feeder DTC 90 | JUNGLE CUTTING DTC MAINTAINANCE | Maintenance Work |  |  | 06-09-2021 | KHB COLONY, CHANNAPURA AREA. |  |  | 11:00 | 12:00 | 1:00
93 | KOLAR CIRCLE | KGF DIVISION | MB1 | O&M2 | H.Gollahalli | F5,F6,F8,F7 | 11 kv Branch line DTC 4 | For aps to mws Thavarakere | CAPEX & Other Works |  |  | 06-09-2021 | Thavarakere |  |  | 13:00 | 15:00 | 2:00
94 | KOLAR CIRCLE | KGF DIVISION | MB1 | O&M2 | H.Gollahalli | F2,F6,F7,F8 | 11 kv Branch line DTC 54 | Est for evacuation of new link to GF4 Vommasandra feeder in O&M-II Sec. | Maintenance Work |  |  | 06-09-2021 | Vommasandra ,KOLADEVI, Kalikere,H gollahali, Sangasandra, Mathagatta |  |  | 0:00 | 0:00 | 0:00
95 | KOLAR CIRCLE | KGF DIVISION | MB1 | BYRKUR | MULBAGAL | F4 | 11 KV Feeder DTC 130 | JUNGLE CUTTING DTC MAINTAINANCE | Maintenance Work |  |  | 06-09-2021 | BYRAKUR AREA |  |  | 11:00 | 13:00 | 2:00
96 | KOLAR CIRCLE | KGF DIVISION | ML1 | MASTHI & TEKAL | masthi&Tekal | F-10 thoralakki& F-11 Nootway | 11 kv Branch line | Est for APS to 10HP Power installation for Poultry form in the name of Smt.Gowramma W/o late Nagappa at Usarhalli in Masthi Sec. 2)Tree trimming and maintainess | Maintenance Work |  |  | 06-09-2021 | usarahalli |  |  | 10:00 | 12:00 | 2:00
97 | NORTH | PEENYA | N5 | SHETTYHALLI | WELCASTSTEEL_66 | F1- GARISSION ENGINEER | FULL FEEDER DTC | OH to UG WORK converrison work DTC wise | CAPEX | H-1919 & DT-13.01.2021 |  | 06-09-2021 | RAVINDRANAGAR,SANTOSHNAGARA, AYYAPPA LAYOUT AIRFORCE. |  |  | 10:00 | 17:30 | 7:30
98 | NORTH | PEENYA | N5 | SHETTYHALLI | MEILAYOUT_66 | Fdr:7 PIPE LINE T-DASARAHALLY | DTC TC71 & TC 237 | OH to UG PENDING WORK converrison work DTC wise | CAPEX |  |  | 06-09-2021 | Kalyananagar, Pipe line road,1st main road |  |  | 10:00 | 17:30 | 7:30
99 | NORTH | PEENYA | N5 | T.DASRAHALLI | WELCASTSTEEL_66 | F09 -Ramesh Road | DTC NO-116,13,14STRINGING of LT ABC | STRINGING of LT ABC | CAPEX |  |  | 06-09-2021 | Bharathi theatre road Nrupathunga road, coconut garden, SM road,Krishna hospital ,TVS show room road , |  |  | 10:00 | 18:00 | 8:00
100 | NORTH | PEENYA | N5 | T.DASRAHALLI | MEILAYOUT_66 | F06-TUMKUR MAIN ROAD | DTC NO-54Charging of LT ABC | Charging of LT ABC | CAPEX |  |  | 06-09-2021 | Maheshwari nagara |  |  | 10:00 | 18:00 | 8:00
101 | NORTH | PEENYA | N7 | Nandini layout | NANDINI LAYOUT | F1 NANDINI LAYOUT | 11 kv Branch line DTC 03 NOS | OH TO LT AB CABLECONVERSION WORK | CAPEX | 2020/PD/14-1927/ H-1891/13.11.20 |  | 06-09-2021 | NANJUNDESHWARA NAGAR SURROUNDING AREA |  |  | 10:00 | 18:00 | 8:00
102 | NORTH | PEENYA | N7 | Nandini layout | NANDINI LAYOUT | F2 NANDINI LAYOUT | 11 kv Branch line DTC 03 NOS | OH TO LT AB CABLECONVERSION WORK | CAPEX | 2020/PD/14-1927/ H-1892/13.11.20 |  | 06-09-2021 | MARAPPANA PALYA & SURROUNDING AREA |  |  | 10:00 | 18:00 | 8:00
103 | NORTH | PEENYA | N7 | Mahalakshmi layout /kurubarahalli | MAHALAKSHMI LAYOUT | F5 HAMSASAGAR | 11 kv Branch line DTC 02 NOS | OH TO LT AB CABLECONVERSION WORK | CAPEX | 2020/PD/14-1927/ H-1916/13.01.21 |  | 06-09-2021 | Mico layout, J.C.Nagar, Jayadurga Choultry Surrounding Area |  |  | 10:00 | 18:00 | 8:00
104 | WEST | RAJAJINAGAR | N8 | NAGARABHAVI | CHANDRALAYOUT | F-07 | 941,872,512 | Conversion of 11KV Overhead line into HT Ug Cable inFeeder CL F7 (O&M Nagarbhvai) N8 Sub Division,Rajaji nagar Division Bangalore West Circle, BMAZ (South), BESCOM under PHASE-I on Total turnkey under Rate Contract (RC.05) on Percentage basis quoting. | CAPEX | 2020/RN/14-1927/N-106353/12.01.2022 |  | 06-09-2021 | GANGAMMA GARDEN MALAGALA | 2 | 3500 | 10:30 | 17:30 | 7:00 | Works includes Srtinging of LT ab Cable one day and connecting servicing connections and load balancing one day
105 | NORTH | JALAHALLI | N9 | Soladevanahalli | Soldevanhalli MUSS | F-8 | 11 KV Feeder DTC | 11 KV Maintenance | Maintenance Work |  |  | 06-09-2021 | Sasveghatta Village,Shivkumar swamy layout |  |  | 10:00 | 13:00 | 3:00
106 | NORTH | JALAHALLI | N9 | Soladevanahalli | Soldevanhalli MUSS | F-6 | 11 KV Feeder DTC | 11 KV Maintenance | Maintenance Work |  |  | 06-09-2021 | Ganapathinagara, Ragavendra lay out, Andanappa lay out Shanthinagara, Guttebasaveswaranagara , Brothers colony |  |  | 10:00 | 13:00 | 3:00
107 | BRC | NELAMANGALA DIVISION | NM1 | Madanayakanalli | 66/11KV WIDIA | WF-7 | 11 KV Feeder DTC 32 | 11KV tree trimming and GOS maintainance | Maintenance Work |  |  | 06-09-2021 | T.G halli |  |  | 10:00 | 14:00 | 4:00
108 | SOUTH | JAYANAGAR | S1 | Jayanagar 8th Block | PBN | F02-PBN | DTC 26.136.35.63.36 | AB CABLE LAYING + CHARGING | CAPEX | 14.1927K-8761-28.6.21 |  | 06-09-2021 | 7th block, 7th west block, A K Colony |  |  | 10:00 | 17:30 | 7:30
109 | SOUTH | HSR | S12 | PANDURANGA NAGAR | South city | F04 | 11 KV Feeder DTC 20 | Preventive maintenance work | Maintenance Work |  |  | 06-09-2021 | Lakshmi layout, Govind nagar, Arekere Micolayout, fortis hospital, part of B.G.road , O Mkar Nagaraand surroundings |  |  | 10:30 | 15:30 | 5:00 | nil
110 | SOUTH | HSR | S13 | Electronic city | Malgudi | F02 | 11 KV Feeder DTC 4 | Sri. Shankar.K.L, No.43 & 57, Konappana Agrahara, Begur(H), Bangalore | Maintenance Work | 29.06.2020 |  | 06-09-2021 | new anand reddy lay-out , Govinda shetty palya , Electronic city phase-2 |  |  | 10:30 | 13:30 | 3:00
111 | SOUTH | HSR | S13 | Electronic city | Malgudi | F02 | 11 KV Feeder DTC 4 | Sri. Shankar.K.L, No.44, Konappana Agrahara, Begur(H), Bangalore | Maintenance Work | 29.06.2020 |  | 06-09-2021 | new anand reddy lay-out , Govinda shetty palya , Electronic city phase-3 |  |  | 10:30 | 13:30 | 3:00
112 | SOUTH | HSR | S13 | Electronic city | Malgudi | F02 | 11 KV Feeder DTC 15 | Tree trimming,Detoriated Jumps renovated @ Basavanagara road,GS Palya road. | Maintenance Work | Maintanance |  | 06-09-2021 | Basavanagara road,Govindshetty Palya road. |  |  | 10:30 | 13:30 | 3:00
113 | SOUTH | HSR | S13 | C.K.nagara | Naganathapura | F19 | 11 KV Feeder DTC 5 | Smt. Mohini Devi, #103, K.no.211/213, Doddanagamangala(V), Begur(H), Bangalore in C.K.Nagara O&M unit, S13 Subdivision. | Maintenance Work | 01.12.2020 |  | 06-09-2021 | DODDANAGAMANGALA VILLAGE |  |  | 10:30 | 16:30 | 6:00 | YES
114 | SOUTH | HSR | S13 | Singasandra | HSR | F16 | 11 KV Feeder DTC 1 | Sri. M. loganathan, no. 77/78, Sai medals, koodlu Bangalore | Maintenance Work | 27.07.2021 |  | 06-09-2021 | sai medals, koodlu |  |  | 11:00 | 13:00 | 2:00 | NO
115 | SOUTH | JAYANAGAR | S14 | JP NAGAR O&M | SARAKKI | F10 | 11 KV Feeder | LT ABC WORK | CAPEX | K-8788/13-08-2021 |  | 06-09-2021 | JP NAGAR 2ND PHASE , 3RD PHASE, 4TH PHASE,5TH PHASE , 15TH CROSS JP NAGAR, DOLLORS LAYOUT |  |  | 10:00 | 17:30 | 7:30
116 | SOUTH | JAYANAGAR | S15 | U-2 KATHRIGUPPE | AREHALLI_MUSS | F7-BHUVANESHWARI NAGARA | 11 KV Feeder 104, 135, 105, TC-501, 509 | conversion of 11KV structure work | CAPEX | J-8826/ 15.12.2020 |  | 06-09-2021 | Channammana acchukattu, KATHRIGUPPE, BSK 3RD STAGE |  |  | 10:30 | 17:30 | 7:00
117 | SOUTH | KORAMANGALA | S16 | SG PALYA | SJW | F8 | 11 KV Feeder | Micro Plan feeder,Tree Trimming &Maintance,providing GOS,top up transil oil,providing LT spacers,providing Grounding,DTC Wiring etc- | Maintenance Work |  |  | 06-09-2021 | Taverkere main Road |  |  | 9:30 | 12:30 | 3:00
118 | SOUTH | JAYANAGAR | S18 | U2 Chikkallasandra | Subramanyapura | F11 | 11 KV Feeder | 3GOS Structure Work | CAPEX | 1637737 30.01.2021 |  | 06-09-2021 | Uttarahalli main road |  |  | 10:00 | 17:00 | 7:00
119 | SOUTH | JAYANAGAR | S18 | U1 Poornaprajnanagar | RRNAGAR | F13 | 11 KV Feeder | O/H to HT UG | CAPEX | OH-UG/ 14:1927/ Ph-11/ RC-13/S18/ J-8963/15.12.2020 |  | 06-09-2021 | BSK 5TH STAGE |  |  | 10:00 | 17:00 | 7:00
120 | SOUTH | JAYANAGAR | S2 | U-2 SAMPANGI RAMANAGAR | BMTC | F10 | DTC DTC NO:224 | LT AB CABLE STRINGING | CAPEX | K-8773 DATE:28.6.2021 1884-88 DATE:09.07-2021 |  | 06-09-2021 | LALBHAG ROAD 1ST AND 2ND CROSS |  |  | 10:00 | 17:00 | 7:00
121 | SOUTH | JAYANAGAR | S2 | U-3 SHANTHINAGAR | AUSTIN TOWN | F04 | DTC DTC NO:302 | LT AB CABLE STRINGING | CAPEX | K-8765 DATE:28.6.2021 1824-28 DATE:09.07-2021 |  | 06-09-2021 | WELLINGTON STREER SURROUNDINGS |  |  | 10:00 | 17:00 | 7:00
122 | SOUTH | HSR | S20 | AGARA | HSR | F07 | 11 KV Feeder DTC 3 | CONVERSION OF O/H TO UG CABLE WORK-STRUCTURE WORK AND AB CABLE WORK | CAPEX | 14.192/L-13656 16.206/L-13756 DT:31.03.2020 |  | 06-09-2021 | 27TH MAIN , 1ST AND 2ND SECTOR, APWD AND NIFT COLLEGE SURROUNDINGS |  |  | 10:00 | 17:00 | 7:00
123 | SOUTH | KORAMANGALA | S3 | Murgeshpalya | AUSIN TOWN | F-02 | 11 KV Feeder DTC 100 | Feeder maintenance,Tree Trimming | Maintenance Work |  |  | 06-09-2021 | Domlure lay out ajja ajji road |  |  | 10:00 | 14:00 | 4:00 | AMAR JYOTHI F-09
124 | SOUTH | JAYANAGAR | S5 | ISRO layout | Subramanyapura | F-14 Adarsha II | 11 KV Feeder DTC144,DTC554,DTC525 | 3GOS Structure Work | CAPEX |  |  | 06-09-2021 | Vasantha Vallaba Nagar, Sarada Nagar, Maruthi Layout |  |  | 10:00 | 17:00 | 7:00
125 | SOUTH | JAYANAGAR | S5 | ISRO layout | ISRO layout | F-10 K.S layout Water Tank | 11 KV Feeder DT-129, DT-475, DT429, | 3GOS Structure Work | CAPEX | 14.1927/J-9036 |  | 06-09-2021 | Kumari Swami Layout,50ft Road,teachers Colony |  |  | 10:00 | 17:00 | 7:00
126 | SOUTH | JAYANAGAR | S6 | Puttenahalli Unit-5 | 66/11KV ELITA | F3-SHARADA NAGAR | 11 KV Feeder | RABBIT RELEASING | CAPEX | OH-UG/ Ph-11/ RC-06/14.1927/J-8830 dt15.12.2022 |  | 06-09-2021 | Jaraganahalli, MS Layout , GKM college road, Chikkaswamy l/o, Rajamma garden, Govind reddy l/o, part of rajeev gandhi rd |  |  | 10:00 | 17:30 | 7:30
127 | SOUTH | KORAMANGALA | S7 | PANATHUR | 66/11KV MUSS CESSNA | F11 PARDHANI | DTC 60 | Errection Of Spun Pole for arranging power supply to an extent of 107kw in favour of Smt.G. SARALA | Maintenance Work | 465/KMLD/20-21/S7/self-ex/109/2-03-21 |  | 06-09-2021 | Kaverappa Layout,panathur & SURROUNDINGS |  |  | 11:00 | 14:00 | 3:00 | F03 CESSNA
128 | SOUTH | JAYANAGAR | S9 | PADMANABHA NAGAR | Padmanabhanagar | F01-Banagiri Nagar | DTC TC-69 | LT AB Cable Laying+Charging | CAPEX | 14.1927/J-9008/17.12.2020 |  | 06-09-2021 | 6th Main Road,Banagiri Nagar Park Road BSK 3rd STAGE |  |  | 10:00 | 17:00 | 7:00
129 | SOUTH | JAYANAGAR | S9 | PADMANABHA NAGAR | Padmanabhanagar | F09-Padmanabhanagar | DTC TC-222 | LT AB Cable Laying+Charging | CAPEX | 14.1927/J-9033/15.03.2021 & 14.1927/J-9012/17.12.2020 |  | 06-09-2021 | Prathanaschool Utttahalli main RoAD |  |  | 10:00 | 17:00 | 7:00
130 | SOUTH | JAYANAGAR | S9 | BSK 2nd Stage | Padmanabhanagar | F10-Yarab Nagar | DTC TC-165 | LT AB Cable | CAPEX | 14.1927/J-9030/15.03.2021 & 14.1927/J-9014/17.12.2020 |  | 06-09-2021 | Teachers Colony BSK 2ND Stage |  |  | 10:00 | 17:00 | 7:00
131 | SOUTH | JAYANAGAR | S9 | BSK 2nd Stage | Padmanabhanagar | F13-Saroja Complex | 11KV Feeder/DTC TCNO -90,92,173,418,325 | 3 GOS Structure/LT AB Cable | CAPEX | 14.1927/J-9031/15.03.2021 & 14.1927/J-9013/17.12.2020 |  | 06-09-2021 | Brigade PETUNIA ,INDO AMERICAN,K.R Road BSK 2ND Stage |  |  | 10:00 | 17:00 | 7:00
132 | RAMANAGARA | KANAKAPURA DIVISION | SA1 | DODDALAHALLI | HAROBELE | F11-NALLAHALLI & F02 HAROBELE |  | MAINTENCE WORK | Maintenance Work |  |  | 06-09-2021 | NALLAHALLI,HAROBELE,JYOTHINAGARA,KADLEDODDI,SIPAYIDODDI |  |  | 11:00 | 13:00 | 2:00
133 | KOLAR CIRCLE | KOLAR DIVISION | SP1 | GOWNAPALLLI | 66/11KV ADDAGAL MUSS | AF-8Gandhinagar | 11KV Feeder DTC 1 | Arranging Power supply to LT-2 installation of Gangamma Temple, in the name of Secretary at Diguvachintapally village in Gownipally section S.V.Pura S/D | CAPEX & Other Works | C-38262/2-3-2021 |  | 06-09-2021 | MWS Borewell |  |  | 7:12 | 11:30 | 4:18
134 | KOLAR CIRCLE | KOLAR DIVISION | SP1 | GOWNAPALLLI | 66/11KV ADDAGAL MUSS | AF-8Gandhinagar | 11KV Feeder DTC 1 | Arranging Power supply to 15HP power supply to bore well for water bussiness in th name of KR KrishnaReddy S/O Ramappa at G Byapally in Gownipally section S.V.Pura S/D | CAPEX & Other Works | D-40480/30-6-2021 |  | 06-09-2021 | Byapally village |  |  | 7:12 | 14:30 | 7:18
135 | TUMKUR CIRCLE | TUMKUR DIVISION | TK1 | central section | Tumkur | Tumkur-1(TF-4) | 11 KV feeder | conversion of overhead by UG cable | CAPEX | U-31623/25.9.2018 |  | 06-09-2021 | barline road, bidarmale thota K.R extn |  |  | 11:00 | 17:00 | 6:00 | Partial feeder
136 | TUMKUR CIRCLE | TUMKUR DIVISION | TK2 | SARASWATHIPURAM | 66/11 KV Muss Tumkur | TF-1 Vijaya Nagara | 11 kv Branch line DTC 13 | Execution of the works of conversion of Overheads by UG cables for 11 kV Feeders, running new 11 kV UG cable for feeder load bifurcation, conversion of LT overhead line and service main by LT UG cables providing LT feeder piller boxes RMUs and other allied works and indicated in the tender documents in LOT-1 of Tumkur town of facilitating quality and reliable power supply on total turn key under percentage rate contract basis | CAPEX & Other Works | U-31643/20.11.18 |  | 06-09-2021 | C.S.I Layout |  |  | 11:00 | 17:00 | 6:00 | Govt.college field RMU VL1 charging along with DTC"s Commissioning
137 | TUMKUR CIRCLE | TUMKUR DIVISION | TK2 | SARASWATHIPURAM | MELEKOTE | MF1, MF2,MF10, MF11, MF12, MF4,MF5,MF9,MF30 | 11 KV Feeder DTC 383 | Smart City Ring Road Pole Shifting Work | CAPEX & Other Works | Work Om No EE(ELE)/AEE/O/TA32019-2020/5670.72/20-08-2019 Work Om No EE(ELE)/AEE/O/TA32019-2020/4204-07/09-07-2019 Work Om No EE(ELE)/AEE/O/TA32019-2020/4200-03/09-07-2019 Work Om No EE(ELE)/AEE/O/TA32019-2020/4196.99/09-07-2019 Work Om No EE(ELE)/AEE/O/TA32019-2020/4196.99/09-07-2019 Work Om No EE(ELE)/AEE/O/TA32019-2020/4216.19/09-07-2035 |  | 06-09-2021 | Melekote, Gangasandra, Tuda layout, Danah Palace, UGD, Tippunagara, Nazarabadh, Veerasagara, Kuripalya, Goodshed, Shanthinagara, Upparahalli, Sadhashivanagara, Amarajyothi Nagara, Kumutaiah Badavane, Ramajoyes Nagara, Saraswathipuram 1ST and 2nd stage, Banashankari 1st and 2nd stage, Yadava Nagara, Maralooru, Maralooru Janatha Colony,Pragathi Badavane, Geddalahally, Gubbi Gate, Kuntammana Thota Dibburu,BH Palya, PH Colony, Vinoba Nagara, EdgaMohalla, Hegade Colony, Tilak Park, Jaipura, KHB Colony, bandimane Choutry |  |  | 7:12 | 17:30 | 10:18
138 | TUMKUR CIRCLE | TUMKUR DIVISION | TK3 | KORA | 66/11kV MUSS Kora | F07-KORA,F5-BRAHMASANDRA,F8-KATTIGENAHALLI | 11 KV Feeder DTC 68 | Estimate for Evacuation of New linkline to KF7- Kora feeder from Kora MUSS to Hariyappanahalli GOS limits in Kora section | Capex | Y-101/15.03.2021 |  | 06-09-2021 | KORA ,CHIKKONAHALLY, KATENAHALLY , MASTIPALYA,HARIYAPPANAHALLY,BRAMHASANDRA,BURADAGATTA, |  |  | 10:00 | 15:00 | 5:00
139 | BRC | HOSAKOTE | VD1 | Sadahalli Gate | Begur_220 | F3 Begur | 11 kv Branch line DTC 253 | For carrying out feeder maintenance work | Maintenance Work |  |  | 06-09-2021 | Begur, Chikkanahalli, Kadyarpanahali, Mylanahalli, Bandikodigehalli |  |  | 11:30 | 13:30 | 2:00
140 | BRC | HOSAKOTE | VD1 | Vidya Nagar | Vidyanagara 66 KV | F7 Local | 11 kv Branch line DTC 193 | For carrying out feeder maintenance work | Maintenance Work |  |  | 06-09-2021 | Sonnapanahalli,Vidyanagara Cross,Kadiganahalli, Chikkajala |  |  | 11:30 | 13:30 | 2:00
141 | WEST | RR NAGAR | W1 | AVALAHALLI - 1 | BSK | F-13 | 11 KV Feeder DTC sptc | Convertion | CAPEX | E-56127/31.03.2020 |  | 06-09-2021 | 50 feet road gerinagar eranna gubndde avalhalli hosekereahalli main road , part muneshwara block SLV hotel area mithrukuta hotel backside |  |  | 10:00 | 18:00 | 8:00 | convertion of OVER HEAD to LT ABC the consumers pertains to perticular dtc is effected
142 | WEST | RR NAGAR | W1 | AVALAHALLI - 1 | BSK | F-13 | 11 KV Feeder DTC 66 | Convertion | CAPEX | E-56127/31.03.2020 |  | 06-09-2021 | KB colony |  |  | 10:00 | 18:00 | 8:00 | convertion of OVER HEAD to LT ABC the consumers pertains to perticular dtc is effected
143 | WEST | RR NAGAR | W1 | AVALAHALLI - 1 | BSK | F-13 | 11 KV Feeder DTC 134 | Convertion | CAPEX | E-56127/31.03.2020 |  | 06-09-2021 | Laxman appt |  |  | 10:00 | 18:00 | 8:00 | convertion of OVER HEAD to LT ABC the consumers pertains to perticular dtc is effected
144 | WEST | RR NAGAR | W1 | AVALAHALLI - 1 | BSK | F-13 | 11 KV Feeder DTC 132 | Convertion | CAPEX | E-56127/31.03.2020 |  | 06-09-2021 | Srinivas adiga |  |  | 10:00 | 18:00 | 8:00 | convertion of OVER HEAD to LT ABC the consumers pertains to perticular dtc is effected
145 | WEST | RR NAGAR | W1 | AVALAHALLI - 1 | BSK | F-13 | 11 KV Feeder DTC 125 | Convertion | CAPEX | E-56127/31.03.2020 |  | 06-09-2021 | Satyanarayana |  |  | 10:00 | 18:00 | 8:00 | convertion of OVER HEAD to LT ABC the consumers pertains to perticular dtc is effected
146 | WEST | RR NAGAR | W6 | BYATARAYANAPURA | Remco | F-4 | 11 KV Feeder DTC 29 | Releasing | Maintenance Work | F-55362/ 12-11-2020 |  | 06-09-2021 | venkateshwara slum |  |  | 10:00 | 18:00 | 8:00
147 | WEST | RR NAGAR | W6 | BYATARAYANAPURA | Remco | F-4 | 11 KV Feeder DTC 19 | Releasing | Maintenance Work | F-55362/ 12-11-2020 |  | 06-09-2021 | venkateshwara slum |  |  | 10:00 | 18:00 | 8:00
148 | WEST | RR NAGAR | W6 | BYATARAYANAPURA | Remco | F-4 | 11 KV Feeder DTC 3 | Releasing | Maintenance Work | F-55362/ 12-11-2020 |  | 06-09-2021 | venkateshwara slum |  |  | 10:00 | 18:00 | 8:00
149 | WEST | RR NAGAR | W6 | BYATARAYANAPURA | VRASHBAVATHI | F2 | 11 KV Feeder | MAINTAINANCE | Maintenance Work | F-55356 /2-11-2020 |  | 06-09-2021 | PANTHRPALYA |  |  | 10:00 | 18:00 | 8:00
150 | WEST | RR NAGAR | W7 | CHANNASANDRA | BSK | F15 BANGARAPPA NAGAR | DTC DTC 67 | Micro plan feeder | Maintenance Work |  |  | 06-09-2021 | Pushpagirinagara |  |  | 10:00 | 13:00 | 3:00
151 | TUMKUR CIRCLE | TUMKUR DIVISION | YD1 | Yediyur | Jiddigere 66/11 | Hulivana | Hulivana DTC 1 | Estimate for Shifting of HT Line at Shettibeedu Village in name of Gruswamy Petaining to Yadiyuru Section Yadiyuru SUB Division | CAPEX | 6.09.2021 |  | 06-09-2021 | Hulivana,Nagasandara,Jiddigere,Sheetibeedu,Hulipura,Ramanayakanapalya |  |  | 10:00 | 14:00 | 4:00
152 | WEST | RAJAJINAGAR | N8 | S G Kaval | Byadarahalli | F-08 | NA | Conversion from HT OH to HTUG Work | CAPEX | 2020/RN/14-1927/N-106361/12.01.2021 |  | 06-09-2021 | RHCS Layout, Annaporneshwari nagar, Health Layout, D Group Layout, Narasapura, Benachakal palya, Muddinapalya main road, Erana palya, Near reliance fresh gowramma Layout and sounding areas | 0 | 8450 | 10:30 | 17:30 | 7:00
153 | TUMKUR CIRCLE | MADHUGIRI DIVISION | KR1 | O&M-1 | Koratagere 66/11kV | F05 Koratagere Town, F18 Urdagere Cross, F01, F03, F04, F09, F06, F07 | DTC 66 | For Providing Switch phase the Street light Control Switch in Koratagere Town limits in O&M-1 Section | CAPEX | R-34482/12.02.2021 |  | 06-09-2021 | Koratagere Town |  |  | 10:00 | 17:00 | 7:00
154 | TUMKUR CIRCLE | TIPTUR DIVISION | TU1 | o&m1 | Talkere | F01 Mangikuppe F02 Talkere F03 Ayarahalli F06 Honkere NJY | 11 KV Feeder | Link line from Donkihalli Bare to Donkihalli G hatti Gate to reduce the over load of F03 overload Feeder | Maintenance Work | B-21401 30.01.2021 |  | 06-09-2021 | Talkere, Donkihalli G Hatti, Donkihalli, D Kalkere, Ayarahalli, Doddaghoraghatta, Chikkaghorghatta, Siddanahatti, Aladevarahatti,Harikaranahalli. |  |  | 10:00 | 17:00 | 7:00
155 | TUMKUR CIRCLE | TIPTUR DIVISION | TU1 | o&m2 | Turuvekere Talkere | F05 Puttamadihalli F04 Anemale F03 Ayarahalli F06 Honkere NJY F17 Badarikashrama | 11 KV Feeder | Reconducting Of Existing F04 Anemale Feeder and Reconducting Of DTC's | Capex | B-37874 09.03.2021 |  | 06-09-2021 | Talkere, Donkihalli G Hatti, Donkihalli, D Kalkere, Ayarahalli, aralikere, sunklapura, dwaranahalli, anemale, mangikuppe |  |  | 10:00 | 17:00 | 7:00
156 | TUMKUR CIRCLE | TIPTUR DIVISION | TU1 | o&m2 | Turuvekere | F1 Mallagatta F3 Hemavathi F8 Anekere F13 Turuvekere F15 Gonitumkur F16 Court | 11 KV Feeder | Shifting Of Poles in Dabbeghatta Road due Road Widening | Maintenance Work |  |  | 06-09-2021 | Turuvekere town, Marasarakottige Mallaghatta, kodigehalli, T Hosahalli, Anekere, Kolghatta, Chikkaturuvekere, Guddenahalli, |  |  | 10:00 | 18:00 | 8:00
157 | DAVANAGERE CIRCLE | HIRIYUR DIVISION | HY1 | HARIYABBE | PD KOTE_66 | F05-HALAGALADDI NJY ,F02-PD-KOTE | 11 KV Feeder | Running 11 Kv Line from Pd ko T0 muss to hoskere limits | Maintenance Work |  |  | 06-09-2021 | maddihally,P.D.Kote,Kanajanahally,Benakanahally,hoskere |  |  | 10:00 | 17:00 | 7:00
158 | DAVANAGERE CIRCLE | HIRIYUR DIVISION | HY1 | HARIYABBE | PD KOTE_66 | F05-HALAGALADDI NJY ,F02-PD-KOTE | 11 KV Feeder | Running 11 Kv Line from Pd ko T0 muss to Benakanahally limits | Maintenance Work |  |  | 06-09-2021 | maddihally,P.D.Kote,Kanajanahally,Benakanahally,hoskere |  |  | 10:00 | 17:00 | 7:00
159 | WEST | RAJAJINAGAR | N6 | 1- KAMAKSHI PALYA | Vijayanagar | F7 | TC-21,20,13,22,28,26,29,33,34,37,38,39,172,173,184,220,231,253,281,283,294,300,301,304,662,664,756,804,863,839,886 | ESTIMATE FOR CONVERSION OF LT OVERHEAD LINE TO LT AB CABLE IN F -07 FEEDER OF VIJAYA NAGAR MUSS IN O&M-01 OF N6 SUB DIVISION | CAPEX | 4330-38/ 30.11.2020 |  | 06-09-2021 | MANIVILLA GARDEN , KAMAKSHIPALYA, VINAYAKA NAGARA, SHIVAFARM, SHIVA TEMPLE , ANDANAPPA LAYOUT, MARIYAPPA ROAD, KAMAKSHIPALYA |  | 6500 | 10:30 | 17:30 | 7:00 | Work will be taken up as schelduled from 1ST SEP 2021
160 | WEST | RAJAJINAGAR | N6 | 3 - SUNKADAKATTE | SRIGANDHA KAVALU | F-6 | TC-542,222,904, 295,744,352,375,353,N6HT-72, 869, 890, 929, N6HT-104, 134, 774, 302, N6HT-33, 133, 581, 581, 740,327, 328, 349,942,860, 135, 852, 228, 895, 831,946, 916, 735, 684, 131, 157, 302, N6HT33, 133,581, 740, 327,328,943,818,N6HT7, 938, 850,816, 342, 126,215, 125,343, 341, 893,54 | ESTIMATE FOR CONVERSION OF HT OVERHEAD LINE TO HT UG CABLE IN F -06 FEEDER OF SRIGANDHA KAVALU MUSS IN O&M-02 OF N6 SUB DIVISION | CAPEX | N-106352/ |  | 06-09-2021 | LAKSHMANA NAGARA, SANJEEVINI NAGARA, VIGNESHWARA NAGARA, HEGGANAHALLI, HEGGANAHALLI CROSS, SUNKADAKATTE, PIPELINE RAOAD SUNAKADAKATTE. |  | 4000 | 10:30 | 17:30 | 7:00 | Work will be taken up as schelduled from 1ST SEP 2021
161 | WEST | RAJAJINAGAR | N8 | S G Kaval | S G Kaval | F-10 | NA | Conversion from HT OH to HTUG Work | CAPEX | 2020/RN/14-1927/N-106330/02.11.2020 |  | 06-09-2021 | RHCS Layout, Annaporneshwari nagar, Health Layout, D Group Layout and sounding areas | 0 | 7860 | 10:30 | 17:30 | 7:00
162 | BRC | HOSAKOTE | DH1 | Vijayapura-2 | 66/11KV VIJAYAPURA | F02BIJJAVARA,F11 MUDDAGURKI,F16 VENKATAGIRI KOTE,F03 NARAYANAPURA,F08 BEEDIGANAHALLI,F12 SAIBABA | 11 KV Feeder | LINE SHIFTING,TRANSFORMER, JUNGLE CUTTING , PROVIDING SPACERS,TC MAINTAINACE,STRAIGHTNING OF LOOSE SPAN, GOS WORK | Maintenance Work |  |  | 06-09-2021 | BIJJAVARA,MUDDAGURKI,VENKATAGIRIKOTE,NARAYANAPURA,BEEDIGANAHALLI |  |  | 10:30 | 12:30 | 2:00
163 | TUMKUR CIRCLE | MADHUGIRI DIVISION | KR1 | Theetha | Koratagere 66/11kV | F12- Doddasaggere | DTC 76 | For maintenance of GOS, replacement of 11 Kv line jumps & DTC's of F12 Doddasaggere NJY feeder | Maintenance Work |  |  | 06-09-2021 | Doddasaggere panchayat limit |  |  | 10:00 | 17:00 | 7:00 | LC given only in Load Shedding time of Agri feeders
164 | TUMKUR CIRCLE | MADHUGIRI DIVISION | KR1 | Theetha | Kolala 66/11kV | F17 Ekalavya | DTC 60 | For maintenance of GOS, replacement of 11 Kv line jumps & DTC's of F17-Ekalavya NJY feeder | Maintenance Work |  |  | 06-09-2021 | Theetha panchayat limit |  |  | 10:00 | 17:00 | 7:00 | LC given only in Load Shedding time of Agri feeders
165 | WEST | RAJAJINAGAR | N2 | MARENAHALLI | VIJAYNAGARA | F8 | 1)DTC164-N2 SUBDIVISION OFFICE 2)DTC51-GOVINDARAJ NAGAR 3)DTC522-GOVINDARAJ NAGAR GOVT SCHOOL 4)DTC184-BCES HBCS. | Estimate for conversion of LT Overhead line in to AB Cable pertaining to F8 Feeder , Vijaynagara MUSS in O&M-5,N2 Sub-division. | CAPEX | 2020/RN/14.1927/P-106373/17-03-2021 |  | 06-09-2021 | N2 SUBDIVISION OFFICE, GOVINDARAJ NAGAR,GOVINDARAJ NAGAR GOVT SCHOOL, ,BCES HBCS. | 0 | 4295 | 10:30 | 17:30 | 7:00
166 | WEST | RAJAJINAGAR | N2 | MARENAHALLI | Chandralayout | F1 | 1)DTC140-WIDIA LAYOUT,KOLIMANE ROAD 2)DTC14-ATTIGUPPE PETROL BUNK MAIN ROAD 3)DTC31-ATTIGUPPE INCOME TAX LAYOUT 4)DTC254-WIDIA LAYOUT 5)DTC117-WIDIA LAYOUT 6)DTC52-WIDIA LAYOUT 7)DTC336-BHEL GUEST HOUSE 8)DTC85- BASAVESHWARA LAYOUT 9)DTC243-NEAR BUNT SANGHA, SUBBANNA GARDEN 10)DTC13- BHEL TOWNSHIP, SUBBANNA GARDEN 11)DTC34-BHEL TOWNSHIP, SUBBANNA GARDEN 12)DTC317- BASAVESHWARA LAYOUT 13)DTC198- SUBBANNA GARDEN . | Estimate for conversion of LT Overhead line in to AB Cable pertaining to F1 Feeder , CHANDRALAYOUT MUSS in O&M-5,N2 Sub-division. | CAPEX | 2021/RN/14.1927/P-113459-15-04-2021 |  | 06-09-2021 | WIDIA LAYOUT,KOLIMANE ROAD,ATTIGUPPE PETROL BUNK MAIN ROAD,ATTIGUPPE INCOME TAX LAYOUT,WIDIA LAYOUT,BHEL GUEST HOUSE, BASAVESHWARA LAYOUT,NEAR BUNT SANGHA, SUBBANNA GARDEN,BHEL TOWNSHIP, SUBBANNA GARDEN, BASAVESHWARA LAYOUT,SUBBANNA GARDEN . | 9 | 5695 | 10:30 | 17:30 | 7:00
167 | WEST | RAJAJINAGAR | N2 | MARENAHALLI | Remco | F9 | 1)DTC76-GANGONDANA HALLY 2)DTC218-CHANDRALAYOUT 3DTC368-HBCS LAYOUT 2,BCC LAYOUT 4)DTC554-GANGONDANAHALLI MAIN ROAD PARK SERVICE ROAD 5)DTC118-BINNY LAYOUT 6)DTC126-GOODWILL APPT 7)DTC86-GOODWILL APPT 8)DTC38-BINNY LAYOUT 9)DTC120-BINNY LAYOUT 10)DTC206-ATTIGUPPE NEAR GOVT COLLAGE 11)DTC116-INDIRA COLONY 12)DTC160-MICO LAYOUT II 13)DTC66-MICO LAYOUT 14)DTC159-CHANDRA LAYOUT,NEAR 15)DTC37-BCC LAYOUT 16)DTC77-GANGONDANA HALLY17)DTC74-GANGONDANA HALLY 18)DTC75-GANGONDANA HALLY 19)DTC148-MICO LAYOUT 20)DTC82-BCC LAYOUT 21)DTC205-ATTIGUPPE NEAR GOVT COLLAGE 22)DTC275-BCC LAYOUT WATER TANK BACK SIDE23)DTC76-GANGONDANA HALLY. | Estimate for conversion of LT Overhead line in to AB Cable pertaining to F9 Feeder , Remco MUSS in O&M-5,N2 Sub-division. | CAPEX | 2020/RN/14.1927/N-19-11-2020 |  | 06-09-2021 | GANGONDANA HALLY -CHANDRALAYOUT HBCS LAYOUT 2,BCC LAYOUT GANGONDANAHALLI MAIN ROAD PARK SERVICE ROAD 5)DTC118-BINNY LAYOUT GOODWILL APPT ,-GOODWILL APPT BINNY LAYOUT ,BINNY LAYOUT ,ATTIGUPPE NEAR GOVT COLLAGE ,INDIRA COLONY, MICO LAYOUT II ,MICO LAYOUT CHANDRA LAYOUT,NEAR,BCC LAYOUT GANGONDANA HALLY ,GANGONDANA HALLY -GANGONDANA HALLY ,MICO LAYOUT -BCC LAYOUT ,ATTIGUPPE NEAR GOVT COLLAGE -BCC LAYOUT WATER TANK BACK SIDE,GANGONDANA HALLY. | 10 | 5511 | 10:30 | 17:30 | 7:00
168 | WEST | RAJAJINAGAR | N2 | MARENAHALLI | NRS | F18 | 1)DTC67-SARASWATHI IRON 2)DTC308-CENTRAL EXCISE LAYOUT 3)DTC307-HARIRAM ALIAS LAYOUT 4)DTC309-HARIRAM ALIAS LAYOUT 5)DTC127-11TH MAIN , M C LAYOUT 6)DTC60-C.E.S LAYOUT 7)DTC16- BAPUJI LAYOUT 8)DTC70- SARASWATHI NAGAR 9)DTC124- BINNY LAYOUT 10)DTC310- 4TH CRS,CENTRAL EXCISE 11)DTC305-MC LAYOUT INDUSTRIAL AREA 12)DTC122-BINNY LAYOUT 13)DTC23-LIBRARY 2 14)DTC154-M.C. LAYOUT 15)DTC17-VINAYAKA LAYOUT 16)DTC27-BAPUJI LAYOUT 17)DTC559-NEAR SARASWATHINAGARA APPARTMENT 18)DTC01-VEERESH THEATER 19)DTC209-HARIRAM ALIDAS LAYOUT 20)DTC150-3RD CROSS, CENTRAL EXISE LAYOUT 21)DTC09- CENTRAL EXCISE LAYOUT 22)DTC47-C.S.LAYOUT 23)DTC02-8TH CROSS , M C LAYOUT 24)DTC42- M C LAYOUT 25)DTC22-LIBRARY 1, M C LAYOUT 26)DTC144- BAYANNA INDL ESTATE AD HALLY , MC LAYOUT 27)DTC151-SHANIMAHATHMA TEMPLE, MC LAYOUT 28)DTC55-13TH CROSS M.C.LAYOUT 29)DTC225-MC LAYOUT 2ND CROSS 30)DTC188-MC LAY OUT NEAR CUTEES HOSPITAL 31)DTC270-BAPUJI LAYOUT 32)DTC366-GKW LAYOUT 33)DTC36-SECRETARIATE LAYOUT 34)DTC112-MARENA HALLI | Estimate for conversion of LT Overhead line in to AB Cable pertaining to F18 Feeder , NRS MUSS in O&M-5,N2 Sub-division. | CAPEX | 2021/RN/14.1927/P-113460/15-04-2021 |  | 06-09-2021 | SARASWATHI IRON CENTRAL EXCISE LAYOUT ,HARIRAM ALIAS LAYOUT ,HARIRAM ALIAS LAYOUT ,11TH MAIN , M C LAYOUT ,C.E.S LAYOUT BAPUJI LAYOUT SARASWATHI NAGAR BINNY LAYOUT,4TH CRS,CENTRAL EXCISEMC LAYOUT INDUSTRIAL AREA BINNY LAYOUT LIBRARY 2 ,M.C. LAYOUT VINAYAKA LAYOUTBAPUJI LAYOUT NEAR SARASWATHINAGARA APPARTMENT VEERESH THEATER 19)DTC209-HARIRAM ALIDAS LAYOUT 3RD CROSS, CENTRAL EXISE LAYOUT,CENTRAL EXCISE LAYOUT,C.S.LAYOUT,8TH CROSS , M C LAYOUT M C LAYOUT LIBRARY 1, M C LAYOUT BAYANNA INDL ESTATE AD HALLY , MC LAYOUT,SHANIMAHATHMA TEMPLE, MC LAYOUT 13TH CROSS M.C.LAYOUTMC LAYOUT 2ND CROSS MC LAY OUT NEAR CUTEES HOSPITAL BAPUJI LAYOUT -GKW LAYOUT -SECRETARIATE LAYOUT,MARENA HALLI . | 17 | 7069 | 11:30 | 17:30 | 6:00 | Work will be taken up as schelduled from 3rd SEP 2021
169 | WEST | RAJAJINAGAR | N2 | MARENAHALLI | Chandralayout | F2 | 1)DTC265-VYALIKAVAL HBCS LAYOUT 2)DTC268- VYALIKAVAL HBCS LAYOUT 3)DTC267- VYALIKAVAL HBCS LAYOUT 4)DTC40-GKW LAYOUT 5)DTC197-GKW LAYOUT 6TH MAIN 6)DTC468-PRIYADARSHINI LAYOUT 7)DTC54-PRIYADARSHINI LAYOUT 8)DTC437-PRIYADARSHINI LAYOUT 9)DTC192- SUBBANA GARDEN 10)DTC266- VYALIKAVAL HBCS, NEAR 11)DTC62-VINAYAKA LAYOUT 12)DTC84-ADJASCENT TO WIIDIA LAYOUT 13)DTC155- NEAR VINAYAKA LAYOUT 14)DTC190-VINAYAKA LAYOUT 15)DTC316-VINAYAKA LAYOUT 1ST MAIN 16)DTC83- SUBBANNA GARDEN17)DTC328- SUBBANNA GARDEN 18)DTC147-SHIVANANDNAGARA 19)DTC156- VINAYAKA LAYOUT 3RD MAIN 20)DTC315-VINAYAKA LAYOUT 1ST MAIN 21)DTC59-MOODALAPALYA 22)DTC46- CHANDRA LAYOUT 23)DTC90- CHANDRA LAYOUT 24)DTC18-GKW LAYOUT 25)DTC115-GKW LAYOUT 26)DTC87-PF LAYOUT 27)DTC88-PF LAYOUT 28)DTC49-VINAYAKA LAYOUT 29)DTC314-VINAYAKA LAYOUT 3RD MAIN 30)DTC245-VYALIKAVAL LAYOUT 31)DTC265-VYALIKAVAL HBCS 32)DTC89-KPA BLOCK CHANDRALAYOUT. | Estimate for conversion of LT Overhead line in to AB Cable pertaining to F2 Feeder , Chandralayout MUSS in O&M-5,N2 Sub-division. | CAPEX | 2021/RN/14.1927/P-113457/15-04-2021 |  | 06-09-2021 | VYALIKAVAL HBCS LAYOUT,GKW LAYOUT,GKW LAYOUT 6TH MAIN, PRIYADARSHINI LAYOUT,SUBBANA GARDEN, VYALIKAVAL HBCS, NEARVINAYAKA LAYOUT, ADJASCENT TO WIIDIA LAYOUT,NEAR VINAYAKA LAYOUT, 1ST MAIN SUBBANNA GARDEN, SHIVANANDNAGARA, ,VINAYAKA LAYOUT 3RD MAIN,VINAYAKA LAYOUT 1ST MAIN,MOODALAPALYA, CHANDRA LAYOUT,GKW LAYOUT,PF LAYOUT,VINAYAKA LAYOUT,VINAYAKA LAYOUT 3RD MAIN,VYALIKAVAL LAYOUT VYALIKAVAL HBCS KPA BLOCK, CHANDRALAYOUT. | 6 | 10122 | 10:30 | 17:30 | 7:00
170 | WEST | RAJAJINAGAR | N2 | MARENAHALLI | Chandralayout | F6 | 1)DTC269-NANJARASAPPA LAYOUT 2)DTC327- NEAR SKYLINE BBMP PARK 3)DTC222- BAPUJI HBCS LAYOUT 4)DTC200-CANARA BANK COLONY 5)DTC330 MARUTHINAGARA 6)DTC320-CHANDRA LAYOUT 7)DTC250- BAPUJI LAYOUT 8)DTC71-CHICKPETE LAYOUT 9)DTC221-BAPUJI LAYOUT10)DTC19-CANARA BANK COLONY 11)DTC162-SKYLINE APARTMENT MAIN ROAD12)DTC111-CANARA BANK COLONY13)DTC503-ANUBHAVA NAGARA 14)DTC137-MARUTHI NAGARA15_DTC332-NAGARABHAVI MAIN ROAD 16)DTC43-MARUTHINAGARA17)DTC323- MARUTHINAGARA 3RD MAIN 18)DTC64-CANARA BANK COLONY 19)DTC269-MC LAYOUT JAYALAKSHMI INDUSTRIAL. | Estimate for conversion of LT Overhead line in to AB Cable pertaining to F6 Feeder , Chandralayout MUSS in O&M-5,N2 Sub-division. | CAPEX | 2021/RN/14.1927/P-113458/15-04-2022 |  | 06-09-2021 | NANJARASAPPA LAYOUT NEAR SKYLINE BBMP PARK BAPUJI HBCS LAYOUT CANARA BANK COLONY,MARUTHINAGARA CHANDRA LAYOUT BAPUJI LAYOUT CHICKPETE LAYOUT BAPUJI LAYOUT CANARA BANK COLONY SKYLINE APARTMENT MAIN ROAD ,CANARA BANK COLONY ,ANUBHAVA NAGARA,MARUTHI NAGARA15,NAGARABHAVI MAIN ROAD,MARUTHINAGARA,MARUTHINAGARA 3RD MAIN,CANARA BANK COLONY MC LAYOUT JAYALAKSHMI INDUSTRIAL. | 2 | 5840 | 10:30 | 17:30 | 7:00
171 | WEST | RAJAJINAGAR | N2 | MARENAHALLI | Chandralayout | F8 | 1)DTC213-CHANDRALAYOUT NEAR SIDDAGANGA SCHOOL BACK SIDE 2)DTC460-Siddaganga School Back side 3)DTC226- INCOME TAX LAYOUT 4)DTC227-INCOME TAX LAYOUT 5)DTC228-INCOME TAX LAYOUT 6)DTC229-INCOME TAX LAYOUT 7)DTC233- VIDYAGIRI LAYOUT 8)DTC157- CHANDRA LAYOUT, BUS 9)DTC119-MARUTHI NAGARA 10)DTC260-CHANDRA LAYOUT 80FEET ROAD 11)DTC458-CHANDRA LAYOUT SIDDAGANGA SCHOOL BACKSIDE 12)DTC450- CHANDRA LAYOUT 80FEET ROAD MARUTHINAGARA 13)DTC438-CHANDRA LAYOUT BMTC DEPOT 14)DTC93- CHANDRA LAYOUT 15)DTC94-CHANDRA LAYOUT MILK BOOTH 16)DTC20-CHANDRA LAYOUT 17)DTC73-CHANDRA LAYOUT 18)DTC72- BASAVESHWARA LAYOUT 19)DTC321- KPA CHANDRA LAYOUT 20)DTC215- MARUTHI NAGARA 80 FEET ROAD 21)DTC263-MARUTHI NAGARA 80 FEET ROAD 22)DTC203- CHANDRALAYOUT 23)DTC244-JYOTHINAGARA 24)DTC168-BCES HBCS 25)DTC169- BCES HBCS 26)DTC232- INCOME TAX LAYOUT 27)DTC233- INCOME TAX LAYOUT 28)DTC261-CHANDRALAYOUT 29)DTC179-BCES HBCS 30)DTC178-BCES HBCS 31)DTC92-N-BHAVI,1 STG,BHND 32)DTC149-SBI, CHANDRALAYOUT 33)DTC240-8TH CROSS, M C LAYOUT 34)DTC50-CHANDRA LAYOUT 35)DTC45- NAGARABHAVI 36)DTC252- CHANDRALAYOUT 12TH CROSS 37)DTC253-CHANDRALAYOUT 11TH CROSS 38)DTC166-BCES HBCS 39)DTC262-CHANDRALAYOUT 12TH CROSS 40)DTC167-BCES HBCS 41)DTC61-CHANDRA LAYOUT SLUM 42)DTC132-CHANDRALAYOUT 43)DTC177- BCES HBCS 44)DTC173- BCES HBCS 45)DTC171- BCES HBCS 46)DTC170- BCES HBCS 47)DTC230-INCOME TAX LAYOUT 48)DTC219-CHANDRALAYOUT 49)DTC181-BCES HBCS 50)DTC182-BCES HBCS 51)DTC459-Siddaganga School Back side. | Estimate for conversion of LT Overhead line in to AB Cable pertaining to F8 Feeder , CHANDRALAYOUT MUSS in O&M-5,N2 Sub-division. | CAPEX | 2021/RN/14.1927/ |  | 06-09-2021 | CHANDRALAYOUT NEAR SIDDAGANGA SCHOOL BACK SIDE ,Siddaganga School Back side , INCOME TAX LAYOUT ,VIDYAGIRI LAYOUT , CHANDRA LAYOUT, BUS ,MARUTHI NAGARA ,CHANDRA LAYOUT 80FEET ROAD ,CHANDRA LAYOUT BMTC DEPOT ,CHANDRA LAYOUT MILK BOOTH , BASAVESHWARA LAYOUT , KPA CHANDRA LAYOUT , MARUTHI NAGARA 80 FEET ROAD ,JYOTHINAGARA ,N-BHAVI,1 STG,BHND ,SBI, CHANDRALAYOUT,8TH CROSS, M C LAYOUT ,NAGARABHAVI ,CHANDRALAYOUT 12TH CROSS ,CHANDRALAYOUT 11TH CROSS ,BCES HBCS ,CHANDRALAYOUT 12TH CROSS ,CHANDRA LAYOUT SLUM. | 0 | 10542 | 10:30 | 17:30 | 7:00
172 | TUMKUR CIRCLE | MADHUGIRI DIVISION | KR1 | Thovinakere | Thovinakere 66/11kV | F06 Thovinakere town | DTC 27 | for Jungle cutting GOS & DTC maintenace | Maintenance Work |  |  | 06-09-2021 | Thovinakere Town |  |  | 11:00 | 15:00 | 4:00 | LC given only in Load Shedding time of Agri feeders
173 | TUMKUR CIRCLE | TUMKUR DIVISION | KU1 | O&M-1 | Anchepalya 66/11 | F13 NJY Hosahally | F13 NJY Hosahally DTC 1 | Est for reconductoring 4 ACSR wire by rabbit conductor with providing intermediate poles of existing 25 KVA DTC at Hosahally Colony in O&M-1 Sec, Kunigal S/D | CAPEX | C-11795 /30.03.2021 |  | 06-09-2021 | Hosahally village limits |  |  | 10:00 | 13:00 | 3:00
174 | TUMKUR CIRCLE | TUMKUR DIVISION | KU1 | O&M-1 | Kunigal 66/11 | F4 Rayappamarga | F4 Rayappamarga DTC 1 | Est for reconductoring 4 ACSR wire by rabbit conductor with providing intermediate poles of existing 100 KVA DTC at Mahaveeranagara village in O&M-1 Sec, Kunigal S/D | CAPEX | C-551 / 20.03.2021 |  | 06-09-2021 | Mahaveeranagara village limits |  |  | 10:00 | 13:00 | 3:00
175 | TUMKUR CIRCLE | TUMKUR DIVISION | YD1 | Yediyur | Jiddigere | F4 Jiddigere | F4 Jiddigere DTC 90 | Estimate for providing 11KV Link line for reduce the over load of F-4 Jiddigere Feeder ( Jiddigere 66/11KV MUSS) , Jiddiger 66/11 KV MUSS to Yallapura village in Yediyur section, Yediyur Subdivision. | CAPEX | C-201 / 29.08.2020 |  | 06-09-2021 | Chottanahallygate,Yallapura gate devara kannasandra,Channthimmanapalya |  |  | 10:00 | 17:00 | 7:00
176 | TUMKUR CIRCLE | TIPTUR DIVISION | CN1 | O&M-1 | CN HALLI_110/11 KV | F2 CN HALLI, F11 MUDDENAHALLI | 11 kv Branch line DTC 85 | Replacement of existing 11 Kv Over Head Line by 11 Kv Cover conductor at Varios Location on F2 C N Halli Feeder | Capex | C-57301/08.06.2021 |  | 06-09-2021 | CN HALLI TOWN, MUDDENAHALLI |  |  | 10:00 | 17:00 | 7:00
177 | DAVANAGERE CIRCLE | CHITRADURGA DIVISION | HD1 | O&M-1 | Hosadurga 66/11KV | F-8 Siddaramanagara,F-14 Devigere(Hosadurga MUSS),F-16 B.V.Nagar(Hosadurga muss),F-17 Mavinakatte(Hosadurga MUSS),F-7 Madure(Hosadurga MUSS) | 11 KV Feeder | pole shifting in Holalkere road to bypass cinnecting link road | Maintenance Work |  |  | 06-09-2021 | hosadurga town and devigere panchayath villages,madurepanchayath village and Hebballi gramapanchayath villages |  |  | 10:00 | 18:00 | 8:00
178 | DAVANAGERE CIRCLE | HIRIYUR DIVISION | TLK | Talak | 66/11KV Mylenahalli MUSS | F05 Mylenahalli, F09 Ghatparthi NJY | 11 KV Feeder | Running New 11KV Link Line from Mylenahalli MUSS to Boodihalli village limits for reducing load of existing 11KV Feeder F09 Ghatparthi Feeder og 66/11KV MUSS Mylenahalli | Maintenance Work |  |  | 06-09-2021 | Mylenahlli, Boodihalli, Bhoganahalli. Ghatparthi, Chanaganahalli, Chitranaykanahlli,Renukapura, Basapura |  |  | 10:00 | 18:00 | 8:00
179 | TUMKUR CIRCLE | TUMKUR DIVISION | KU1 | KEMPANAHALLI | Kempanahally 66/11 | F6 YADEHALLY | F6 YADEHALLY DTC 1 | Est for reconductoring 4 ACSR wire by rabbit conductor with providing intermediate poles of existing 25 KVA DTC at Haluvagilu Colony in Kempanahally Sec, Kunigal S/D | CAPEX | C-11794 /30.03.2021 |  | 06-09-2021 | Haluvagilu village limits |  |  | 10:00 | 13:00 | 3:00
180 | WEST | RAJAJINAGAR | N1 | 2nd BLOCK RAJAJI NAGAR | NANDINI | F4 | 1, | Estimate for conversion of LT Overhead line to LT AB Cable in F1 Feeder of NANDINI MUSS in O&M-2, N1 Sub-division | CAPEX | 2020/RN/14-1927/N-106241/24.09.2020 |  | 06-09-2021 | 2ND BLK | 9 | 191 | 10:30 | 17:30 | 7:00
181 | TUMKUR CIRCLE | MADHUGIRI DIVISION | PG1 | Nagalamadike | Nagalamadike 66/11KV | F11 Ryapte NJY | DTC 11 | For LT reconductoring of 2/4 ACSR by Rabbit Conductor at Vallur Village limits 2 x 63 KVA DTC in Nagalamadike Section | CAPEX | R-33857/18.02.2021 |  | 06-09-2021 | Vallur |  |  | 10:00 | 17:00 | 7:00
182 | DAVANAGERE CIRCLE | CHITRADURGA DIVISION | SRP | belagur | 66/11kv garaga muss | F9 Kalkere feeder from Garga MUSS to Kabbala dibba -12kms | 11 KV Feeder | 11KV Link line to Bifurcate the load on F9 Kalkere feeder from Garga MUSS to Kabbala dibba -12kms | Maintenance Work |  |  | 06-09-2021 | Hosadurga town and devigere panchayath limit villages,madure panchayath limit villages and Hebballi gramapanchayath limit villages |  |  | 10:00 | 18:00 | 8:00
183 | DAVANAGERE CIRCLE | HIRIYUR DIVISION | TLK | Talak | 66/11KV Talak MUSS | F01 Devarahalli, F11 Rudrammanahalli | 11 KV Feeder | Estimate for Reconductoring of 2/4ACSR Conductor by Rabbit ACSR Conductor of F01 Devarahalli Feeder from 66/11KV Talak MUSS to N Devarahalli village Limits in O&M Section Talak of Talak Sub Division. | Capex |  |  | 06-09-2021 | Hosahalli, Marenahatti. N Devrahalli ,Bhiminakere, Kalderahatti |  |  | 10:00 | 18:00 | 8:00
184 | TUMKUR CIRCLE | TUMKUR DIVISION | YD1 | Amruthur | Amruthur 66/121 KV | F 6 Snanba | F 6 Snanba DTC 80 | Estimate for providing 11KV Link line for reduce the over load of F-6 Sanaba Feeder Amruthur 66/11KV MUSS) Link line ,from Amruthur MUSS to Chikkakere in Amruthur section, Yediyur Subdivision. | Maintenance Work | C-11713 / 23.03.2021 |  | 06-09-2021 | Amruthur village limits sondekoppa Indiranagara,Hosakere gate |  |  | 10:00 | 17:00 | 7:00
185 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | KADABA | KADABA-110/11KV | F10-DASARAKALLAHALLI NJY ,F04 Honnashettyhally, F05 Bmallenahally, F7 Kadaba, F08 Byalahally | 11 KV Feeder DTC 74 | Bifercater load of F-10 Dasarakallahalli NJY Feeder to Reduce intereption to kadaba twonlimits in kadaba section nittur | Capex | Y-401 30.03.21 |  | 06-09-2021 | KADABA,K,RAMPURA,KOMMANAHALLI,BYADAGERE |  |  | 10:00 | 18:00 | 8:00 | DUE TO RAIN LC NOT AVAILED
186 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | KADABA | KGTEMPLE -110/11KV | F-12 Konnakere njy, F-2 suragenahally, f-5koppa, F-4 kunnala | 11 KV Feeder DTC 132 | For Replacing of Existing Detoriated 4 ACSR Conductor by Good Rabbit ACSR Conductor 11 KV HT Line From D Kunnala to Jeeganahalli Gollarahatti Village Limits of F4 Kunnala Feeder in Kadaba Section (DP- 06 No, 9 Mtr PSCC Pole 95 Nos Rabbit Wire-19.525 KM) | CAPEX | Y-24412/26.03.21 |  | 06-09-2021 | Koppa,kunnala,lingammanahally,konnemadanahally,konnakere,jeeganahally |  |  | 10:00 | 18:00 | 8:00 | DUE TO RAIN LC NOT AVAILED
187 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | KADABA | KGTEMPLE -110/11KV | F-12 Konnakere njy, F-2 suragenahally, f-5koppa, F-4 kunnala | 11 KV Feeder DTC 75 | For Providing Evacation of New 11 KV Link Line Konnakere to Konnanakere Village Limits to Biforcate Load From F5 B Mallenahalli Feeder From Kadaba Muss in Kadaba Section Nittur Sub Division (DP Set-10, 9Mt Pole-58 No, Rabbit Wire-7.605 KM) | Maintenance Work | Y-24371/26.03.21 |  | 06-09-2021 | Koppa,kunnala,lingammanahally,konnemadanahally,konnakere,jeeganahally |  |  | 10:00 | 18:00 | 8:00 | DUE TO RAIN LC NOT AVAILED
188 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | NITTUR | NITTUR220/110/11 KV | F16-SOPANAHALLI.F19-BOMMENAHALLI,F3-SAGAGARANAHALLI,F4-M.S.HALLI,F2-YALLAPURA,F5-HEMAVATHI,F6-THYAGATUR | 11 KV Feeder DTC 215 | For Providing Evacation of New 11 KV Link Line NITTUR MUSS to ADALAGERE PUMP HOUSE Village Limits to Biforcate Load From F3-SAGARANAHALLI FeederIN NITTUR Muss in NITTUR Section Nittur Sub Division (DP Set-10, 9Mt Pole-58 No, Rabbit Wire-7.605 KM) | Maintenance Work | Y-24373/26.3.21 |  | 06-09-2021 | SAGARANAHALLI,THYAGATUR,M.S.HALLI,YALLAPURA,BOMMENAHALLI,KUNDURANAHALLI. |  |  | 10:00 | 18:00 | 8:00
189 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | NITTUR | NITTUR220/110/11 KV | F15-NITTUR,F8-HESARAHALLI,F7-BENACHIGERE,F9-BELAVATHA | 11 KV Feeder DTC 183 | For replacement of existing 11 KV over head lines by 11 KV covered conductor from various locations in Nittur Section. | CAPEX | W-1243/18.3.2020 |  | 06-09-2021 | NITTUR,Mathighatta.HESARAHALLI |  |  | 10:00 | 18:00 | 8:00
190 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | KADABA | KADABA-110/11KV | F03-BELAVATHA, F013 thogarighatta, F11 Belavatha NJY | 11 KV Feeder DTC 84 | Kadaba Muss To Belavatha Village limits Biforcate Over loaded F-9 Belavatha Feeder | Capex | Y-402 31.03.21 |  | 06-09-2021 | ADAGONDANAHALLI , BELAVATHA,LAKSHMIPURA |  |  | 10:00 | 18:00 | 8:00 | DUE TO RAIN LC NOT AVAILED
191 | TUMKUR CIRCLE | TUMKUR DIVISION | YD1 | Yediyur | Yadiyur 66/11 | F-1 Siddalingeshwara Feeder | F-1 Siddalingeshwara Feeder DTC 10 | Estimate for Providing Continous power Supply 2KM Surrounding Yadiyuru Town Limits From F-1 Siddalingeshwara Feeder Feeding From Yadiyuru MUSS Pertaining to Yadiyuru Section Yadiyuru S/D. | CAPEX & Other Works | D-451/08.07.2021 |  | 06-09-2021 | Yadiyuru,Chakenahalli,Doddamadhure,Jaladhigere,Hemavathi,Beerganahalli |  |  | 10:00 | 17:00 | 7:00
192 | TUMKUR CIRCLE | TUMKUR DIVISION | YD1 | Yediyur | Yadiyur 66/11 | F-1 Siddalingeshwara Feeder | F-1 Siddalingeshwara Feeder DTC 12 | Estimate for Providing Continous power Supply 2KM Surrounding Yadiyuru Town Limits From F-1 Siddalingeshwara Feeder and Bifurcation of IP Sets Pertaining to Yadiyuru Section Yadiyuru S/D. | CAPEX & Other Works | D-452/08.07.2021 |  | 06-09-2021 | Yadiyuru,Chakenahalli,Doddamadhure,Jaladhigere,Hemavathi,Beerganahalli |  |  | 10:00 | 17:00 | 7:00
193 | DAVANAGERE CIRCLE | CHITRADURGA DIVISION | HL1 | O&M - 1 | Holalkere66/11KV | F15-Punajuru, F14-malenahalli NJY, f10-Malladihalli,F11-Gundimadu | 11 KV Feeder | 11 KV Link line from Holalkere Railway station to Malenahalli limits | Maintenance Work |  |  | 06-09-2021 | Arehalli,punajur,Malenahalli, avalihatti,gundimadu,kunagali,Shivapura,Agrahara,Hulemalali,Jaipura |  |  | 10:00 | 18:00 | 8:00
194 | WEST | RAJAJINAGAR | N8 | Mallathahalli | Sir MV | F-01 | 342, 339, 205 | Conversion of 11KV Overhead line into HT Ug Cable inFeeder F-01 (O&M Mallathahalli) N8 Sub Division,Rajaji nagar Division Bangalore West Circle, BMAZ (South), BESCOM under PHASE-I on Total turnkey under Rate Contract (RC.05) on Percentage basis quoting. | CAPEX | 2020/RN/14-1927/N-106255/02.11.2020 |  | 06-09-2021 | Railway Layout and surrounding areas | 2 | 500 | 10:30 | 17:30 | 7:00 | Works includes Srtinging of LT ab Cable one day and connecting servicing connections and load balancing one day
195 | BRC | HOSAKOTE | DH1 | O&M 1 | 66/11KV DEVANAHALLI | F02 BEERSANDRA ,F19 KUNDANA | 11 KV Feeder | EXECUTING THE GANGA KALYANA WORKS | Maintenance Work |  |  | 06-09-2021 | BEERSANDRA,VISHWANATHAPURA,DINNE SOLURU |  |  | 10:00 | 12:00 | 2:00
196 | WEST | RAJAJINAGAR | N8 | Mallathahalli | Sir MV | F-09 | 332, 333, 334 | Conversion of 11KV Overhead line into HT Ug Cable inFeeder F-09 (O&M Mallathahalli) N8 Sub Division,Rajaji nagar Division Bangalore West Circle, BMAZ (South), BESCOM under PHASE-I on Total turnkey under Rate Contract (RC.05) on Percentage basis quoting. | CAPEX | 2020/RN/14-1927/N-106363/12.01.2021 |  | 06-09-2021 | MPM Layout and surrounding areas | 0 | 750 | 10:30 | 17:30 | 7:00 | Works includes Srtinging of LT ab Cable one day and connecting servicing connections and load balancing one day
197 | WEST | RAJAJINAGAR | N8 | S G Kaval | Byadarahalli | F-01 | 253, 271 | Conversion from HT OH to HTUG Work | CAPEX | 2020/RN/14-1927/N-106369/10.03.2021 |  | 06-09-2021 | Rajivgandi Nagar, Byraveshwara Nagara, Near wild kraft, Kebbehalli, Hanumantharayana Palya, | 0 | 5927 | 10:30 | 17:30 | 7:00
198 | DAVANAGERE CIRCLE | CHITRADURGA DIVISION | HD1 | O&M-2 | Hosadurga MUSS | F4 Kondapura, F16-Kondapura NJY, F4-Hebbali, F17-B V Nagara | 11 KV Feeder | GK Works | Maintenance Work |  |  | 06-09-2021 | Kondapura Hebbali, B V Nagara Areas |  |  | 11:00 | 15:00 | 4:00
199 | TUMKUR CIRCLE | MADHUGIRI DIVISION | PG1 | Mangalawada | Mangalawada 66/11KV | F08 Hanumasagara | DTC 11 | For HT reconductoring of 4 ACSR by Rabbit Conductor of F-08 Hanumasagara feeder from rangswamy Land to Gopalreddy and in in Mangalawada Section | CAPEX | R-33315/18.02.2021 |  | 06-09-2021 | Kannamedi, Honnamedi, Kotthuru, Hariharapura |  |  | 10:00 | 17:00 | 7:00
200 | TUMKUR CIRCLE | MADHUGIRI DIVISION | PG1 | Mangalawada | Shylapura 66/11KV | F12 Gujjanadu NJY | DTC 8 | For LT reconductoring of 2/4 ACSR by Rabbit Conductor at Gujjaralahalli Village limits 63 KVA DTC opposite school Limits in Mangalawada Section | CAPEX | R-33855/18.02.2021 |  | 06-09-2021 | Gujjarahalli |  |  | 10:00 | 17:00 | 7:00
201 | WEST | RAJAJINAGAR | N8 | Mallathahalli | Srigandakaval | F-04 | 421422 | Conversion of 11KV Overhead line into HT Ug Cable inFeeder SGK F-04 (O&M Mallathahalli) N8 Sub Division,Rajaji nagar Division Bangalore West Circle, BMAZ (South), BESCOM under PHASE-I on Total turnkey under Rate Contract (RC.05) on Percentage basis quoting. | CAPEX | 2020/RN/14-1927/N-106365/12.01.2021 |  | 06-09-2021 | NGEF Layout and surrounding areas | 2 | 3500 | 10:30 | 17:30 | 7:00 | Works includes Srtinging of LT ab Cable one day and connecting servicing connections and load balancing one day
202 | WEST | RAJAJINAGAR | N8 | S G Kaval | Byadarahalli | F-01 | 162, 84 | Conversion from HT OH to HTUG Work | CAPEX | 2020/RN/14-1927/N-106369/10.03.2021 |  | 06-09-2021 | Rajivgandi Nagar, Byraveshwara Nagara, Near wild kraft, Kebbehalli, Hanumantharayana Palya, | 0 | 5927 | 10:30 | 17:30 | 7:00
203 | KOLAR CIRCLE | CHINTAMANI DIVISION | CM2 | IRAGAMPALLI | iragampalli | F12 K Raguttahalli | 11 KV Feeder | New Service connection line Work | Capex | U 24 28.07.2021 |  | 06-09-2021 | Nernahalli,Nallarallahalli,Kuramaralahalli,Mindigal,Bodanamari,Sujjanahalli, |  |  | 11:00 | 12:30 | 1:30
204 | KOLAR CIRCLE | CHINTAMANI DIVISION | CM2 | IRAGAMPALLI | iragampalli | F12 K Raguttahalli | 11 KV Feeder | Cover conductor replacement works | Capex | U-4922/10.08.2021 |  | 06-09-2021 | Anakalu,Jagathanahalli,Gudisalahalli,B. Bathalahalli,Kotagal,Byrasandra,Moogalamari,Upparahalli,Bandakota,Thippenahalli,Shettihalli,Chowdanahalli |  |  | 10:00 | 17:00 | 7:00
205 | KOLAR CIRCLE | CHINTAMANI DIVISION | SG1 | O&M-1 | Sidlaghatta | F14 Thummanahalli | 11 kv Branch line DTC 55 | For Maintanace work | Maintenance Work |  |  | 06-09-2021 | Thippenahalli,hujagur,doddadasarahalli,gudlanarshimhanahalli, |  |  | 11:00 | 13:00 | 2:00
206 | KOLAR CIRCLE | CHINTAMANI DIVISION | SG2 | MELUR | melur | F3- Kamadahalli | 11 KV Feeder | Jungle Cutting, GOS Manitance, TC Maintance, Jumps Replacing | Maintenance Work |  |  | 06-09-2021 | Kamadahalli, Appegowdanahalli. |  |  | 10:00 | 13:00 | 3:00 | Line clear to be arranged during Load Shedding period & one NJY Feeder is interruption of2:30Hours