## 11-09-2021
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Schedule Interruptions for the month of September 2021
Details of works to avail Line Clear for CAPEX, RC, Service connection, OH to UG conversion, Self execution maintenance works
Sl No | Circle | Division | Sub Dvn | OM Unit | Station Name | Feeder No /Name | IF LT Work DTC code capacity | Nomenclature of Works | CAPEX/ Maintenance | Work order No and Date | Sanctioned Date | Date of LC planned | Areas affected | No: of consumers affected |  | Duration of LC required |  |  | Remarks (changeover arranged details) | Work Belongs to Station / BESCOM | LC Taken or Not (Yes / No) | Issue | Remarks | Station/Feeder charged time |  |  | Confirmed by BESCOM / KPTCL | Remarks (If time extended)
[14 empty] | HT consumers | LT consumers | from | To | Total interruption period in | [5 empty] | From | To | Total interruption period in
1 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | BP1 | O&M-1 | 220/66/11 KV Mittemari MUSS | F4- Garudadhri | 11 kv Branch line DTC 36 |  | Maintenance Work |  |  | 11-09-2021 | Mervapalli,Papinayakanapalli,Kothakote,Kodipalli,Pillagutta,Kanagamakalapalli,Dommharahatti,Giriyapalli,Malligurki,Appaswamythanda,Kempaihathnada,Mervapalli,Muthinapalli,Reddyvaripalli. |  |  | 11:00 | 13:00 | 2:00
2 | NORTH | HEBBAL | C7 | Yelahanka old town | PUTTENAHALLI | F12 | 11 KV Feeder DTC TC 649,TC 213,Ragavendra TC, TC 511, TC 547, TC 577, TC 659 | Conversion of 11KV OH to UG Line for F12 ( Puttenahalli Muss) MARUTHI NAGAR BLR Feeder in Yelahanka Old Town O&M 19A of C7 Sub Division, Hebbal Division | CAPEX |  |  | 11-09-2021 | maruthi Nagar, 8th cross road |  |  | 10:00 | 17:00 | 7:00
3 | NORTH | HEBBAL | C7 | Yelahanka old town | PUTTENAHALLI | F13 | 11 kv Branch line DTC HT 677, HT 266, HT 32, HT 191, TC 145 | Conversion of 11KV OH to UG Line for F13 ( Puttenahalli Muss) Venkatala BLR Feeder in Yelahanka Old Town O&M 19A of C7 Sub Division, Hebbal Division | CAPEX |  |  | 11-09-2021 | Bagalur Main Road, Big Mart area |  |  | 10:00 | 17:00 | 7:00
4 | NORTH | HEBBAL | C8 | Sahakar nagar | SKN | F8 | 11 kv Branch lineAll Dtcs | OH to UG | CAPEX |  |  | 11-09-2021 | G K V K |  |  | 9:00 | 17:00 | 8:00
5 | NORTH | HEBBAL | C8 | Sahakar nagar | SKN | F14 | 11 kv Branch lineAll Dtcs | OH to UG | CAPEX |  |  | 11-09-2021 | AGRAHARA, KOGILU, HEGDENAGARA |  |  | 9:00 | 17:00 | 8:00
6 | NORTH | HEBBAL | C8 | Sahakar nagar | SKN | F20 | 11 kv Branch lineAll Dtcs | OH to UG | CAPEX |  |  | 11-09-2021 | THIRUMENAHALLI VILLAGE, KOGILU |  |  | 9:00 | 17:00 | 8:00
7 | DAVANAGERE CIRCLE | CHITRADURGA DIVISION | CD2 | Sirigere | BHARAMASAGARA_66 | F10-ADAVIGOLLARAHALLI NJY | 11 KV Feeder | Maintenance work | Maintenance Work |  |  | 11-09-2021 | Heggadehalu,Heggadehalu Vadarahatti,Kasavanahalli, |  |  | 13:00 | 15:00 | 2:00
8 | RAMANAGARA | CHANDAPURA DIVISION | CH1 | Hebbagodi | Electronic City | F13 Sparsh Hospital |  | Tree trimming, Maintenance of GOS, loose span restrining, Bent pole straightening | Maintenance Work |  |  | 11-09-2021 | Sansera Bommasandra Indl area , Sparsh Hospital Road Kithaganahalli |  |  | 10:00 | 12:00 | 2:00
9 | RAMANAGARA | CHANDAPURA DIVISION | CH1 | Bommasandra | Bommasandra | F4 KSSIDC 2nd Stage |  | Tree trimming, Maintenance of GOS, loose span restrining, Bent pole straightening | Maintenance Work |  |  | 11-09-2021 | KSSIDC Sheds Bommasandra Indl area 4th Phase, Maini Road , MTR Road , RNS Motors road |  |  | 10:00 | 12:00 | 2:00
10 | RAMANAGARA | CHANDAPURA DIVISION | CH1 | Bommasandra | Bommasandra | F7- MAINE MATERIALS ROAD |  | Tree trimming, Maintenance of GOS, loose span restrining, Bent pole straightening | Maintenance Work |  |  | 11-09-2021 | Bommasandra Indl area 4th Phase |  |  | 10:00 | 12:00 | 2:00
11 | RAMANAGARA | CHANDAPURA DIVISION | CH1 | Bommasandra | Bommasandra | F8 BBS Alloys |  | Tree trimming, Maintenance of GOS, loose span restrining, Bent pole straightening | Maintenance Work |  |  | 11-09-2021 | Bommasandra Indl area 4th Phase |  |  | 10:00 | 12:00 | 2:00
12 | RAMANAGARA | CHANDAPURA DIVISION | CH1 | Bommasandra | Bommasandra | F11 Billforge |  | Tree trimming, Maintenance of GOS, loose span restrining, Bent pole straightening | Maintenance Work |  |  | 11-09-2021 | KSSIDC Sheds Bommasandra Indl area 4th Phase, Maini Road , MTR Road , RNS Motors road |  |  | 10:00 | 12:00 | 2:00
13 | RAMANAGARA | CHANDAPURA DIVISION | CH1 | Bommasandra | Bommasandra | F13- MESHA ENGINEERINR |  | Tree trimming, Maintenance of GOS, loose span restrining, Bent pole straightening | Maintenance Work |  |  | 11-09-2021 | KSSIDC Sheds Bommasandra Indl area 4th Phase, Maini Road , MTR Road , RNS Motors road |  |  | 10:00 | 12:00 | 2:00
14 | RAMANAGARA | CHANDAPURA DIVISION | CH1 | Hebbagodi | Electronic city | F19-KSSIDC |  | Tree trimming, Maintenance of GOS, loose span restrining, Bent pole straightening | Maintenance Work |  |  | 11-09-2021 | KSSIDC area |  |  | 10:00 | 12:00 | 2:00
15 | DAVANAGERE CIRCLE | HIRIYUR DIVISION | CK1 | O&M-1 | CHALLAKERE | F8 BALLERY ROAD | 11 KV Feeder | SHIFTING OF 11KV LINE | Maintenance Work |  |  | 11-09-2021 | BALLERY ROAD, CHITHRAIAHNAHATTY, JAFFER SHARIF LAYOUT, GORLAKATTE, AND VALMIKI NAGARA AND SOROUNDING AREAS. |  |  | 10:00 | 17:30 | 7:30
16 | RAMANAGARA | RAMANAGARA DIVISION | CP2 | Kudlur | AKKUR | F-2 GARAKAHALLI |  | MAINTENANCE | Maintenance Work |  |  | 11-09-2021 | SULLERI, GARAKAHALLI |  |  | 10:30 | 12:30 | 2:00
17 | BRC | HOSAKOTE | DH1 | Budigere | devanahalli | f-7 gangavara | 11KV Feeder | Maintance work with Jungle trimming | Maintenance Work |  |  | 11-09-2021 | haraluru s tellahalli balepura |  |  | 9:00 | 12:00 | 3:00
18 | BRC | NELAMANGALA DIVISION | DPT | Thyamagondlu | 66/11KV Thyamagondlu | TF7-Beeragondanahalli,TF8-Thotanahalli & TF5-Gundenahalli | 11 KV Branch line DTC 22 | for providing new25KVA at Thyamagondlu Town Limits village limits in Thyamagondlu section | Maintenance Work |  |  | 11-09-2021 | Thyamagondlu Town ,Beeragondana halli,Doddabele,muddalingana halli ,Thipaashetty Halli |  |  | 12:00 | 15:00 | 3:00
19 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | DV2 | O&M - 2 | DAVANAGERE | F-15 Commercial | 11 KV Feeder | DSCL | Maintenance Work | - |  | 11-09-2021 | Chowkipete Road, Vijayalaxmi Road, Kaipete road |  |  | 10:00 | 16:00 | 6:00
20 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | DV3 | Elebethur | Yaragunta_66 | F17-Amruthanagara | 11 KV Feeder | Maintenance of Microplan feeder-Jungle clearance, Load Balancing of DTCs | Maintenance Work | - |  | 11-09-2021 | Amruthanagara, Devarahatti, Chikkabudihal, Doddabudihal, B Kalapanahalli, Chittanahalli, Boosavvanahatti |  |  | 10:00 | 17:00 | 7:00
21 | EAST | INDIRANAGAR | E11 | Bhattarhalli | ITI | F7 KIADB | 11 kv Branch Line & LT Line With DTC 1.RMU-10 V/L-01 to F7 FDTC GREEN PARADISE 2.RMU-10 V/L-02 to F7 FDTC BESIDE ANANDHA SADAN 3.F7 FDTC BESIDE ANANDHA SADAN to F7 SDTC KEWA LOTUS 4.F7 SDTC KEWA LOTUS to F7 F DTC NEAR NEIYAPUNITYA L/O 5.RMU-10 V/L-03 to F7 SDTC DMAX | GOS&95 Sqmm Cable Charging | CAPEX |  |  | 11-09-2021 | Subhash nagar , TC palya , Bhatrahalli, halehalli , garden city college sorounding areas |  |  | 10:00 | 16:00 | 6:00
22 | EAST | SHIVAJINAGAR | E9 | GOVINDAPURA | HBR_66 | F08-RACHENAHALLI | 1 | DTC MAINTENANCE | Maintenance Work |  |  | 11-09-2021 | UMAR NAGARA,YAEEM NAGARA SURROUNDING AREAS |  |  | 10:00 | 12:30 | 2:30 | -
23 | EAST | SHIVAJINAGAR | E9 | Kothanur | Geddalahalli | F-07 | TC - SIVA SAKTHI | OH to UG Conversion | CAPEX | 1627944 & 01.04.2021 |  | 11-09-2021 | AVALAHALLI MAIN ROAD |  |  | 0:00 | 120:00 | 120:00 | -
24 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | GB1 | MANCHENAHALLI | Manchenahalli 66/11 | F10 MARIMAKALAHALLI | 11 kv Branch line DTC 152 | GOS Maintainance,Jungle cutting& LOOSE SPAN Restringing | Maintenance Work |  |  | 11-09-2021 | minakanagurki, marimakalahalli, sdandiganahalli, pidachalahalli, rayanakallu, kamabalahalli, kambathalli |  |  | 14:00 | 16:00 | 2:00
25 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | GB1 | O&M-2 | Gowribidanuru 220/66/11 | F5 INDUSTRIAL | 11 KV Feeder DTC 78 | service connection WORK | Maintenance Work |  |  | 11-09-2021 | Rymaonds , mini vidhana sowda , vedalaveni , sugar factory near |  |  | 14:00 | 16:00 | 2:00 | service connection
26 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | GB1 | HOSUR | Gowribidanuru 220/66/11 | F14 MUDUGERE | 11 KV Feeder DTC 80 | service connection WORK | Maintenance Work |  |  | 11-09-2021 | kadalaveni, mudugere, KT Halli, Kenkarte, Kachamachanahalli , channenahalli, dimmagattanahalli |  |  | 14:00 | 16:00 | 2:00 | service connection
27 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | GB1 | HOSUR | Gowribidanuru 220/66/11 | F14 MUDUGERE | 11 KV Feeder DTC 87 | service connection WORK | Maintenance Work |  |  | 11-09-2021 | kadalaveni, mudugere, KT Halli, Kenkarte, Kachamachanahalli , channenahalli, dimmagattanahalli |  |  | 14:00 | 16:00 | 2:00 | service connection
28 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | GB1 | MANCHENAHALLI | Manchenahalli 66/11 | F13 KAMAREDDYHALLI | 15 KV Feeder DTC 64 | GOS Maintainance,Jungle cutting& LOOSE SPAN Restringing | Maintenance Work |  |  | 11-09-2021 | minakanagurki, marimakalahalli, sdandiganahalli, pidachalahalli, rayanakallu, kamabalahalli, kambathalli |  |  | 14:00 | 16:00 | 2:00
29 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | GB1 | MANCHENAHALLI | Manchenahalli 66/11 | F6 KANAGANAKOPPA | 16 KV Feeder DTC 112 | GOS Maintainance,Jungle cutting& LOOSE SPAN Restringing | Maintenance Work |  |  | 11-09-2021 | minakanagurki, marimakalahalli, sdandiganahalli, pidachalahalli, rayanakallu, kamabalahalli, kambathalli |  |  | 14:00 | 16:00 | 2:00
30 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | GB1 | MANCHENAHALLI | Manchenahalli 66/11 | F1 DANDIGANAHALLI, | 17 KV Feeder DTC 130 |  | Maintenance Work |  |  | 11-09-2021 | minakanagurki, marimakalahalli, sdandiganahalli, pidachalahalli, rayanakallu, kamabalahalli, kambathalli |  |  | 14:00 | 16:00 | 2:00
31 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | GB1 | MANCHENAHALLI | Manchenahalli 66/11 | F3 JARABANDANAHALLI | 18 KV Feeder DTC 146 | GOS Maintainance,Jungle cutting& LOOSE SPAN Restringing | Maintenance Work |  |  | 11-09-2021 | minakanagurki, marimakalahalli, sdandiganahalli, pidachalahalli, rayanakallu, kamabalahalli, kambathalli |  |  | 14:00 | 16:00 | 2:00
32 | KOLAR CIRCLE | CHIKKABALLAPURA DIVISION | GD1 | GUDIBANDE | Gudibande_66 | F08-Bogenahalli | 11 KV Feeder DTC 167 | GOS Maintainance,Jungle cutting | Maintenance Work |  |  | 11-09-2021 | Bogenahalli,Chenduru,Dhumkuntahalli,Kondabanahalli,Gangadharapura,Eragareddyhalli |  |  | 13:00 | 15:00 | 2:00
33 | BRC | HOSAKOTE | HK1 | Hosakote Town | HOSAKOTE_66 | F1 JADIGENAHALLI | 11 KV Feeder | Maintenance Works | Maintenance Work |  |  | 11-09-2021 | F1 JADIGENAHALLI FEEDER MAINTENANCE WORK Kannurahalli, Nisarga Layout |  |  | 10:00 | 16:00 | 6:00
34 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | JL1 | Sokke | Sokke_66 | F02-Chikkaujjini | 11 KV Feeder | Maintenance work | Maintenance Work | - |  | 11-09-2021 | Sokke, chikkabantanahalli, gopalapura, gadimakunte, chikkaujjini, lakampura, kyasenahalli, tumbinakatte, gowripura and marikatte |  |  | 10:00 | 18:00 | 8:00
35 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | JL1 | Pallagatte | Pallagatte_66 | F01 to F08 | 11 KV Feeder | Maintenance work | Maintenance Work | - |  | 11-09-2021 | Kenchammanagattihalli, Diddagi, hucchangipura, ujjapavaderahalli, siddayyanakote, basavankote and uddaboranahalli Tarehalli, gode, goddadalinganahalli, mustugarahalli, miniragahalli, iyyanahalli, basavapura, chennapura, kodadagudda, suraddihalli, palanayakanakote, kallenahalli, suragondahalli, palanayakanakote, kallenahalli, medakeranahlli and suragondahalli hosuru |  |  | 9:00 | 18:00 | 9:00
36 | DAVANAGERE CIRCLE | DAVANAGERE DIVISION | JL1 | Bilichodu | Bilichodu_66 | F01 to F08 | 11 KV Feeder | Maintenance work | Maintenance Work | - |  | 11-09-2021 | Madanahalli, Bilichodu janatha colony, katenahalli, narenahalli, NR pura, chadaragolla, mucchunuru, kolamgatta, asagodu, dharmpura, oblapura, asagodu vaddarahatti, tuppadahalli and matigettahalli |  |  | 9:00 | 18:00 | 9:00
37 | RAMANAGARA | CHANDAPURA DIVISION | JN1 | KIADB | 66/11kv Kumbaranahalli | F6 Kumbaranahalli |  | GOS Maintanance works and tree trimming works | Maintenance Work |  |  | 11-09-2021 | Kumbaranahalli |  |  | 10:00 | 14:00 | 4:00
38 | WEST | KENGERI | K2 | Andrahalli | NG Halli | F-7-LT | Spur Line TC-29,118,06 | Estimate for conversion of LT OH to LT AB Cable of F07 feeder from NG Halli muss in Andrahalli O&M-2, K2 Sub divin, Kengeri Divin, Bangalore-91 | CAPEX | I-15407 I-15707 I-15607 Dt:13-01-2021 |  | 11-09-2021 | GANESH TEMPLE T.G PALYA |  |  | 10:00 | 17:00 | 7:00
39 | WEST | KENGERI | K2 | DB Kallu | NG Halli | F-12-HT | Full Feeder TC-68,29,63,26&NEW 110 | Estimate for conversion of 11KV OH Line to HT UG Cable of F12 feeder from NG Halli muss in Doddabidarakallu O&M-3, K2 Sub divin, Kengeri Divin, Bangalore | CAPEX | I-15412 I-15612 I-15712 ,DT:22-02-2021 |  | 11-09-2021 | Rukmini Nagar,Siddha ganga layout |  |  | 10:00 | 17:00 | 7:00
40 | WEST | KENGERI | K2 | Herohalli | Byadarahalli | F-3 -LT | Spur Line TC-121,TC-122,TC-123 | Estimate for conversion of LT OH to LT AB Cable of F3 feeder from Byadarahalli muss in Herohalli O&M-1, K2 Sub divin, Kengeri Divin, Bangalore-91 | CAPEX | I-15404 I-15704 I-15604 ,DT:13-01-2021 |  | 11-09-2021 | Hosahalli Road |  |  | 10:00 | 17:00 | 7:00
41 | RAMANAGARA | MAGADI | KD1 | KUDUR | SRIGIRI PURA | SF 2 VEERASAGARA |  | TREE TRIMMING & MAINTANANCE WORKS | Maintenance Work |  |  | 11-09-2021 | ANCHEPALYA, BETTALLI HOSALLI MALLAPPANAHALLI SRIGIRIPURA, VEERASAGARA |  |  | 11:00 | 12:00 | 1:00
42 | KOLAR CIRCLE | KGF DIVISION | KG1 | ROBERTSONPET-2 | KGF | F-15 | 11 kv Branch line | Est for APS to lgt. Inst. Of of sri. SALEEM s/o Abdul ahamad at Ashok nagar in R Pet-2 kgf s/d | CAPEX & Other Works |  |  | 11-09-2021 | Ashoknagarkrishnavaram |  |  | 11:00 | 11:45 | 0:45
43 | KOLAR CIRCLE | KOLAR DIVISION | KL2 | Kyalnur | Kyalanur | F09 A.R Agrahara | 11KV Feeder DTC 10 | For A/L/P/S of Smt Radamma W/o Seenappa at Balanagenahalli V in Kyalanur Section RSD Kolar. | CAPEX & Other Works | C-37250 dt:16.12.2020 |  | 11-09-2021 | Vishvanagar,Kamandahalli,Byrandahalli,Kadgattur & Beechagondanahalli |  |  | 11:00 | 12:30 | 1:30
44 | KOLAR CIRCLE | KGF DIVISION | MB1 | O&M2 | H.Gollahalli | F2,F6,F7,F8 | 11 kv Branch line DTC 54 | Est for evacuation of new link to GF4 Vommasandra feeder in O&M-II Sec. | Maintenance Work |  |  | 11-09-2021 | Vommasandra ,KOLADEVI, Kalikere,H gollahali, Sangasandra, Mathagatta |  |  | 0:00 | 0:00 | 0:00
45 | WEST | RAJAJINAGAR | N8 | NAGARABHAVI | CHANDRALAYOUT | F-07 | 782,755,297, N2HT82 | Conversion of 11KV Overhead line into HT Ug Cable inFeeder CL F7 (O&M Nagarbhvai) N8 Sub Division,Rajaji nagar Division Bangalore West Circle, BMAZ (South), BESCOM under PHASE-I on Total turnkey under Rate Contract (RC.05) on Percentage basis quoting. | CAPEX | 2020/RN/14-1927/N-106353/12.01.2022 |  | 11-09-2021 | MALAGALA VILLAGE | 0 | 350 | 10:30 | 17:30 | 7:00 | Works includes Srtinging of LT ab Cable one day and connecting servicing connections and load balancing one day
46 | SOUTH | JAYANAGAR | S2 | U-2 SAMPANGI RAMANAGAR | BMTC | F07 | DTC DTC NO:249 | LT AB CABLE STRINGING | CAPEX | K-8769 DATE:28.6.2021 1879-83 DATE:09.07-2021 |  | 11-09-2021 | VINOBHA NAGAR SLUM |  |  | 10:00 | 17:00 | 7:00
47 | SOUTH | JAYANAGAR | S2 | U-3 SHANTHINAGAR | BMTC | F11 | DTC DTC NO:354 | LT AB CABLE STRINGING | CAPEX | K-8771 DATE:28.6.2021 1849-58 DATE:09.07-2021 |  | 11-09-2021 | SWAMY ALCOVE 4TH CROSS |  |  | 10:00 | 17:00 | 7:00
48 | SOUTH | JAYANAGAR | S5 | ISRO layout | ISRO layout | F-08 Vikram Nagar | 11 KV Feeder DT-1, DT-02, DT-321 | 3GOS Structure Work | CAPEX | 14.1927/J-9038 |  | 11-09-2021 | Bikisipura,Mango Garden, Prathima Industrial Layout,kashi Nagar Lake, Isro Layout |  |  | 10:00 | 17:00 | 7:00
49 | SOUTH | JAYANAGAR | S5 | Vasanthpura | ISCKON | F-02 Kuvempu Nagar | 11 KV Feeder DTC-367,DTC368,DTC369,DTC374 | 3GOS Structure Work | CAPEX | 14.1927/J-9040 |  | 11-09-2021 | Vasantha Vallaba Nagar, kuvempu Nagar Main Road, Vasathapura |  |  | 10:00 | 17:00 | 7:00
50 | SOUTH | HSR | S8 | Hongasandra | Naganathapura | F16 | 11 KV Feeder | Preventive Maintenance of the feeder , Tree trimming , Jump renovation | Maintenance Work |  |  | 11-09-2021 | AECS Layout B Block and sourroundings |  |  | 10:30 | 14:00 | 3:30 | Naganathpura F8 Feeder
51 | SOUTH | JAYANAGAR | S9 | PADMANABHA NAGAR | Padmanabhanagar | F08-Rajiv Nagar | DTC TC-85 | LT AB Cable Laying+Charging | CAPEX | 14.1927/J-9011/17.12.2020 & 14.1927/J-9034/15.03.2021 |  | 11-09-2021 | 18th Main |  |  | 10:00 | 17:00 | 7:00
52 | SOUTH | JAYANAGAR | S9 | PADMANABHA NAGAR | Padmanabhanagar | F09-Padmanabhanagar | DTC TC-86 | LT AB Cable Laying+Charging | CAPEX | 14.1927/J-9033/15.03.2021 & 14.1927/J-9012/17.12.2020 |  | 11-09-2021 | Padmanabhanagara bus stand ,Puttalingaiah Road ,Carmel School |  |  | 10:00 | 17:00 | 7:00
53 | SOUTH | JAYANAGAR | S9 | BSK 2nd Stage | Padmanabhanagar | F03-S9 Office | 11KV Feeder/DTC TC-296 | 3 GOS Structure/LT AB Cable | CAPEX | 14.1927/J-9027/15.03.2021 & 14.1927/J-9009/17.12.2020 |  | 11-09-2021 | 14th main road,13th main road,7th main road |  |  | 10:00 | 17:00 | 7:00
54 | SOUTH | JAYANAGAR | S9 | BSK 2nd Stage | Padmanabhanagar | F05 9th Main Bata Show Room | 11KV Feeder/DTC TC-192 | 3 GOS Structure/LT AB Cable | CAPEX | 14.1927/J-9029/15.03.2021 & 14.1927/J-11066/04.12.2020 |  | 11-09-2021 | CHINNAPPANAIDU LAYOUT bsk 3 rd Stage |  |  | 10:00 | 17:00 | 7:00
55 | SOUTH | JAYANAGAR | S9 | BSK 2nd Stage | Padmanabhanagar | F10-Yarab Nagar | DTC TC-22 | LT AB Cable | CAPEX | 14.1927/J-9030/15.03.2021 & 14.1927/J-9014/17.12.2020 |  | 11-09-2021 | 31st Main,29th Main Yarab Nagar |  |  | 10:00 | 17:00 | 7:00
56 | TUMKUR CIRCLE | TUMKUR DIVISION | TK1 | central section | Tumkur | TF-09 (NJY) | DTC4 | Jangalcatting | Maintenance Work |  |  | 11-09-2021 | Belagumba,Kundur, Bhagyanagara |  |  | 10:30 | 13:30 | 3:00
57 | TUMKUR CIRCLE | TUMKUR DIVISION | TK2 | SARASWATHIPURAM | MELEKOTE | MF1, MF2,MF10, MF11, MF12, MF4,MF5,MF9,MF35 | 11 KV Feeder DTC 383 | Smart City Ring Road Pole Shifting Work | CAPEX & Other Works | Work Om No EE(ELE)/AEE/O/TA32019-2020/5670.72/20-08-2019 Work Om No EE(ELE)/AEE/O/TA32019-2020/4204-07/09-07-2019 Work Om No EE(ELE)/AEE/O/TA32019-2020/4200-03/09-07-2019 Work Om No EE(ELE)/AEE/O/TA32019-2020/4196.99/09-07-2019 Work Om No EE(ELE)/AEE/O/TA32019-2020/4196.99/09-07-2019 Work Om No EE(ELE)/AEE/O/TA32019-2020/4216.19/09-07-2040 |  | 11-09-2021 | Melekote, Gangasandra, Tuda layout, Danah Palace, UGD, Tippunagara, Nazarabadh, Veerasagara, Kuripalya, Goodshed, Shanthinagara, Upparahalli, Sadhashivanagara, Amarajyothi Nagara, Kumutaiah Badavane, Ramajoyes Nagara, Saraswathipuram 1ST and 2nd stage, Banashankari 1st and 2nd stage, Yadava Nagara, Maralooru, Maralooru Janatha Colony,Pragathi Badavane, Geddalahally, Gubbi Gate, Kuntammana Thota Dibburu,BH Palya, PH Colony, Vinoba Nagara, EdgaMohalla, Hegade Colony, Tilak Park, Jaipura, KHB Colony, bandimane Choutry |  |  | 7:12 | 17:30 | 10:18
58 | TUMKUR CIRCLE | TUMKUR DIVISION | TK3 | KORA | 66/11kV MUSS Kora | KF7 KORA | 11 KV Feeder DTC 62 | KF7 KORA maintenance work | Maintenance Work |  |  | 11-09-2021 | KORA ,CHIKKONAHALLY, KATENAHALLY , MASTIPALYA,HARIYAPPANAHALLY,BRAMHASANDRA,BURADAGATTA, |  |  | 10:00 | 14:00 | 4:00
59 | WEST | RR NAGAR | W2 | SHANKAR PURAM | NATIONAL_COLLEGE_66 | F09-UTTARADI-MUTT-RMU | DTC DTC DTC NO:108 | Micro feeder Plan work | Maintenance Work |  |  | 11-09-2021 | SAMEER PURAM MAIN ROAD & NANJAPPA BLACK |  |  | 9:45 | 12:00 | 2:15
60 | DAVANAGERE CIRCLE | HIRIYUR DIVISION | HY1 | HARIYABBE | PD KOTE_66 | F05-HALAGALADDI NJY ,F02-PD-KOTE | 11 KV Feeder | Running 11 Kv Line from Pd ko T0 muss to hoskere limits | Maintenance Work |  |  | 11-09-2021 | maddihally,P.D.Kote,Kanajanahally,Benakanahally,hoskere |  |  | 10:00 | 17:00 | 7:00
61 | DAVANAGERE CIRCLE | HIRIYUR DIVISION | HY1 | HARIYABBE | PD KOTE_66 | F05-HALAGALADDI NJY ,F02-PD-KOTE | 11 KV Feeder | Running 11 Kv Line from Pd ko T0 muss to Benakanahally limits | Maintenance Work |  |  | 11-09-2021 | maddihally,P.D.Kote,Kanajanahally,Benakanahally,hoskere |  |  | 10:00 | 17:00 | 7:00
62 | WEST | RAJAJINAGAR | N6 | 1- KAMAKSHI PALYA | Vijayanagar | F7 | TC-21,20,13,22,28,26,29,33,34,37,38,39,172,173,184,220,231,253,281,283,294,300,301,304,662,664,756,804,863,839,886 | ESTIMATE FOR CONVERSION OF LT OVERHEAD LINE TO LT AB CABLE IN F -07 FEEDER OF VIJAYA NAGAR MUSS IN O&M-01 OF N6 SUB DIVISION | CAPEX | 4330-38/ 30.11.2020 |  | 11-09-2021 | MANIVILLA GARDEN , KAMAKSHIPALYA, VINAYAKA NAGARA, SHIVAFARM, SHIVA TEMPLE , ANDANAPPA LAYOUT, MARIYAPPA ROAD, KAMAKSHIPALYA |  | 6500 | 10:30 | 17:30 | 7:00 | Work will be taken up as schelduled from 1ST SEP 2021
63 | WEST | RAJAJINAGAR | N6 | 3 - SUNKADAKATTE | SRIGANDHA KAVALU | F-6 | TC-542,222,904, 295,744,352,375,353,N6HT-72, 869, 890, 929, N6HT-104, 134, 774, 302, N6HT-33, 133, 581, 581, 740,327, 328, 349,942,860, 135, 852, 228, 895, 831,946, 916, 735, 684, 131, 157, 302, N6HT33, 133,581, 740, 327,328,943,818,N6HT7, 938, 850,816, 342, 126,215, 125,343, 341, 893,54 | ESTIMATE FOR CONVERSION OF HT OVERHEAD LINE TO HT UG CABLE IN F -06 FEEDER OF SRIGANDHA KAVALU MUSS IN O&M-02 OF N6 SUB DIVISION | CAPEX | N-106352/ |  | 11-09-2021 | LAKSHMANA NAGARA, SANJEEVINI NAGARA, VIGNESHWARA NAGARA, HEGGANAHALLI, HEGGANAHALLI CROSS, SUNKADAKATTE, PIPELINE RAOAD SUNAKADAKATTE. |  | 4000 | 10:30 | 17:30 | 7:00 | Work will be taken up as schelduled from 1ST SEP 2021
64 | WEST | RAJAJINAGAR | N2 | MARENAHALLI | VIJAYNAGARA | F8 | 1)DTC164-N2 SUBDIVISION OFFICE 2)DTC51-GOVINDARAJ NAGAR 3)DTC522-GOVINDARAJ NAGAR GOVT SCHOOL 4)DTC184-BCES HBCS. | Estimate for conversion of LT Overhead line in to AB Cable pertaining to F8 Feeder , Vijaynagara MUSS in O&M-5,N2 Sub-division. | CAPEX | 2020/RN/14.1927/P-106373/17-03-2021 |  | 11-09-2021 | N2 SUBDIVISION OFFICE, GOVINDARAJ NAGAR,GOVINDARAJ NAGAR GOVT SCHOOL, ,BCES HBCS. | 0 | 4295 | 10:30 | 17:30 | 7:00
65 | WEST | RAJAJINAGAR | N2 | MARENAHALLI | Chandralayout | F1 | 1)DTC140-WIDIA LAYOUT,KOLIMANE ROAD 2)DTC14-ATTIGUPPE PETROL BUNK MAIN ROAD 3)DTC31-ATTIGUPPE INCOME TAX LAYOUT 4)DTC254-WIDIA LAYOUT 5)DTC117-WIDIA LAYOUT 6)DTC52-WIDIA LAYOUT 7)DTC336-BHEL GUEST HOUSE 8)DTC85- BASAVESHWARA LAYOUT 9)DTC243-NEAR BUNT SANGHA, SUBBANNA GARDEN 10)DTC13- BHEL TOWNSHIP, SUBBANNA GARDEN 11)DTC34-BHEL TOWNSHIP, SUBBANNA GARDEN 12)DTC317- BASAVESHWARA LAYOUT 13)DTC198- SUBBANNA GARDEN . | Estimate for conversion of LT Overhead line in to AB Cable pertaining to F1 Feeder , CHANDRALAYOUT MUSS in O&M-5,N2 Sub-division. | CAPEX | 2021/RN/14.1927/P-113459-15-04-2021 |  | 11-09-2021 | WIDIA LAYOUT,KOLIMANE ROAD,ATTIGUPPE PETROL BUNK MAIN ROAD,ATTIGUPPE INCOME TAX LAYOUT,WIDIA LAYOUT,BHEL GUEST HOUSE, BASAVESHWARA LAYOUT,NEAR BUNT SANGHA, SUBBANNA GARDEN,BHEL TOWNSHIP, SUBBANNA GARDEN, BASAVESHWARA LAYOUT,SUBBANNA GARDEN . | 9 | 5695 | 10:30 | 17:30 | 7:00
66 | WEST | RAJAJINAGAR | N2 | MARENAHALLI | Remco | F9 | 1)DTC76-GANGONDANA HALLY 2)DTC218-CHANDRALAYOUT 3DTC368-HBCS LAYOUT 2,BCC LAYOUT 4)DTC554-GANGONDANAHALLI MAIN ROAD PARK SERVICE ROAD 5)DTC118-BINNY LAYOUT 6)DTC126-GOODWILL APPT 7)DTC86-GOODWILL APPT 8)DTC38-BINNY LAYOUT 9)DTC120-BINNY LAYOUT 10)DTC206-ATTIGUPPE NEAR GOVT COLLAGE 11)DTC116-INDIRA COLONY 12)DTC160-MICO LAYOUT II 13)DTC66-MICO LAYOUT 14)DTC159-CHANDRA LAYOUT,NEAR 15)DTC37-BCC LAYOUT 16)DTC77-GANGONDANA HALLY17)DTC74-GANGONDANA HALLY 18)DTC75-GANGONDANA HALLY 19)DTC148-MICO LAYOUT 20)DTC82-BCC LAYOUT 21)DTC205-ATTIGUPPE NEAR GOVT COLLAGE 22)DTC275-BCC LAYOUT WATER TANK BACK SIDE23)DTC76-GANGONDANA HALLY. | Estimate for conversion of LT Overhead line in to AB Cable pertaining to F9 Feeder , Remco MUSS in O&M-5,N2 Sub-division. | CAPEX | 2020/RN/14.1927/N-19-11-2020 |  | 11-09-2021 | GANGONDANA HALLY -CHANDRALAYOUT HBCS LAYOUT 2,BCC LAYOUT GANGONDANAHALLI MAIN ROAD PARK SERVICE ROAD 5)DTC118-BINNY LAYOUT GOODWILL APPT ,-GOODWILL APPT BINNY LAYOUT ,BINNY LAYOUT ,ATTIGUPPE NEAR GOVT COLLAGE ,INDIRA COLONY, MICO LAYOUT II ,MICO LAYOUT CHANDRA LAYOUT,NEAR,BCC LAYOUT GANGONDANA HALLY ,GANGONDANA HALLY -GANGONDANA HALLY ,MICO LAYOUT -BCC LAYOUT ,ATTIGUPPE NEAR GOVT COLLAGE -BCC LAYOUT WATER TANK BACK SIDE,GANGONDANA HALLY. | 10 | 5511 | 10:30 | 17:30 | 7:00
67 | WEST | RAJAJINAGAR | N2 | MARENAHALLI | NRS | F18 | 1)DTC67-SARASWATHI IRON 2)DTC308-CENTRAL EXCISE LAYOUT 3)DTC307-HARIRAM ALIAS LAYOUT 4)DTC309-HARIRAM ALIAS LAYOUT 5)DTC127-11TH MAIN , M C LAYOUT 6)DTC60-C.E.S LAYOUT 7)DTC16- BAPUJI LAYOUT 8)DTC70- SARASWATHI NAGAR 9)DTC124- BINNY LAYOUT 10)DTC310- 4TH CRS,CENTRAL EXCISE 11)DTC305-MC LAYOUT INDUSTRIAL AREA 12)DTC122-BINNY LAYOUT 13)DTC23-LIBRARY 2 14)DTC154-M.C. LAYOUT 15)DTC17-VINAYAKA LAYOUT 16)DTC27-BAPUJI LAYOUT 17)DTC559-NEAR SARASWATHINAGARA APPARTMENT 18)DTC01-VEERESH THEATER 19)DTC209-HARIRAM ALIDAS LAYOUT 20)DTC150-3RD CROSS, CENTRAL EXISE LAYOUT 21)DTC09- CENTRAL EXCISE LAYOUT 22)DTC47-C.S.LAYOUT 23)DTC02-8TH CROSS , M C LAYOUT 24)DTC42- M C LAYOUT 25)DTC22-LIBRARY 1, M C LAYOUT 26)DTC144- BAYANNA INDL ESTATE AD HALLY , MC LAYOUT 27)DTC151-SHANIMAHATHMA TEMPLE, MC LAYOUT 28)DTC55-13TH CROSS M.C.LAYOUT 29)DTC225-MC LAYOUT 2ND CROSS 30)DTC188-MC LAY OUT NEAR CUTEES HOSPITAL 31)DTC270-BAPUJI LAYOUT 32)DTC366-GKW LAYOUT 33)DTC36-SECRETARIATE LAYOUT 34)DTC112-MARENA HALLI | Estimate for conversion of LT Overhead line in to AB Cable pertaining to F18 Feeder , NRS MUSS in O&M-5,N2 Sub-division. | CAPEX | 2021/RN/14.1927/P-113460/15-04-2021 |  | 11-09-2021 | SARASWATHI IRON CENTRAL EXCISE LAYOUT ,HARIRAM ALIAS LAYOUT ,HARIRAM ALIAS LAYOUT ,11TH MAIN , M C LAYOUT ,C.E.S LAYOUT BAPUJI LAYOUT SARASWATHI NAGAR BINNY LAYOUT,4TH CRS,CENTRAL EXCISEMC LAYOUT INDUSTRIAL AREA BINNY LAYOUT LIBRARY 2 ,M.C. LAYOUT VINAYAKA LAYOUTBAPUJI LAYOUT NEAR SARASWATHINAGARA APPARTMENT VEERESH THEATER 19)DTC209-HARIRAM ALIDAS LAYOUT 3RD CROSS, CENTRAL EXISE LAYOUT,CENTRAL EXCISE LAYOUT,C.S.LAYOUT,8TH CROSS , M C LAYOUT M C LAYOUT LIBRARY 1, M C LAYOUT BAYANNA INDL ESTATE AD HALLY , MC LAYOUT,SHANIMAHATHMA TEMPLE, MC LAYOUT 13TH CROSS M.C.LAYOUTMC LAYOUT 2ND CROSS MC LAY OUT NEAR CUTEES HOSPITAL BAPUJI LAYOUT -GKW LAYOUT -SECRETARIATE LAYOUT,MARENA HALLI . | 17 | 7069 | 11:30 | 17:30 | 6:00 | Work will be taken up as schelduled from 3rd SEP 2021
68 | WEST | RAJAJINAGAR | N2 | MARENAHALLI | Chandralayout | F2 | 1)DTC265-VYALIKAVAL HBCS LAYOUT 2)DTC268- VYALIKAVAL HBCS LAYOUT 3)DTC267- VYALIKAVAL HBCS LAYOUT 4)DTC40-GKW LAYOUT 5)DTC197-GKW LAYOUT 6TH MAIN 6)DTC468-PRIYADARSHINI LAYOUT 7)DTC54-PRIYADARSHINI LAYOUT 8)DTC437-PRIYADARSHINI LAYOUT 9)DTC192- SUBBANA GARDEN 10)DTC266- VYALIKAVAL HBCS, NEAR 11)DTC62-VINAYAKA LAYOUT 12)DTC84-ADJASCENT TO WIIDIA LAYOUT 13)DTC155- NEAR VINAYAKA LAYOUT 14)DTC190-VINAYAKA LAYOUT 15)DTC316-VINAYAKA LAYOUT 1ST MAIN 16)DTC83- SUBBANNA GARDEN17)DTC328- SUBBANNA GARDEN 18)DTC147-SHIVANANDNAGARA 19)DTC156- VINAYAKA LAYOUT 3RD MAIN 20)DTC315-VINAYAKA LAYOUT 1ST MAIN 21)DTC59-MOODALAPALYA 22)DTC46- CHANDRA LAYOUT 23)DTC90- CHANDRA LAYOUT 24)DTC18-GKW LAYOUT 25)DTC115-GKW LAYOUT 26)DTC87-PF LAYOUT 27)DTC88-PF LAYOUT 28)DTC49-VINAYAKA LAYOUT 29)DTC314-VINAYAKA LAYOUT 3RD MAIN 30)DTC245-VYALIKAVAL LAYOUT 31)DTC265-VYALIKAVAL HBCS 32)DTC89-KPA BLOCK CHANDRALAYOUT. | Estimate for conversion of LT Overhead line in to AB Cable pertaining to F2 Feeder , Chandralayout MUSS in O&M-5,N2 Sub-division. | CAPEX | 2021/RN/14.1927/P-113457/15-04-2021 |  | 11-09-2021 | VYALIKAVAL HBCS LAYOUT,GKW LAYOUT,GKW LAYOUT 6TH MAIN, PRIYADARSHINI LAYOUT,SUBBANA GARDEN, VYALIKAVAL HBCS, NEARVINAYAKA LAYOUT, ADJASCENT TO WIIDIA LAYOUT,NEAR VINAYAKA LAYOUT, 1ST MAIN SUBBANNA GARDEN, SHIVANANDNAGARA, ,VINAYAKA LAYOUT 3RD MAIN,VINAYAKA LAYOUT 1ST MAIN,MOODALAPALYA, CHANDRA LAYOUT,GKW LAYOUT,PF LAYOUT,VINAYAKA LAYOUT,VINAYAKA LAYOUT 3RD MAIN,VYALIKAVAL LAYOUT VYALIKAVAL HBCS KPA BLOCK, CHANDRALAYOUT. | 6 | 10122 | 10:30 | 17:30 | 7:00
69 | WEST | RAJAJINAGAR | N2 | MARENAHALLI | Chandralayout | F6 | 1)DTC269-NANJARASAPPA LAYOUT 2)DTC327- NEAR SKYLINE BBMP PARK 3)DTC222- BAPUJI HBCS LAYOUT 4)DTC200-CANARA BANK COLONY 5)DTC330 MARUTHINAGARA 6)DTC320-CHANDRA LAYOUT 7)DTC250- BAPUJI LAYOUT 8)DTC71-CHICKPETE LAYOUT 9)DTC221-BAPUJI LAYOUT10)DTC19-CANARA BANK COLONY 11)DTC162-SKYLINE APARTMENT MAIN ROAD12)DTC111-CANARA BANK COLONY13)DTC503-ANUBHAVA NAGARA 14)DTC137-MARUTHI NAGARA15_DTC332-NAGARABHAVI MAIN ROAD 16)DTC43-MARUTHINAGARA17)DTC323- MARUTHINAGARA 3RD MAIN 18)DTC64-CANARA BANK COLONY 19)DTC269-MC LAYOUT JAYALAKSHMI INDUSTRIAL. | Estimate for conversion of LT Overhead line in to AB Cable pertaining to F6 Feeder , Chandralayout MUSS in O&M-5,N2 Sub-division. | CAPEX | 2021/RN/14.1927/P-113458/15-04-2022 |  | 11-09-2021 | NANJARASAPPA LAYOUT NEAR SKYLINE BBMP PARK BAPUJI HBCS LAYOUT CANARA BANK COLONY,MARUTHINAGARA CHANDRA LAYOUT BAPUJI LAYOUT CHICKPETE LAYOUT BAPUJI LAYOUT CANARA BANK COLONY SKYLINE APARTMENT MAIN ROAD ,CANARA BANK COLONY ,ANUBHAVA NAGARA,MARUTHI NAGARA15,NAGARABHAVI MAIN ROAD,MARUTHINAGARA,MARUTHINAGARA 3RD MAIN,CANARA BANK COLONY MC LAYOUT JAYALAKSHMI INDUSTRIAL. | 2 | 5840 | 10:30 | 17:30 | 7:00
70 | WEST | RAJAJINAGAR | N2 | MARENAHALLI | Chandralayout | F8 | 1)DTC213-CHANDRALAYOUT NEAR SIDDAGANGA SCHOOL BACK SIDE 2)DTC460-Siddaganga School Back side 3)DTC226- INCOME TAX LAYOUT 4)DTC227-INCOME TAX LAYOUT 5)DTC228-INCOME TAX LAYOUT 6)DTC229-INCOME TAX LAYOUT 7)DTC233- VIDYAGIRI LAYOUT 8)DTC157- CHANDRA LAYOUT, BUS 9)DTC119-MARUTHI NAGARA 10)DTC260-CHANDRA LAYOUT 80FEET ROAD 11)DTC458-CHANDRA LAYOUT SIDDAGANGA SCHOOL BACKSIDE 12)DTC450- CHANDRA LAYOUT 80FEET ROAD MARUTHINAGARA 13)DTC438-CHANDRA LAYOUT BMTC DEPOT 14)DTC93- CHANDRA LAYOUT 15)DTC94-CHANDRA LAYOUT MILK BOOTH 16)DTC20-CHANDRA LAYOUT 17)DTC73-CHANDRA LAYOUT 18)DTC72- BASAVESHWARA LAYOUT 19)DTC321- KPA CHANDRA LAYOUT 20)DTC215- MARUTHI NAGARA 80 FEET ROAD 21)DTC263-MARUTHI NAGARA 80 FEET ROAD 22)DTC203- CHANDRALAYOUT 23)DTC244-JYOTHINAGARA 24)DTC168-BCES HBCS 25)DTC169- BCES HBCS 26)DTC232- INCOME TAX LAYOUT 27)DTC233- INCOME TAX LAYOUT 28)DTC261-CHANDRALAYOUT 29)DTC179-BCES HBCS 30)DTC178-BCES HBCS 31)DTC92-N-BHAVI,1 STG,BHND 32)DTC149-SBI, CHANDRALAYOUT 33)DTC240-8TH CROSS, M C LAYOUT 34)DTC50-CHANDRA LAYOUT 35)DTC45- NAGARABHAVI 36)DTC252- CHANDRALAYOUT 12TH CROSS 37)DTC253-CHANDRALAYOUT 11TH CROSS 38)DTC166-BCES HBCS 39)DTC262-CHANDRALAYOUT 12TH CROSS 40)DTC167-BCES HBCS 41)DTC61-CHANDRA LAYOUT SLUM 42)DTC132-CHANDRALAYOUT 43)DTC177- BCES HBCS 44)DTC173- BCES HBCS 45)DTC171- BCES HBCS 46)DTC170- BCES HBCS 47)DTC230-INCOME TAX LAYOUT 48)DTC219-CHANDRALAYOUT 49)DTC181-BCES HBCS 50)DTC182-BCES HBCS 51)DTC459-Siddaganga School Back side. | Estimate for conversion of LT Overhead line in to AB Cable pertaining to F8 Feeder , CHANDRALAYOUT MUSS in O&M-5,N2 Sub-division. | CAPEX | 2021/RN/14.1927/ |  | 11-09-2021 | CHANDRALAYOUT NEAR SIDDAGANGA SCHOOL BACK SIDE ,Siddaganga School Back side , INCOME TAX LAYOUT ,VIDYAGIRI LAYOUT , CHANDRA LAYOUT, BUS ,MARUTHI NAGARA ,CHANDRA LAYOUT 80FEET ROAD ,CHANDRA LAYOUT BMTC DEPOT ,CHANDRA LAYOUT MILK BOOTH , BASAVESHWARA LAYOUT , KPA CHANDRA LAYOUT , MARUTHI NAGARA 80 FEET ROAD ,JYOTHINAGARA ,N-BHAVI,1 STG,BHND ,SBI, CHANDRALAYOUT,8TH CROSS, M C LAYOUT ,NAGARABHAVI ,CHANDRALAYOUT 12TH CROSS ,CHANDRALAYOUT 11TH CROSS ,BCES HBCS ,CHANDRALAYOUT 12TH CROSS ,CHANDRA LAYOUT SLUM. | 0 | 10542 | 10:30 | 17:30 | 7:00
71 | WEST | RAJAJINAGAR | N10 | PATTEGAR PALYA | Vijayanagar | F15 | 6ADTC-595,437,317,238,252,237,30,318,268,417,702,471,02,784,31,735,644,760,280,19,21,25,553,270,772 | ESTIMATE FOR CONVERSION OF LT OVERHEAD LINE TO LT AB CABLE IN F -15 FEEDER OF VIJAYA NAGAR MUSS IN O&M-6A PATTEGARAPALYA OF N10 SUB DIVISION | CAPEX | 113467/15.04.2021 |  | 11-09-2021 | PETECHANNAPPA INDUSTRAIL AREA | 0 | 685 | 11:30 | 17:30 | 6:00 | Work will be taken up as schelduled Saturday & Sunday only
72 | WEST | RAJAJINAGAR | N10 | PATTEGAR PALYA | Vijayanagar | F10 | 6ADTC-32,33,326,732,552,36,35,525,296,710,411,41,368,587,500,409,34,749,37,779,216,39,580 | ESTIMATE FOR CONVERSION OF LT OVERHEAD LINE TO LT AB CABLE IN F -10 FEEDER OF VIJAYA NAGAR MUSS IN O&M-6A PATTEGARAPALYA OF N10 SUB DIVISION | CAPEX | 106346/19.11.2020 |  | 11-09-2021 | KAMAKSHIPALYA INDUSTRIAL ESTATE,KCG ESTATE | 0 | 485 | 11:30 | 17:30 | 6:00 | Work will be taken up as schelduled Saturday & Sunday only
73 | WEST | RAJAJINAGAR | N10 | PATTEGAR PALYA | Vijayanagar | F15 | PETECHANNAPPA INDUSTRIAL AREA FEEDER OH TO UG STRUCTURE WORK | ESTIMATE FOR CONVERSION OF HT OVERHEAD LINE TO UG CABLE IN F -15 FEEDER OF VIJAYA NAGAR MUSS IN O&M-6A PATTEGARAPALYA OF N10 SUB DIVISION | CAPEX | N-106357/12.02.2021 |  | 11-09-2021 | PETECHANNAPPA INDUSTRAIL AREA | 5 | 685 | 11:30 | 17:30 | 6:00 | Work will be taken up as schelduled Saturday & Sunday only
74 | WEST | RAJAJINAGAR | N10 | PATTEGAR PALYA | Vijayanagar | F10 | KAMAKSHI PALYA INDUSTRIAL AREA FEEDER OH TO UG STRUCTURE WORK | ESTIMATE FOR CONVERSION OF HT OVERHEAD LINE TO UG CABLE IN F -10 FEEDER OF VIJAYA NAGAR MUSS IN O&M-6A PATTEGARAPALYA OF N10 SUB DIVISION | CAPEX | 2019/RN/14-1927/M-97837/31.03.2020 |  | 11-09-2021 | KAMAKSHIPALYA INDUSTRIAL ESTATE,KCG ESTATE | 4 | 485 | 11:30 | 17:30 | 6:00 | Work will be taken up as schelduled Saturday & Sunday only
75 | TUMKUR CIRCLE | TUMKUR DIVISION | YD1 | Yediyur | Jiddigere | F4 Jiddigere | F4 Jiddigere DTC 90 | Estimate for providing 11KV Link line for reduce the over load of F-4 Jiddigere Feeder ( Jiddigere 66/11KV MUSS) , Jiddiger 66/11 KV MUSS to Yallapura village in Yediyur section, Yediyur Subdivision. | CAPEX | C-201 / 29.08.2020 |  | 11-09-2021 | Chottanahallygate,Yallapura gate devara kannasandra,Channthimmanapalya |  |  | 10:00 | 17:00 | 7:00
76 | DAVANAGERE CIRCLE | CHITRADURGA DIVISION | SRP | belagur | 66/11kv garaga muss | F9 Kalkere feeder from Garga MUSS to Kabbala dibba -12kms | 11 KV Feeder | 11KV Link line to Bifurcate the load on F9 Kalkere feeder from Garga MUSS to Kabbala dibba -12kms | Maintenance Work |  |  | 11-09-2021 | Hosadurga town and devigere panchayath limit villages,madure panchayath limit villages and Hebballi gramapanchayath limit villages |  |  | 10:00 | 18:00 | 8:00
77 | DAVANAGERE CIRCLE | HIRIYUR DIVISION | TLK | Talak | 66/11KV Talak MUSS | F01 Devarahalli, F11 Rudrammanahalli | 11 KV Feeder | Estimate for Reconductoring of 2/4ACSR Conductor by Rabbit ACSR Conductor of F01 Devarahalli Feeder from 66/11KV Talak MUSS to N Devarahalli village Limits in O&M Section Talak of Talak Sub Division. | Capex |  |  | 11-09-2021 | Hosahalli, Marenahatti. N Devrahalli ,Bhiminakere, Kalderahatti |  |  | 10:00 | 18:00 | 8:00
78 | TUMKUR CIRCLE | TUMKUR DIVISION | YD1 | Amruthur | Amruthur 66/121 KV | F 6 Snanba | F 6 Snanba DTC 80 | Estimate for providing 11KV Link line for reduce the over load of F-6 Sanaba Feeder Amruthur 66/11KV MUSS) Link line ,from Amruthur MUSS to Chikkakere in Amruthur section, Yediyur Subdivision. | Maintenance Work | C-11713 / 23.03.2021 |  | 11-09-2021 | Amruthur village limits sondekoppa Indiranagara,Hosakere gate |  |  | 10:00 | 17:00 | 7:00
79 | DAVANAGERE CIRCLE | CHITRADURGA DIVISION | HL1 | CHIKKAJAJUR | Sasalu66/11KV | F4-Kalaghatta,F9-Topenahalli NJY, F8-hreyemmiganur,F7-dandigenahalli | 11 KV Feeder | 11KV Link line from Sasalu MUSS to Kalaghatta vaddarahati limits | Maintenance Work |  |  | 11-09-2021 | Kalaghatta,dandigenahalli, Hiriyur,Vishwanathanahalli,anthapura Nandhihall,hireyemmiganur,Kamanahalli, |  |  | 10:00 | 18:00 | 8:00
80 | TUMKUR CIRCLE | MADHUGIRI DIVISION | KR1 | O&M-2 | Koratagere 66/11kV | F05 Koratagere Town | DTC 2 | For LT Re-conductoring of Kote TC 250 KVA DTC in O&M-1 Section | CAPEX | R-33767/12.02.2021 |  | 11-09-2021 | Koratagere Town |  |  | 10:00 | 17:00 | 7:00
81 | TUMKUR CIRCLE | MADHUGIRI DIVISION | KR1 | Thovinakere | Thovinakere 66/11kV | F13 Chowdeswari | DTC 54 | for Jungle cutting GOS & DTC maintenace | Maintenance Work |  |  | 11-09-2021 | Dasalakunte, Manuvinakurike, Kurmkote panchayat limits |  |  | 11:00 | 15:00 | 4:00 | LC given only in Load Shedding time of Agri feeders
82 | TUMKUR CIRCLE | TUMKUR DIVISION | KU1 | O&M-2 | Kunigal 66/11 | F 8 Baktharahally | F 8 Baktharahally DTC 70 | Est for proposed new link line from 66/11KV MUSS Kunigal to Kottagere village to construct new dedicated Honnenahally feeder in O&M-2 Sec, KunigalS/D | Maintenance Work | C-106/22.02.2021 |  | 11-09-2021 | Kothagere Panchayat |  |  | 10:00 | 17:00 | 7:00
83 | DAVANAGERE CIRCLE | HIRIYUR DIVISION | TLK | Doddaullarthi | 66/11KV Mylenahalli MUSS | F05 Mylenahlli, F11 Kamasamudra NJY | 11 KV Feeder | Running New 11KV Link Line from Mylenahalli MUSS to Basapura village limits for reducing load of existing 11KV Feeder F05 Mylenahalli Feeder og 66/11KV MUSS Mylenahalli | Maintenance Work |  |  | 11-09-2021 | Renukapura,Basapura |  |  | 10:00 | 18:00 | 8:00
84 | TUMKUR CIRCLE | TUMKUR DIVISION | HLD | Yadavani | Yadavani 66/11 KV | F8 Kodavathi | F8 Kodavathi DTC 60 | To Raplace 2/4 ACSR Conductor by rabbit conductor from Sugganahalli to Torebommanahalli of F8 Kodavathi feeder 66/11 KV Yadavani MUSS Yadavani Sec H Durga S/D | CAPEX | C-752 / 10.09.2020 |  | 11-09-2021 | Sugganahally Villagae limits,Torebaommanahally Kodavathi. |  |  | 10:00 | 16:00 | 6:00
85 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | KADABA | KGTEMPLE -110/11KV | All feeder of station | 11 KV Feeder DTC 132 | For Providing Evacation of New 11 KV Link Line From K G Temple Muss to Dadubai Palya Village Limits to Biforcate Load From F4 Kunnala Feeder From K G Temple Muss Due to Over Load in Kadaba Section Nittur Sub Division (DP Set-10, 9Mt Pole-60 No, Rabbit Wire-8.648 KM) | Maintenance Work | Y-24372/26.03.21 |  | 11-09-2021 | Koppa,kunnala,lingammanahally,konnemadanahally,konnakere,jeeganahally |  |  | 10:00 | 18:00 | 8:00 | DUE TO RAIN LC NOT AVAILED
86 | WEST | RAJAJINAGAR | N8 | Mallathahalli | Srigandakaval | F-04 | 427, 429 | Conversion of 11KV Overhead line into HT Ug Cable inFeeder SGK F-04 (O&M Mallathahalli) N8 Sub Division,Rajaji nagar Division Bangalore West Circle, BMAZ (South), BESCOM under PHASE-I on Total turnkey under Rate Contract (RC.05) on Percentage basis quoting. | CAPEX | 2020/RN/14-1927/N-106365/12.01.2021 |  | 11-09-2021 | Sir MV 9th block and surrounding areas | 0 | 380 | 10:30 | 17:30 | 7:00 | Works includes Srtinging of LT ab Cable one day and connecting servicing connections and load balancing one day
87 | WEST | RAJAJINAGAR | N8 | S G Kaval | Byadarahalli | F-01 | 79, 283 | Conversion from HT OH to HTUG Work | CAPEX | 2020/RN/14-1927/N-106369/10.03.2021 |  | 11-09-2021 | Rajivgandi Nagar, Byraveshwara Nagara, Near wild kraft, Kebbehalli, Hanumantharayana Palya, | 0 | 5927 | 10:30 | 17:30 | 7:00
88 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | NITTUR | NITTUR220/110/11 KV | F16-SOPANAHALLI.F19-BOMMENAHALLI,F3-SAGAGARANAHALLI,F4-M.S.HALLI,F2-YALLAPURA,F5-HEMAVATHI,F6-THYAGATUR | 11 KV Feeder DTC 215 | For Providing Evacation of New 11 KV Link Line NITTUR MUSS to ADALAGERE PUMP HOUSE Village Limits to Biforcate Load From F3-SAGARANAHALLI FeederIN NITTUR Muss in NITTUR Section Nittur Sub Division (DP Set-10, 9Mt Pole-58 No, Rabbit Wire-7.605 KM) | Maintenance Work | Y-24373/26.3.21 |  | 11-09-2021 | SAGARANAHALLI,THYAGATUR,M.S.HALLI,YALLAPURA,BOMMENAHALLI,KUNDURANAHALLI. |  |  | 10:00 | 18:00 | 8:00
89 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | NITTUR | NITTUR220/110/11 KV | F15-NITTUR,F8-HESARAHALLI,F7-BENACHIGERE,F9-BELAVATHA | 11 KV Feeder DTC 183 | For replacement of existing 11 KV over head lines by 11 KV covered conductor from various locations in Nittur Section. | CAPEX | W-1243/18.3.2020 |  | 11-09-2021 | NITTUR,Mathighatta.HESARAHALLI |  |  | 10:00 | 18:00 | 8:00
90 | TUMKUR CIRCLE | TUMKUR DIVISION | NT1 | KADABA | KADABA-110/11KV | F03-BELAVATHA, F013 thogarighatta, F11 Belavatha NJY | 11 KV Feeder DTC 84 | Kadaba Muss To Belavatha Village limits Biforcate Over loaded F-9 Belavatha Feeder | Capex | Y-402 31.03.21 |  | 11-09-2021 | ADAGONDANAHALLI , BELAVATHA,LAKSHMIPURA |  |  | 10:00 | 18:00 | 8:00 | DUE TO RAIN LC NOT AVAILED
91 | TUMKUR CIRCLE | MADHUGIRI DIVISION | PG1 | Mangalawada | Mangalawada 66/11KV | F10 C.K.Pura NJY | DTC 12 | For LT reconductoring of 2/4 ACSR by Rabbit Conductor at Devarahatti Village limits 25 KVA DTC in Mangalawada Section | CAPEX | R-33861/18.02.2021 |  | 11-09-2021 | Devarahatti |  |  | 10:00 | 17:00 | 7:00
92 | TUMKUR CIRCLE | MADHUGIRI DIVISION | PG1 | O&M-1 | Pavagada 66/11KV | F01 Pavagada Town | DTC 24 | For replacement of existing 11 KV overhead lines by 11 KV Covered condcutor from SSK DP to Tumkur Road & Banashankari Layout in Pavagada O&M-1 | CAPEX | S-5804/14.06.2021 |  | 11-09-2021 | Pavagada Town & Roppa Village |  |  | 10:00 | 17:00 | 7:00
93 | TUMKUR CIRCLE | MADHUGIRI DIVISION | MG1 | O&M1 | MADHUGIRI 66/11kV | F02-MADHUGIRI TOWN | DTC 118 | For MAINTENANCE WORK OF 11KV F02-TOWN FEEDER Madhugiri O&M-1 Section | Maintenance Work | _ |  | 11-09-2021 | MADHUGIRI TOWN AREA |  |  | 10:00 | 16:00 | 6:00
94 | TUMKUR CIRCLE | MADHUGIRI DIVISION | SR1 | BARGURU | P N HALLI | F10 RAGALAHALLI , F8 AGRAHARA, F7 P M HALLI | SDP LT RECONDUCTING DTC 1 | For LT Reconductoring of of 2/4 ACSR by rabbit conductor in LT Line at Gonihalli Baragur section Sira CSD | CAPEX | R-33587/18.02.2021 |  | 11-09-2021 | GONIHALLI |  |  | 12:00 | 18:00 | 6:00
95 | TUMKUR CIRCLE | TIPTUR DIVISION | TU1 | o&m2 | Turuvekere | F1 Mallagatta F3 Hemavathi F8 Anekere F13 Turuvekere F15 Gonitumkur F16 Court | 11 KV Feeder | Estimate for replacement of existing 11KV RABBIT CONDUCTOR by 11KV covered conductor at varios locations of F-13 TURUVEKERE TOWN | Capex | C-57228 05.06.2021 |  | 11-09-2021 | Turuvekere town, Marasarakottige Mallaghatta, kodigehalli, T Hosahalli, Anekere, Kolghatta, Chikkaturuvekere, Guddenahalli, |  |  | 10:00 | 17:00 | 7:00
96 | WEST | RAJAJINAGAR | N8 | Mallathahalli | Sir MV | F-01 | 342, 339, 205 | Conversion of 11KV Overhead line into HT Ug Cable inFeeder F-01 (O&M Mallathahalli) N8 Sub Division,Rajaji nagar Division Bangalore West Circle, BMAZ (South), BESCOM under PHASE-I on Total turnkey under Rate Contract (RC.05) on Percentage basis quoting. | CAPEX | 2020/RN/14-1927/N-106255/02.11.2020 |  | 11-09-2021 | Railway Layout and surrounding areas | 2 | 500 | 10:30 | 17:30 | 7:00 | Works includes Srtinging of LT ab Cable one day and connecting servicing connections and load balancing one day